## FY 2021-22
PROJECTS COMPLETED DURING FY 2021-22
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of completion | Work order No. & Date | Estimated cost (Rs. Cr.) | Awarded Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 12/2022 (Rs. Cr.)
1 | 2X20MVA, 132/33kV Grid S/S at Thuapalli and associated line (JICA) | 04.11.2020 | 30.06.2021 | 14.07.2021 | M/s Angelique International Ltd., New Delhi W.O. No: 2788, Dtd 05.05.2017. | 41.43 | 39.6 | 38.86
2 | 2x40MVA 220/33kV Grid S/S at Telkoi and associated 220kV LILO line from 220kV TTPS-Joda Line. | 08/2020 | 31.07.2021 | 14.07.2021 | M/s. A.K.Das Associates ltd. JV GPIL W.O. No. 4371 dt. 20.08.2018 | 55.71 | 43.9 | 38.63
3 | 132kV Digapahandi-Aska DC line & 132KV Fdr. Bay Extns. | 02/2020 | 06/2021 | 21.07.2021 | M/s Bharati Constructions, Bhubaneswar. W.O. No. dt.30.03.2018 | 26.32 | 25.92 | 26.11
4 | 2X20 MVA,220/33 kV Grid S/S at Sunamunda, Deogarh alongwith associated line (JICA) | 06.06.2019 | 30.06.2021 | 06.08.2021 | M/s Angelique International Ltd. WO 2788 dt.05.05.2017 | 44.33 | 46.8 | 50.25
5 | 2X20 MVA, 220/33 kV Grid S/S at Aunlabahal, Lephripada alongwith associated line.(JICA) | 06.06.2019 | 31.05.2021 | 08.08.2021 | M/s Angelique International Ltd. WO 2788 dt.05.05.17 | 42.15 | 40.17 | 37.07
6 | 132kV Kuchei- Bangiriposi S/C Line with one no feeder bay extension at both end | 01/2020 | 06/2021 | 14.08.2021 | M/s JDC Infratech Pvt. Ltd, Balasore. W.O. no.3654 dt.04.07.2018 | 16.46 | 15.11 | 11.75
7 | 2X20MVA 132/33kV Grid S/S at Rajnagar & associated line | 08/2020 | 08/2021 | 28.08.2021 | M/s STELMEC LTD. W.O No. 4296 dt. 16.08.2018 | 48.17 | 43.65 | 38.13
8 | 2X20MVA 132/33kV Grid S/S at Gondia & associated line. | 08/2020 | 08/2021 | 31.08.2021 | M/s STELMEC LTD. W.O No. 4296 Dtd. 16.08.2018 | 42.71 | 42.42 | 35.5
9 | 132kV SC line on DC tower from PADAMPUR Grid S/S to NUAPADA Grid S/S with 132kV feeder bay extension at both s/s end. | 30.06.2017 for original WO 01.03.2020 for balance work | 31.08.2021 | 06.08.2021 | Offloaded from M/S Fedders Lloyed Corporation Limited, LOA No-8745 Dt 31.12.2014. Balance Work awarded to M/S Abhisek Contech (I) Pvt. Ltd., | 37.69 | 37.42 | 38.91
10 | 2 nos. 220kV feeders from 220/132/33kV Grid S/S of OPTCL at JAYANAGAR to 400/220kV Grid S/S of PGCIL at Jayanagar | 21.11.2020 | 31.07.2021 | 08.07.2021 | M/s Maa Durga Engineering Associates,W.O.No-1793 Dt 07.10.2020 | 22.32 | 16.46 | 16.48
11 | 132kV Podagada-Potangi line along with bay extension at both end. | 17.01.2021 | 31.07.2021 | 30.10.2021 | M/s Siddhartha Engineering Ltd. LOI No- 16-2018-19 Dt 18.01.2019 | 25.12 | 22.79 | 21.61
12 | 2 x 20 MVA, 132/33kV Grid Sub-Station (AIS) with SAS at Nabarangpur with associated line. | 01.03.2021 | Not Revised | 29.12.2021 | M/s Siddhartha Engineering Ltd W.O. No. 991(14) dt. 01.03.2019 | 39.17 | 30.69 | 25.45
13 | 2x500MVA, 400/220kV GIS at Meramundali-B. | 2019-06-29 | 31-09-2021 | 08.01.2022 | Sr.GM-CPC-I-e-Tender-(Meramandali-B)-(Pkg-57/2016-17)/48/2016 (PT-I)/7354 dated 30.12.2017 | Rs. 171.79 Cr (Contract Cost : Rs.143.39Cr.+ Trf cost Rs. 28.4 Cr.) Revised | Rs. 171.79 Cr (Contract Cost : Rs.143.39Cr.+ Trf cost Rs. 28.4 Cr.) Revised | 171.79
14 | 220/132kV S/S at Kesinga with associated 220kV Line & 02 Nos. Bay Extn. at Bolangir. Balane work of 220kV Bolangir-Kesimga DC line by RCH of OPTCL (material supplied by OPTCL) | Balance work by RCH dated '07/2020) | 31.03.2022 | 04.03.2022 | M/S A.K. Das associates W.O No. 4503 (Erection) & 4498 (Supply) dt.27.07.12. Work Order issued to (RCH)Order No-120 dt 12.01.2018 | Initial Estimated at 82.67 Cr. and Revised to Rs. 110.00 Cr. | Rs. 57.26 Cr. to M/s A.K. Das and offloaded. Then work executed departmentally | 111.55
15 | 2 X 40MVA, 132/33kV Gas (SF6) Insulated Sub-Station with SAS at Hirakud, Sambalpur. | 22.02.2020 | 31.03.2022 | 17.03.2022 | M/s GE T & D India Ltd., LOA No: 4455, Dtd 23.08.2018 | 48.4 | 33.01 | 31.47

## FY 2022-23
PROJECTS COMPLETED DURING FY 2022-2023 till December '2022
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of completion | Work order No. & Date | Estimated cost (Rs. Cr.) | Awarded Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 12/2022 (Rs. Cr.)
1 | 2x20MVA, 132/33kV Grid S/s at Birmaharajpur with line.(Off loaded from M/s Fedders.Paid : Rs.18.17 Cr..Again Revised Awarded Cost : Rs.14.35Cr. | 12/2020 | 04/2022 | 13.05.2022 | The work Offloaded from M/s Feeders and the balance work awarded to M/s S.B.Electrostructurels Pvt.Ltd. JV with M/s Feedback Energy Distribution Co. Ltd. Order No- 1109 Dt 08.03.2019. | 32.52 | 32.52 | 33.12* |  | 33.12
2 | 2X63MVA, 220/33kV Gas Insulated Sub-station at Godisahi | 08/2020 | 08/2022 | 21.06.2022 | M/s Toshiba Transmission & Distribution System(India) Pvt. Ltd. W.O No. 118 dt. 22.02.2019 | 95.34 (for both Godishahi & Kantabada) | 95.34 | 43.22* (Godishahi)
3 | 2X40MVA,132/33kV GIS sub-station at Hinjili. | 08/2020 | 01/2022 | 29.07.2022 | M/s GE T&D India Ltd.W.O No.659 dtd. 14.02.2019. | 35.72 | 35.72 | 27.93* |  | 27.93
4 | 2X40MVA, 132/33kV Grid S/S at Atuda, Bahugram with associated 132kV line. | 03/2021 | 06/2022 | 03.08.2022 | M/s Siddharth Engineering Ltd. JV M/s Asthavinayaka Construction. W.O No-1078 dt. 08.03.2019 | 36.61 | 33.59 | 27.97* |  | 27.97
5 | 2X20MVA, 132/33kV Grid S/S at Chandipur with associated 132kV line. | 02/2021 | 02/2022 | 30.08.2022 | M/s STELMEC LTD.JV with M/s Laxmi Transmission,W.O No. 701 dt. 18.02.2019 | 46.84 | 41.8 | 32.58* |  | 32.58
6 | 2x160MVA + 2x20MV, 220/132/33kV Grid S/S with SAS at Bamra and associated 220kV LILO line | 05/2020 | 08/2022 | 04.09.2022 | M/s Empowertrans Pvt Ltd. W.O. No.2410 dt.16.05.2018 | 81.87 | 77.76 | 77.78* |  | 77.78
7 | 2x20MVA 220/33KV Grid S/S at Kalimela & line | 02/2018 | 06/2020 | 11/2022 | M/s Flowmore Limited, LOA No-1032 Dt 11.02.2015 | 70.16 | 66.39 | 63.01*
8 | 220kV DC line from 400/220kV S/S Pandiabil (Benapanjari) of PGCIL to 220/132/33kV S/S Pratapasasan. | 09/2017 | 04/2019 | 19.05.2022 | M/s Fedders Lloyd Corpn.Ltd. LOA 9551 & 9556 dt.22.09.2015 | 29.15 | 27.95 | 27.20*
9 | 132KV ABREL Sw. S/s. |  |  | 31.05.2022 |  | Benificiary work
Estimated Cost : Included with project award cost(contract cost) along with Transformer cost & overhead cost ( such as transportation 5%,Contigency 3% & price escallation 10% as per guide line of OERC. ** Awarded cost: Actual Contract value
*Actual Expenditure is un-audited.Also minimum spill over work is going on. | [8 empty] | 27.2
1350.0975
1350.0975