## 2022-23
PROJECTS COMPLETED DURING FY 2022-2023 till December '2022
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of completion | Work order No. & Date | Estimated cost (Rs. Cr.) | Awarded Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 12/2022 (Rs. Cr.)
1 | 2x20MVA, 132/33kV Grid S/s at Birmaharajpur with line.(Off loaded from M/s Fedders.Paid : Rs.18.17 Cr..Again Revised Awarded Cost : Rs.14.35Cr. | 12/2020 | 04/2022 | 13.05.2022 | The work Offloaded from M/s Feeders and the balance work awarded to M/s S.B.Electrostructurels Pvt.Ltd. JV with M/s Feedback Energy Distribution Co. Ltd. Order No- 1109 Dt 08.03.2019. | 32.52 | 32.52 | 33.12* |  | 33.12
2 | 2X63MVA, 220/33kV Gas Insulated Sub-station at Godisahi | 08/2020 | 08/2022 | 21.06.2022 | M/s Toshiba Transmission & Distribution System(India) Pvt. Ltd. W.O No. 118 dt. 22.02.2019 | 95.34 (for both Godishahi & Kantabada) | 95.34 | 43.22* (Godishahi)
3 | 2X40MVA,132/33kV GIS sub-station at Hinjili. | 08/2020 | 01/2022 | 29.07.2022 | M/s GE T&D India Ltd.W.O No.659 dtd. 14.02.2019. | 35.72 | 35.72 | 27.93* |  | 27.93
4 | 2X40MVA, 132/33kV Grid S/S at Atuda, Bahugram with associated 132kV line. | 03/2021 | 06/2022 | 03.08.2022 | M/s Siddharth Engineering Ltd. JV M/s Asthavinayaka Construction. W.O No-1078 dt. 08.03.2019 | 36.61 | 33.59 | 27.97* |  | 27.97
5 | 2X20MVA, 132/33kV Grid S/S at Chandipur with associated 132kV line. | 02/2021 | 02/2022 | 30.08.2022 | M/s STELMEC LTD.JV with M/s Laxmi Transmission,W.O No. 701 dt. 18.02.2019 | 46.84 | 41.8 | 32.58* |  | 32.58
6 | 2x160MVA + 2x20MV, 220/132/33kV Grid S/S with SAS at Bamra and associated 220kV LILO line | 05/2020 | 08/2022 | 04.09.2022 | M/s Empowertrans Pvt Ltd. W.O. No.2410 dt.16.05.2018 | 81.87 | 77.76 | 77.78* |  | 77.78
7 | 2x20MVA 220/33KV Grid S/S at Kalimela & line | 02/2018 | 06/2020 | 11/2022 | M/s Flowmore Limited, LOA No-1032 Dt 11.02.2015 | 70.16 | 66.39 | 63.01*
8 | 220kV DC line from 400/220kV S/S Pandiabil (Benapanjari) of PGCIL to 220/132/33kV S/S Pratapasasan. | 09/2017 | 04/2019 | 19.05.2022 | M/s Fedders Lloyd Corpn.Ltd. LOA 9551 & 9556 dt.22.09.2015 | 29.15 | 27.95 | 27.20*
9 | 132KV ABREL Sw. S/s. |  |  | 31.05.2022 |  | Benificiary work
Estimated Cost : Included with project award cost(contract cost) along with Transformer cost & overhead cost ( such as transportation 5%,Contigency 3% & price escallation 10% as per guide line of OERC. ** Awarded cost: Actual Contract value
*Actual Expenditure is un-audited.Also minimum spill over work is going on. | [8 empty] | 27.2
1350.0975
1350.0975

## 2021-22
PROJECTS COMPLETED DURING FY 2021-22
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of completion | Work order No. & Date | Estimated cost (Rs. Cr.) | Awarded Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 12/2022 (Rs. Cr.)
1 | 2X20MVA, 132/33kV Grid S/S at Thuapalli and associated line (JICA) | 04.11.2020 | 30.06.2021 | 14.07.2021 | M/s Angelique International Ltd., New Delhi W.O. No: 2788, Dtd 05.05.2017. | 41.43 | 39.6 | 38.86
2 | 2x40MVA 220/33kV Grid S/S at Telkoi and associated 220kV LILO line from 220kV TTPS-Joda Line. | 08/2020 | 31.07.2021 | 14.07.2021 | M/s. A.K.Das Associates ltd. JV GPIL W.O. No. 4371 dt. 20.08.2018 | 55.71 | 43.9 | 38.63
3 | 132kV Digapahandi-Aska DC line & 132KV Fdr. Bay Extns. | 02/2020 | 06/2021 | 21.07.2021 | M/s Bharati Constructions, Bhubaneswar. W.O. No. dt.30.03.2018 | 26.32 | 25.92 | 26.11
4 | 2X20 MVA,220/33 kV Grid S/S at Sunamunda, Deogarh alongwith associated line (JICA) | 06.06.2019 | 30.06.2021 | 06.08.2021 | M/s Angelique International Ltd. WO 2788 dt.05.05.2017 | 44.33 | 46.8 | 50.25
5 | 2X20 MVA, 220/33 kV Grid S/S at Aunlabahal, Lephripada alongwith associated line.(JICA) | 06.06.2019 | 31.05.2021 | 08.08.2021 | M/s Angelique International Ltd. WO 2788 dt.05.05.17 | 42.15 | 40.17 | 37.07
6 | 132kV Kuchei- Bangiriposi S/C Line with one no feeder bay extension at both end | 01/2020 | 06/2021 | 14.08.2021 | M/s JDC Infratech Pvt. Ltd, Balasore. W.O. no.3654 dt.04.07.2018 | 16.46 | 15.11 | 11.75
7 | 2X20MVA 132/33kV Grid S/S at Rajnagar & associated line | 08/2020 | 08/2021 | 28.08.2021 | M/s STELMEC LTD. W.O No. 4296 dt. 16.08.2018 | 48.17 | 43.65 | 38.13
8 | 2X20MVA 132/33kV Grid S/S at Gondia & associated line. | 08/2020 | 08/2021 | 31.08.2021 | M/s STELMEC LTD. W.O No. 4296 Dtd. 16.08.2018 | 42.71 | 42.42 | 35.5
9 | 132kV SC line on DC tower from PADAMPUR Grid S/S to NUAPADA Grid S/S with 132kV feeder bay extension at both s/s end. | 30.06.2017 for original WO 01.03.2020 for balance work | 31.08.2021 | 06.08.2021 | Offloaded from M/S Fedders Lloyed Corporation Limited, LOA No-8745 Dt 31.12.2014. Balance Work awarded to M/S Abhisek Contech (I) Pvt. Ltd., | 37.69 | 37.42 | 38.91
10 | 2 nos. 220kV feeders from 220/132/33kV Grid S/S of OPTCL at JAYANAGAR to 400/220kV Grid S/S of PGCIL at Jayanagar | 21.11.2020 | 31.07.2021 | 08.07.2021 | M/s Maa Durga Engineering Associates,W.O.No-1793 Dt 07.10.2020 | 22.32 | 16.46 | 16.48
11 | 132kV Podagada-Potangi line along with bay extension at both end. | 17.01.2021 | 31.07.2021 | 30.10.2021 | M/s Siddhartha Engineering Ltd. LOI No- 16-2018-19 Dt 18.01.2019 | 25.12 | 22.79 | 21.61
12 | 2 x 20 MVA, 132/33kV Grid Sub-Station (AIS) with SAS at Nabarangpur with associated line. | 01.03.2021 | Not Revised | 29.12.2021 | M/s Siddhartha Engineering Ltd W.O. No. 991(14) dt. 01.03.2019 | 39.17 | 30.69 | 25.45
13 | 2x500MVA, 400/220kV GIS at Meramundali-B. | 2019-06-29 | 31-09-2021 | 08.01.2022 | Sr.GM-CPC-I-e-Tender-(Meramandali-B)-(Pkg-57/2016-17)/48/2016 (PT-I)/7354 dated 30.12.2017 | Rs. 171.79 Cr (Contract Cost : Rs.143.39Cr.+ Trf cost Rs. 28.4 Cr.) Revised | Rs. 171.79 Cr (Contract Cost : Rs.143.39Cr.+ Trf cost Rs. 28.4 Cr.) Revised | 171.79
14 | 220/132kV S/S at Kesinga with associated 220kV Line & 02 Nos. Bay Extn. at Bolangir. Balane work of 220kV Bolangir-Kesimga DC line by RCH of OPTCL (material supplied by OPTCL) | Balance work by RCH dated '07/2020) | 31.03.2022 | 04.03.2022 | M/S A.K. Das associates W.O No. 4503 (Erection) & 4498 (Supply) dt.27.07.12. Work Order issued to (RCH)Order No-120 dt 12.01.2018 | Initial Estimated at 82.67 Cr. and Revised to Rs. 110.00 Cr. | Rs. 57.26 Cr. to M/s A.K. Das and offloaded. Then work executed departmentally | 111.55
15 | 2 X 40MVA, 132/33kV Gas (SF6) Insulated Sub-Station with SAS at Hirakud, Sambalpur. | 22.02.2020 | 31.03.2022 | 17.03.2022 | M/s GE T & D India Ltd., LOA No: 4455, Dtd 23.08.2018 | 48.4 | 33.01 | 31.47

## CWIP (18)
Project wise,Scheme wise,Source of funding wise of Capital Work in Progress(CWIP) position of Transmisssion projects
(i) CWIP position of project started on or before 31.03.2022
Sl. No. | Scheme Name | Project Name | Contract / Award Cost (Rs. In Cr.) | Source of Funding (Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date (Rs. In Cr.) | [5 empty] | Expenditure incurred / to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | Start | Complete / Expected completion | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | upto 31.03.2022 | FY 2022-23 | FY 2023-24 | FY 2024-25 | Total
1 | SCRIPS | 2X160MVA 220/132kV & 2X63MVA 132/33kV, 220/132/33kV GIS at Balianta (Benupur), BBSR and associated line using monopole | 139.2 |  |  | 139.2 |  |  |  | 03/2019 | 06/2023 |  |  | 66.46 |  |  |  | 16.38 | 47.626 | 18 | 57.194 | 139.2
|  | 2X63MVA, 132/33kV GIS at Nayapalli, BBSR | 87.88 |  |  | 87.88 |  |  |  | 03/2019 | 07/2023 |  |  | 42.47 |  |  |  | 36.22 | 14.14 | 15 | 22.52 | 87.88
|  | 2X63MVA, 132/33kV GIS at Satyanagar, BBSR | 170.65 |  |  | 170.65 |  |  |  | 02/2019 | 02/2024 |  |  | 74.04 |  |  |  | 57.47 | 21.96 | 55 | 36.22 | 170.65
2X63MVA, 132/33kV GIS at Badagada, BBSR
|  | 2X63MVA, 220/33kV GIS at Kantabada, Gothapatna | 95.34 (Kantabada+ Godishahi) |  |  | 95.34 |  |  |  | 02/2019 | 03/2023 |  |  | 48.04 |  |  |  | 60.63 (Kantabada+ Godishahi) | 35.02 (Kantabada + Godishahi) | 15 | -0.31
2 | DRPS | 132kV DC line from 132/33kV GIS Chandbali to 220/132/33kV Grid S/S at Balimunda, Dhamara. | 19.4 |  |  | 19.4 |  |  |  | 01/2019 | 03/2023 |  |  | 19.4 |  |  |  | 16.23 | 2 | 1.17
3 | RRCP | 132kV D/C line from Parlakhemundi to R.Udayagiri. | 41.82 |  |  | 41.82 |  |  |  | 03/2018 | 06/2023 |  |  | 41.82 |  |  |  | 27.44 | 7.1 | 7.28
|  | 132kV D/C line from Lapanga to Brajrajnagar with diversion of 220kV IB - Budhipdara DC line. | 12.44 |  |  | 12.44 |  |  |  | 02/2017 | 03/2023 |  |  | 12.44 |  |  |  | 5.87 | 2.5 | 4.07
|  | 220kV LILO line from 220kV Theruvalli-Narendrapur DC line to 220/132/33kV Grid S/S at Aska | 39.08 |  |  | 39.08 |  |  |  | 12/2018 | 03/2023 |  |  | 39.08 |  |  |  | 26.61 | 6 | 6.47
|  | 132kV Boudh-Phulbani DC line with bay extn. at both ends | 44.98 |  |  | 44.98 |  |  |  | 03/2016 | 06/2023 | [6 empty] | 44.78
4 | DRC | Installation of 3rd ICT with 400kV & 220kV bay extension at New Duburi | 19.8 |  |  | 19.8 |  |  |  | 05/2018 | 03/2023 (waiting ICT) |  |  | 19.8 |  |  |  | 14.91 | 3 | 1.89
5 | SSP (System Strengthing Project) | 2X 40MVA 220/33kV Grid S/S at Palei, Balichandrapur with line. | 41.77 | 12.531 | 29.239 |  |  |  |  | 02/2019 | 06/2023 |  |  | 14.15 |  |  |  | 8.14 | 20 | 13.63
|  | 2x160MVA+2x40MVA, 220/132/33kV Grid S/S, Dhamara with line | 89.5 | 26.85 | 62.65 |  |  |  |  | 06/2018 | 03/2023 |  |  | 24.58 |  |  |  | 47.82 | 30 | 11.68
|  | 2X40MVA, 132/33kV Grid S/S at Bhatli along with line | 52.3 | 15.69 | 36.61 |  |  |  |  | 11/2018 | 03/2023 |  |  | 15.66 |  |  |  | 38.69 | 12 | 1.61
|  | 2X20MVA, 132kV Grid S/S Lamtaput with SAS and associated line. | 26.32 | 7.896 | 18.424 |  |  |  |  | 11/2018 | 03/2023 |  |  | 10.54 |  |  |  | 15.87 | 10 | 0.45
|  | 132kV DC line from 220/132/33kV S/S Baner (Jaipatna) to 132/33kV S/S at Junagarh | 36.46 | 10.938 | 25.522 |  |  |  |  | 08/2019 | 05/2023 |  |  | 10.99 |  |  |  | 8.61 | 20 | 7.85
|  | Diversion of 400kV & 220kV lines with 220kV LILO arrangement for connectivity with 400/220kV GIS at Meramundali-B. | 41.53 | 0 | 29.071 |  |  | 12.459 |  | 03/2019 | 03/2023 |  |  |  | 13.08 |  |  | 27.29 | 7 | 7.24
6 | GoO Rs. 300 Cr. Equity Support | 2x160 MVA + 2 x 40 MVA, 220/132/33kV S/S at Kuanrmunda and associated line | 109.39 | 23.17 | 86.22 |  |  |  |  | 05/2018 | 01/2023 | 23.171 | 49.4244 |  |  |  |  | 108.95 | 5.54 | 0
|  | 2x20MVA, 220/33kV S/S at Baliguda and associated line | 138.94 | 37.4294 | 101.5106 |  |  |  |  | 02/2015 | 03/2023 | 37.4294 | 63.647 |  |  |  |  | 110.27 | 4.06 | 24.61
|  | 2x20MVA, 132/33kV R.Udyagiri S/S and associated line | 48.02 | 16.7901 | 31.2299 |  |  |  |  | 09/2014 | 01/2023 | 16.7901 | 28.5508 |  |  |  |  | 43.25 | 1 | 3.77
|  | 2x20MVA, 132/33kV Grid S/S at Boriguma and associated line | 35.113 | 7.5884 | 27.5246 |  |  |  |  | 02/2019 balance work | 03/2023 | 7.5884 | 13.0834 |  |  |  |  | 18.06 | 0 | 17.053
|  | 132kV Jayanagar-Sunabeda line | 24.97 | 7.7289 | 17.2411 |  |  |  |  | 07/2013 | 01/2023 | 7.7289 | 13.1627 |  |  |  |  | 19.31 | 1 | 4.66
7 | GoO Equity Support | 2x500MVA, 400/220/33kV GIS at Paradeep and associated line | 686.82 | 191.24 | 495.58 |  |  |  |  | Line:12/2021,GSS:12/2022 | 03/2024 |  |  | 186.24 |  |  |  | 2.73 | 50 | (FY2023-24)365.00 Cr , (FY2024-25)269.00 Cr
8 | 100% Govt. Support | 2X20MVA, 132/33KVGSS at Brundabahal with associated line | 45.54 | 58.12 | [5 empty] | 02/2021 | 05/2023 |  |  | 58.12 |  |  |  | 5.22 | 20 | 20.32
|  | 132/33 KV S/S at Tarabha with associated 132kV LILO Line | 26.53 | 26.53 | [5 empty] | 12/2021 | 06/2023 |  |  | 13.69 |  |  |  | 1.32 | 15 | 10.21
9 | JICA | 2x20 MVA, 220/33kV S/S at Dasapalla with associated line | 59.26 |  | 41.482 |  | 8.1429 | 9.6351 | 59.26 | 01/2018 | 03/2023 |  |  | 26.306 | 8.1429 |  |  | 37.58 | 10 | 11.68
|  | 2x160MVA + 1x20MVA, 220/132/33kV S/S at Kiakata with associated lines | 160.19 |  | 112.133 |  | 8.1429 | 39.9141 | 160.19 | 01/2018 | 06/2023 |  |  | 77.434 | 8.1429 |  |  | 110.62 | 20 | 29.57
|  | 2X20MVA, 132/33kV Grid S/S at Kudaloi, Lakhanpur with associated lines | 46.42 |  | 32.494 |  | 8.1429 | 5.7831 | 46.42 | 05/2017 | 02/2023 |  |  | 25.641 | 8.1429 |  |  | 36.63 | 6.11 | 3.68
|  | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga with associated line. | 103.12 |  | 72.184 |  | 8.1429 | 22.7931 | 103.12 | 02/2019 | 06/2023 |  |  | 53.326 | 8.1429 |  |  | 76.18 | 20 | 6.94
(ii) CWIP position of project started on or after 01.04.2022 to till date
Sl.No. | Scheme Name | Project Name | Contract/ Award Cost (Rs. In Cr.) | Source of Funding(Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date(Rs. In Cr.) | [5 empty] | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other |  | Total | Start | Complete | Equity | Debt | Grant | Other |  | Total | Till date of FY 2022-23 | Total in FY2022-23 | FY2023-24 |  | Total
1 | RRCP-II | 132kV LILO of one ckt of Budhipadar-Sundergarh line at Bamra | 31.3 | 9.39 | 21.91 |  |  |  |  | 11/2022 | 11/2025 | 4.94
|  | 132kV SC on DC Tower from Kantabanji to Patnagarh | 24.25 | 7.275 | 16.975 |  |  |  |  | 11/2022 | 11/2024 | 4.94
|  | 132kV SC Line on DC Tower from Ghense to Padampur | 22.94 | 6.882 | 16.058 |  |  |  |  | 12/2022 | 12/2024 | 3.96
2 | LVMS | 132/33kV Athamallick S/s with associated line | 39.65 | 11.895 | 27.755 |  |  |  |  | 10/2022 | 10/2024 | 7.51
(iii) Project in hands will be started from till dated to by the end of 31.03.2024
Sl.No. | Scheme Name | Project Name | Tentative Estimated Cost (Rs. In Cr.) | Source of Funding(Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date(Rs. In Cr.) | [5 empty] | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other |  | Total | Start | Complete | Equity | Debt | Grant | Other |  | Total | FY 2022-23 | FY 2023-24 | After FY 2023-24 |  | Total
1 | RRCP-II | 220kV Balimela_Jayanagar LILO at Govindpalli | 7.552 | 2.2656 | 5.2864 | [6 empty] | 1.31
|  | 132kV LILO of Chend-Adhunik Line at Kuanramunda | 2.03 | 0.609 | 1.421 | [6 empty] | 1.5
2 | LVMS | 132/33kV Agalpur(Rampur) S/s with SAS with associated line | 36.75 | 11.025 | 25.725 | [6 empty] | 7.08
|  | 220/33kV S/s at M. Rampur with associated line | 63.18 | 18.954 | 44.226 | [6 empty] | 12.18
|  | 220/33kV S/s at Chitalo with associated line | 90 | 27 | 63 | [6 empty] | 17.35
|  | 132kV line from Turumunga to Dhenkikote | 30.5 | 9.15 | 21.35 | [6 empty] | 5.88

## CWIP (FINAL)
Project wise,Scheme wise,Source of funding wise of Capital Work in Progress(CWIP) position of Transmisssion projects
(i) CWIP position of project started on or before 31.03.2022
Sl. No. | Scheme Name | Project Name | Contract / Award Cost (Rs. In Cr.) | Source of Funding (Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date (Rs. In Cr.) | [5 empty] | Expenditure incurred / to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | Start | Complete | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | upto 31.03.2022 | FY 2022-23 | FY 2023-24 | FY 2024-25 | Total
1 | SCRIPS | 2X160MVA 220/132kV & 2X63MVA 132/33kV, 220/132/33kV GIS at Balianta (Benupur), BBSR and associated line using monopole | 139.2 |  |  | 139.2 |  |  |  | 03/2019 | WIP |  |  | 66.46 |  |  |  | 16.38 | 47.626 | 18 | 57.194 | 139.2
2 |  | 2X63MVA, 132/33kV GIS at Nayapalli, BBSR | 87.88 |  |  | 87.88 |  |  |  | 03/2019 | WIP |  |  | 42.47 |  |  |  | 36.22 | 14.14 | 15 | 22.52 | 87.88
3 |  | 2X63MVA, 132/33kV GIS at Satyanagar, BBSR | 170.65 |  |  | 170.65 |  |  |  | 02/2019 | WIP |  |  | 74.04 |  |  |  | 57.47 | 21.96 | 55 | 36.22 | 170.65
4 |  | 2X63MVA, 132/33kV GIS at Badagada, BBSR | [8 empty] | WIP
5 |  | 2X63MVA, 220/33kV GIS at Kantabada, Gothapatna | 95.34 (Kantabada+ Godishahi) |  |  | 95.34 |  |  |  | 02/2019 | WIP |  |  | 48.04 |  |  |  | 60.63 | 35.02 | 15 |  | 110.34
6 | DRPS | 132 KV DC line from 220/132/33 KV Grid s/s at ASKA to 132/33 KV Grid s/s at Digapahandi on Dc tower with 2Nos of feeder bay extention at both s/s. | 27.02 |  |  | 25.32 |  | 1.7 |  |  | WIP |  |  | 25.32 |  | 1.7 |  | 26.8712 | 0.15 | 0 | -0.0011686 | 110.34
7 |  | Construction of 2 X 40 MVA, 132/33 KV GIS, CHANDBALI with associated line. Deposit Work,Under DRPS Scheme | 39.75 |  |  | 39.75 |  |  |  |  | WIP |  |  | 39.75 |  |  |  | 12.4516 | 6.2397 | 2.12 | 18.9387 | 39.75
8 |  | 132kV DC line from 132/33kV GIS Chandbali to 220/132/33kV Grid S/S at Balimunda, Dhamara. | 19.4 |  |  | 19.4 |  |  |  | 01/2019 | WIP |  |  | 19.4 |  |  |  | 16.23 | 2 | 1.17 |  | 19.4
9 | RRCP | 132kV D/C line from Parlakhemundi to R.Udayagiri. | 41.82 |  |  | 41.82 |  |  |  | 03/2018 | WIP |  |  | 41.82 |  |  |  | 24.44 | 7.1 | 4.33 | 5.95 | 41.82
10 |  | 132kV D/C line from Lapanga to Brajrajnagar with diversion of 220kV IB - Budhipdara DC line. | 12.84 |  |  | 12.44 |  |  |  | 02/2017 | WIP |  |  | 12.44 |  |  |  | 5.93 | 6.91 | 0 |  | 12.84
11 |  | 220kV LILO line from 220kV Theruvalli-Narendrapur DC line to 220/132/33kV Grid S/S at Aska | 39.09 |  |  | 39.08 |  |  |  | 12/2018 | WIP |  |  | 39.08 |  |  |  | 27.79 | 5.85 | 5.45 |  | 39.09
12 |  | 132kV Boudh-Phulbani DC line with bay extn. at both ends | 56.08 |  |  | 56.08 |  |  |  | 03/2016 | WIP |  |  | 56.08 |  |  |  | 43.93 | 4.94 | 7.21 |  | 56.08
13 |  | Const. of 132 KV SC line from proposed 132/33 grid S/s Pottangi to proposed 132/33 KV grid s/s Podagada with bay extension at both end [RRCP] | 25.85 |  |  | 21.31 |  |  |  |  | WIP |  |  | 21.31 |  |  |  | 23.85 | 2 | 0 | -3.5527e-15 | 25.85
14 |  | 132 KV DC Line from Padampur to Nuapada (RRCP Project) | 38.76 |  |  | 38.76 |  |  |  |  | WIP |  |  | 38.76 |  |  |  | 35.5809 | 3.1793 | 0 | -0.00019485 | 38.76
15 |  | 132kV SC line on DC tower from Bhadrak - Andapur (RRCP) | 23.31 |  |  | 23.31 |  |  |  |  | WIP |  |  | 23.31 |  |  |  | 2.01 | 2.22 | 0 | 19.08 | 23.31
16 | DRC | Installation of 3rd ICT with 400kV & 220kV bay extension at New Duburi | 21.49 |  |  | 21.49 |  |  |  | 05/2018 | WIP |  |  | 21.49 |  |  |  | 18.49 | 3 | 0 |  | 21.49
17 | SSP (System Strengthing Project) | 2X 40MVA 220/33kV Grid S/S at Palei, Balichandrapur with line. | 41.77 | 12.531 | 29.239 |  |  |  |  | 02/2019 | WIP | 12.531 | 14.15 |  |  |  |  | 7.35 | 20 | 7 | 7.42 | 41.77
18 |  | 2x160MVA+2x40MVA, 220/132/33kV Grid S/S, Dhamara with line | 89.5 | 26.85 | 62.65 |  |  |  |  | 06/2018 | WIP | 26.85 | 24.58 |  |  |  |  | 52.71 | 29.91 | 1.36 | 5.52 | 89.5
19 |  | 2X40MVA, 132/33kV Grid S/S at Bhatli along with line | 52.3 | 15.69 | 36.61 |  |  |  |  | 11/2018 | WIP | 15.69 | 15.66 |  |  |  |  | 41.2 | 6.1 | 2 | 3 | 52.3
20 |  | 2X20MVA, 132kV Grid S/S Lamtaput with SAS and associated line. | 26.32 | 7.896 | 18.424 |  |  |  |  | 11/2018 | WIP | 7.896 | 10.54 |  |  |  |  | 16.5 | 5 | 4 | 0.82 | 26.32
21 |  | 132kV DC line from 220/132/33kV S/S Baner (Jaipatna) to 132/33kV S/S at Junagarh | 36.46 | 10.938 | 25.522 |  |  |  |  | 08/2019 | WIP | 10.938 | 10.99 |  |  |  |  | 3.65 | 9.64 | 16.01 | 7.16 | 36.46
22 | Own | Diversion of 400kV & 220kV lines with 220kV LILO arrangement for connectivity with 400/220kV GIS at Meramundali-B. | 41.53 | 0 | 29.071 |  |  | 12.459 |  | 03/2019 | WIP | 0 |  |  | 13.08 |  |  | 22.96 | 5.98 | 2 | 10.59 | 41.53
23 | GoO Rs. 300 Cr. Equity Support | 2x160 MVA + 2 x 40 MVA, 220/132/33kV S/S at Kuanrmunda and associated line | 89.3 | 23.17 | 66.13 |  |  |  |  | 05/2018 | WIP | 23.171 | 49.4244 |  |  |  |  | 71.42 | 17.88 | 0 |  | 89.3
24 |  | 2x20MVA, 220/33kV S/S at Baliguda and associated line | 138.94 | 37.4294 | 101.5106 |  |  |  |  | 02/2015 | WIP | 37.4294 | 63.647 |  |  |  |  | 110.27 | 4.06 | 24.61 | 0 | 138.94
25 |  | 2x20MVA, 132/33kV R.Udyagiri S/S and associated line | 51.64 | 16.7901 | 34.8499 |  |  |  |  | 09/2014 | WIP | 16.7901 | 28.5508 |  |  |  |  | 50.64 | 1 |  |  | 51.64
26 |  | 2x20MVA, 132/33kV Grid S/S at Boriguma and associated line | 35.113 | 7.5884 | 27.5246 |  |  |  |  | 02/2019 balance work | WIP | 7.5884 | 13.0834 |  |  |  |  | 22.93 | 8 | 0.1 | 4.083 | 35.113
27 |  | 132kV Jayanagar-Sunabeda line | 26.38 | 7.7289 | 18.6511 |  |  |  |  | 07/2013 | WIP | 7.7289 | 13.1627 |  |  |  |  | 24.48 | 1 | 0.9 |  | 26.38
28 | Paradeep | 2x500MVA, 400/220/33kV GIS at Paradeep and associated line | 686.82 | 191.24 | 495.58 |  |  |  |  | Line:12/2021,GSS:12/2022 | WIP |  |  | 186.24 |  |  |  | 0.39 | 99.76 | 110 | 476.67 | 686.82
29 | 100% Govt. Support | 2X20MVA, 132/33KVGSS at Brundabahal with associated line | 45.54 | 58.12 | [5 empty] | 02/2021 | WIP |  |  | 58.12 |  |  |  | 5.32 | 17.04 | 14.7 | 8.48 | 45.54
|  | 132/33 KV S/S at Tarabha with associated 132kV LILO Line | 26.53 | 26.53 | [5 empty] | 12/2021 | WIP |  |  | 13.69 |  |  |  | 1.44 | 10 | 12 | 3.09 | 26.53
30 | JICA | 2x20 MVA, 220/33kV S/S at Dasapalla with associated line | 61.21 |  | 42.847 |  | 8.1429 | 10.2201 | 61.21 | 01/2018 | WIP |  | 28.42 |  | 8.1429 |  |  | 40.6 | 10 | 10.61 |  | 61.21
31 |  | 2x160MVA + 1x20MVA, 220/132/33kV S/S at Kiakata with associated lines | 174.81 |  | 122.367 |  | 8.1429 | 44.3001 | 174.81 | 01/2018 | WIP |  | 90.349 |  | 8.1429 |  |  | 129.07 | 25.64 | 20.1 | 0 | 174.81
32 |  | 2X20MVA, 132/33kV Grid S/S at Kudaloi, Lakhanpur with associated lines | 46.88 |  | 32.816 |  | 8.1429 | 5.9211 | 46.88 | 05/2017 | WIP |  | 28.924 |  | 8.1429 |  |  | 41.32 | 5.42 | 0.14 | 2.3315e-15 | 46.88
33 |  | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga with associated line. | 110.51 |  | 77.357 |  | 8.1429 | 25.0101 | 110.51 | 02/2019 | WIP |  | 47.796 |  | 8.1429 |  |  | 68.28 | 20 | 22.23 | 0 | 110.51
34 |  | Construction of 132/33 KV Grid S/s at Rajnagar with associated 132 KV Line. | 48.17 |  | 33.719 |  |  | 14.451 |  |  | WIP |  | 47.796 |  |  |  |  | 39.7988 | 1 | 0 | 7.3712 | 48.17
35 |  | Construction of 132/33 KV Grid S/s at Bahugram with associated 132 KV Line. | 37.08 |  | 25.956 |  |  | 11.124 |  |  | WIP |  | 47.796 |  |  |  |  | 31.0794 | 6 | 0 | 0.00056713 | 36.61
36 |  | Const. Of 132/33 kv Grid S/S at Chandipur. | 46.84 |  | 32.788 |  |  | 14.052 |  |  | WIP |  | 47.796 |  |  |  |  | 29.0451 | 10.911 | 1.97 | 4.9138 | 46.84
37 |  | Construction Of 132/33 KV Sub-Station at Gondia, Dhenkanal (JICA Work) | 42.71 |  | 29.897 |  |  | 12.813 |  |  | WIP |  | 47.796 |  |  |  |  | 37.2574 | 1 | 0 | 4.4526 | 42.71
38 |  | 2x20 MVA, 220/33 Grid S/s near Deogarh along with associated LILO arrangement from 220 KV Rengali-Tarkera Transmission Line | 56.02 |  | 39.214 |  |  | 16.806 |  |  | WIP |  | 47.796 |  |  |  |  | 51.74 | 4.2823 | 0 | -0.0023 | 56.02
39 |  | Construction of 220/33 KV Grid S/s at Lephripada along with associated LILO Transmission line from 220 KV Budhipadar-Basundhara line. Est.No. 09/2016-17 | 41.57 |  | 29.099 |  |  | 12.471 |  |  | WIP |  | 47.796 |  |  |  |  | 38.06 | 3.506 | 0 | 0.004 | 41.57
40 |  | Construction of 220/132/33 KV Grid S/s at Gunupur with LILO arrangement of 220 KV line from Therubali-Bhanjanagar as well as 132 KV LILO arrangment of Akhusing to Paralakhemundi. (Sanctioned Est. No. 31/2014-15 of SGM, Zone-II, Sambalpur vide letter no. 89 dtd. 17.01.2015) | 95.45 |  | 66.815 |  |  | 28.635 |  |  | WIP |  | 47.796 |  |  |  |  | 82.2963 | 4.37 | 1 | 7.7837 | 95.45
41 |  | 132/33 KV Grid S/S Thuapali (Deshbhatli) & Associated Line | 41.43 |  | 29.001 |  |  | 12.429 |  |  | WIP |  | 47.796 |  |  |  |  | 37.2952 | 1.495 | 0 | 2.6398 | 41.43
42 | OWN | Diversion of 400 KV Meramundali-Duburi line in between (A) Loc No. 27/0 & 28/0 (B) Loc No. 43/2 to 43A/0 at two places (C ) Loc. No. 16/0 to 18/0 for crossing of proposed Angul - Sukinda new railway line. Amount deposited by M/s RVNL Rs.22.472 lakhs | 22.47 |  |  |  |  | 22.47 |  |  | WIP | [6 empty] | 12.9363 | 1.38 | 0.2 | 7.9537 | 22.47
43 | OWN | Stringing of 2nd Circuit of 132 KV Bhadrak-Anandpur Transmission Line. | 8.15 |  |  |  |  | 8.15 |  |  | WIP | [6 empty] | 0.0044504 | 5.002 | 3.14 | 0.0035934 | 8.15
44 | OWN | Constn. Of 132 KV Kuchei(PG)-Bangiriposi S/C line with associated 1 No of bay extn. at both ends. | 21.52 |  |  |  |  | 21.52 |  |  | WIP | [6 empty] | 14.5381 | 6 | 0.98 | 0.0018534 | 21.52
45 | OWN | 400/220/132 KV Grid S/S at Meramundali-B | 174.85 |  |  |  |  | 174.85 |  |  | WIP | [6 empty] | 158.7852 | 11.06 | 5 |  | 174.8452
46 | OWN | 220kV LILO line from Joda-TTPS line to 220/33 KV GIS Keonjhar | 12.46 |  |  |  |  | 12.46 |  |  | WIP | [6 empty] | 6.35 | 6 | 0.11 | 3.1919e-16 | 12.46
47 | OWN | Construction of circuit-III & IV, 220 KV line from Tarkera to Bisra (Rourkela) PG. | 22.58 |  |  |  |  | 22.58 |  |  | WIP | [6 empty] | 0 | 6.774 | 15.806 | 0 | 22.58
48 | 30% Govt. | 220/33kV Grid ss,Golabandha, Telkoi | 51.09 | 16.7964 |  |  |  | 51.09 |  |  | WIP | 16.7964 | [5 empty] | 46.0923 | 5 | 0 | -0.0022808 | 51.09
49 | 30% Govt. | Construction of 132/33 KV Grid S/s GIS at Hinjilikatu, Ganjam | 45.22 | 13.495 |  |  |  | 45.22 |  |  | WIP | 13.495 | [5 empty] | 24.0083 | 7.8 | 0 | 13.4117 | 45.22
50 | 30% Govt. | Construction of 2x20 MVA, 132/33 KV Grid S/s at Hirakud with GIS along with associated 132 KV LILO lind from existing 132 KV Burla-Lapanga line & existing 132 KV ALCO line. Est. Cost-11/2017-18 | 48.4 | 14.5955 |  |  |  | 48.4 |  |  | WIP | 14.5955 | [5 empty] | 33.72 | 3.72 | 0 | 10.96 | 48.4
51 | (50% Deposit Work from Railway) | Construction of 220 KV LILO line from Loc. No. 125 & Loc. No. 126 of existing 220 KV Budhipadar to Tarkera line (CKT-II) and 132 KV LILO line from Loc. No. 291 of existing 132 KV Budhipadar to Tarkera line (CKT-II) and 220/132/33 KV Grid Sub-Station at Bamra. (50% Deposit Work) | 47.13 |  |  | 23.565 |  | 23.565 |  |  | WIP |  |  | 45.42 |  | 0 |  | 34.23 | 12.9 | 0 | -3.5527e-15 | 47.13
52 | 30% Govt. | 132/33 KV Grid S/S BIRMAHARAJPUR & Associated Line | 38.51 | 8.34 | 38.51 | [5 empty] | WIP | 8.34 | [5 empty] | 33.4125 | 4.5 | 0.6 | -0.0025231 | 38.51
53 | 40% Govt. | 220 KV DC Line from Bolangir to Kesinga | 100.41 | 33.8519 | 66.5581 | [5 empty] | WIP | 33.8519 | 66.5636 |  |  |  |  | 92.39 | 8.0176 | 0
54 | 30% Govt. | Construction of 2x20 MVA 220/33 KV Grid S/S at kalimela with associated 220 kv SC line on DC tower from Malkangiri s/s to the proposed Kalimela s/s with one number feeder bay extension at MALKANGIRI | 66.89 | 18.31 | [6 empty] | WIP | 18.31 | [5 empty] | 51.14 | 2 | 0 | 13.75 | 66.89
55 | 30% Govt. | Construction of 2x20 MVA 132/33 KV Grid S/S at Nawarangpur with associated 132 KV DC line for LILO arrangement of existing 132 KV Jayanagar - Tentulikhunti line | 31.64 | 11.8096 | [6 empty] | WIP | 11.8096 | [5 empty] | 26.64 | 5 | 0 | 0 | 31.64
56 | 40% Govt. | Design engineering, Errection, Testing & Commissioning of 220KV double circuit line from Jayanagar 220/132/33 Kv s/s of OPTCL to 400/220KV s/s of PGCIL at Kaliagaon | 17.41 | 5.8887 | [6 empty] | WIP | 5.8887 | 10.6988 |  |  |  |  | 16.8071 | 0.5 | 0 | 0.10293 | 17.41
57 | 40% Govt. | (A) Construction of 220/132/33KV grid substation at Jayapatna with one no. bay extension at proposed 132/33KV grid substation at Dabugaon and 220KV LILO line from 220KV Indravati-Theruvalli line. (B) Const. of 132KV SC line on DC tower from 132/33KV Dabugaon grid substation to proposed 220/132/33KV grid substation at Jayapatna. (In principle approved by the BoD) | 94.43 | 34.9694 | [6 empty] | WIP | 34.9694 | 59.4638 |  |  |  |  | 93.44 | 0.99 | 0 | 0 | 94.43
(ii) CWIP position of project started on or after 01.04.2022 to till date
Sl.No. | Scheme Name | Project Name | Contract/ Award Cost (Rs. In Cr.) | Source of Funding(Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date(Rs. In Cr.) | [5 empty] | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other |  | Total | Start | Complete | Equity | Debt | Grant | Other |  | Total | Till date of FY 2022-23 | Total in FY2022-23 | FY2023-24 |  | Total
1 | RRCP-II | 132kV LILO of one ckt of Budhipadar-Sundergarh line at Bamra | 31.3 | 9.39 | 21.91 |  |  |  |  | 11/2022 | 11/2025 | 4.94 | [5 empty] | 0 | 8.37 | 15.07 | 7.86 | 31.3
2 |  | 132kV SC on DC Tower from Kantabanji to Patnagarh | 24.25 | 7.275 | 16.975 |  |  |  |  | 11/2022 | 11/2024 | 4.94 | [5 empty] | 0 | 2.5 | 12 | 9.75 | 24.25
3 |  | 132kV SC Line on DC Tower from Ghense to Padampur | 22.94 | 6.882 | 16.058 |  |  |  |  | 12/2022 | 12/2024 | 3.96 | [5 empty] | 0 | 2.61 | 12 | 8.33 | 22.94
4 | LVMS | 132/33kV Athamallick S/s with associated line | 39.65 | 11.895 | 27.755 |  |  |  |  | 10/2022 | 10/2024 | 7.51 | [5 empty] | 0.11 | 2 | 15 | 22.54 | 39.65
5 |  | State Transmission Assets Management System (STAMPS) | [17 empty] | 50 |  | 50
8 |  | 220/132/33 KV S/S Nuapada | [15 empty] | 0.35575 | 0.5 | 0.5 |  | 1.3558
9 |  | 400/220kV S/S at Khuntuni (Dalabhag) | [15 empty] | 0.24991 | 0 | 1 |  | 1.2499
10 |  | 220/132kV GIS at Dhenkanal-B | [15 empty] | 0.30871 | 0 | 1 |  | 1.3087
11 |  | Const. Of 2x500 MVA ,400/220 KV Outdoor GIS Sub Station with SAS at Ramakrushnapur in Bhadrak District. | [15 empty] | 5.5969 | 0.3 | 1.5 |  | 7.3969
12 |  | Bay Extension at Padampur-Nuapada | [15 empty] | 0 | 2.5 | 0.5 |  | 3
(iii) Project in hands will be started from till dated to by the end of 31.03.2024
Sl.No. | Scheme Name | Project Name | Tentative Estimated Cost (Rs. In Cr.) | Source of Funding(Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date(Rs. In Cr.) | [5 empty] | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other |  | Total | Start | Complete | Equity | Debt | Grant | Other |  | Total | FY 2022-23 | FY 2023-24 | After FY 2023-24 |  | Total
1 | RRCP-II | 220kV Balimela_Jayanagar LILO at Govindpalli | 32.522 | 9.7566 | 22.7654 | [6 empty] | 1.31 | [5 empty] | 28.52 | 2 | 2 | 0.002 | 32.522
|  | 132kV LILO of Chhend-Adhunik Line at Kuanramunda | 2.03 | 0.609 | 1.421 | [6 empty] | 1.5 | [8 empty] | 2.03 | 2.03
2 | LVMS | 132/33kV Agalpur(Rampur) S/s with SAS with associated line | 36.75 | 11.025 | 25.725 | [6 empty] | 7.08 | [5 empty] | 0 | 3 | 20 | 13.75 | 36.75
|  | 220/33kV S/s at M. Rampur with associated line | 63.18 | 18.954 | 44.226 | [6 empty] | 12.18 | [5 empty] | 0.06 | 3.5 | 20 | 39.62 | 63.18
|  | 220/33kV S/s at Chitalo with associated line | 90 | 27 | 63 | [6 empty] | 17.35 | [8 empty] | 90 | 90
|  | 132kV line from Turumunga to Dhenkikote | 30.5 | 9.15 | 21.35 | [6 empty] | 5.88 | [8 empty] | 30.5 | 30.5

## F-2_(i)
Details of the transmission Projects which are under CWIP but without approval of the Commission (if any)
(i) CWIP position without approval of the Commission (if any)
Sl.No. | Scheme Name | Project Name | Contract/Award Cost(Rs. In Cr.) | Source of Funding(Rs. In Cr.) |  |  |  |  | Project Period |  | Actual fund received till date(Rs. In Cr.) |  |  |  |  | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other | Total | Start | Complete | Equity | Debt | Grant | Other | Total | upto 31.03.2022 | FY2022-23 | FY2023-24 | Total
1 | SCRIPS | 2X160MVA 220/132kV & 2X63MVA 132/33kV, 220/132/33kV GIS at Balianta (Benupur), BBSR and associated line using monopole | 139.2 | [5 empty] | 03/2019 | 06/2023 |  |  | 66.46 |  |  | 15.15 | 30 | 94.05 | 139.2
|  | 2X63MVA, 132/33kV GIS at Nayapalli, BBSR | 87.88 | [5 empty] | 03/2019 | 07/2023 |  |  | 42.47 |  |  | 32.01 | 30 | 25.87 | 87.88
|  | 2X63MVA, 132/33kV GIS at Satyanagar, BBSR | 170.65 | [5 empty] | 02/2019 | 02/2024 |  |  | 74.04 |  |  | 55.21 | 29.24 | 86.2 | 170.65
2X63MVA, 132/33kV GIS at Badagada, BBSR
|  | 2X63MVA, 220/33kV GIS at Kantabada, Gothapatna | 95.34 (Kantabada+Godishahi) | [5 empty] | 02/2019 | 03/2023 |  |  | 48.04 |  |  | 58.33 (Kantabada+Godishahi) | 30.00 (Kantabada+Godishahi) | 7.01
2 | DRPS | 132kV DC line from 132/33kV GIS Chandbali to 220/132/33kV Grid S/S at Balimunda, Dhamara. | 19.4 | [5 empty] | 01/2019 | 03/2023 |  |  | 19.4 |  |  | 16.23 | 2 | 1.17
3 | RRCP | 132kV D/C line from Parlakhemundi to R.Udayagiri. | 41.82 | [5 empty] | 03/2018 | 06/2023 |  |  | 41.82 |  |  | 25.03 | 8 | 8.79
|  | 132kV D/C line from Lapanga to Brajrajnagar with diversion of 220kV IB - Budhipdara DC line. | 12.44 | [5 empty] | 02/2017 | 03/2023 |  |  | 12.44 |  |  | 5.87 | 2.5 | 4.07
|  | 220kV LILO line from 220kV Theruvalli-Narendrapur DC line to 220/132/33kV Grid S/S at Aska | 39.08 | [5 empty] | 12/2018 | 03/2023 |  |  | 39.08 |  |  | 26.61 | 6 | 6.47
|  | 132kV Boudh-Phulbani DC line with bay extn. at both ends | 44.98 | [5 empty] | 03/2016 | 06/2023 | [5 empty] | 44.78
4 | DRC | Installation of 3rd ICT with 400kV & 220kV bay extension at New Duburi | 19.8 | [5 empty] | 05/2018 | 03/2023 (waiting ICT) |  |  | 19.8 |  |  | 14.91 | 3 | 1.89
5 | SSP (System Strengthing Project) | Diversion of 400kV & 220kV lines with 220kV LILO arrangement for connectivity with 400/220kV GIS at Meramundali-B. | 41.53 | [5 empty] | 03/2019 | 03/2023 |  |  |  | 13.08 |  | 27.29 | 7 | 7.24
6 | GoO Rs. 300 Cr. Equity Support | 132kV Jayanagar-Sunabeda line | 24.97 | [5 empty] | 07/2013 | 01/2023 |  | 13.1627 |  |  |  | 19.31 | 1 | 4.66
7 | GoO Equity Support | 2x500MVA, 400/220/33kV GIS at Paradeep and associated line | 686.82 | [5 empty] | Line:12/2021,GSS:12/2022 | 03/2024 | [5 empty] | 2.73 | 50 | (FY2023-24)365.00 Cr , (FY2024-25)269.00 Cr
8 | 100% Govt. Support | 2X20MVA, 132/33KVGSS at Brundabahal & associated line | 45.54 | [5 empty] | 02/2021 | 05/2023 | [5 empty] | 5.22 | 20 | 20.32
|  | 132/33 KV S/S at Tarabha, and associated 132KV LILO Lin | 26.53 | [5 empty] | 12/2021 | 06/2023 | [5 empty] | 1.32 | 15 | 10.21
9 | JICA | 2x20 MVA, 220/33kV S/S at Dasapalla and associated line | 59.26 | [5 empty] | 01/2018 | 03/2023 | [5 empty] | 37.58 | 10 | 11.68
|  | 2X20MVA, 132/33kV Grid S/S at Kudaloi, Lakhanpur and associated lines | 46.42 | [5 empty] | 05/2017 | 02/2023 | [5 empty] | 36.63 | 6.11 | 3.68
|  | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga and associated line. | 103.12 | [5 empty] | 02/2019 | 06/2023 | [5 empty] | 76.18 | 20 | 6.94
9 | RRCP-II | 132kV LILO of one ckt of Budhipadar-Sundergarh line at Bamra | 31.3 | [5 empty] | 11/2022 | 11/2025 | 4.94
|  | 132kV SC on DC Tower from Kantabanji to Patnagarh | 24.25 | [5 empty] | 11/2022 | 11/2024 | 4.94
|  | 132kV SC Line on DC Tower from Ghense to Padampur | 22.94 | [5 empty] | 12/2022 | 12/2024 | 3.96
10 | LVMS | 132/33kV Athamallick S/s with associated line | 39.65 | [5 empty] | 10/2022 | 10/2024 | 7.51

## CWIP (Non approval )
Project wise,Scheme wise,Source of funding wise of Capital Work in Progress(CWIP) position of Transmisssion projects
(i) CWIP position of project started on or before 31.03.2022
Sl. No. | Scheme Name | Project Name | Contract / Award Cost (Rs. In Cr.) | Source of Funding (Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date (Rs. In Cr.) | [5 empty] | Expenditure incurred / to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | Start | Complete | Equity | Debt | Deposit / Grant | Other (SACI) | Own | Total | upto 31.03.2022 | FY 2022-23 | FY 2023-24 | FY 2024-25 | Total
1 | SCRIPS | 2X160MVA 220/132kV & 2X63MVA 132/33kV, 220/132/33kV GIS at Balianta (Benupur), BBSR and associated line using monopole | 139.2 |  |  | 139.2 |  |  |  | 03/2019 | WIP |  |  | 66.46 |  |  |  | 16.38 | 47.626 | 18 | 57.194 | 139.2
2 |  | 2X63MVA, 132/33kV GIS at Nayapalli, BBSR | 87.88 |  |  | 87.88 |  |  |  | 03/2019 | WIP |  |  | 42.47 |  |  |  | 36.22 | 14.14 | 15 | 22.52 | 87.88
3 |  | 2X63MVA, 132/33kV GIS at Satyanagar, BBSR | 170.65 |  |  | 170.65 |  |  |  | 02/2019 | WIP |  |  | 74.04 |  |  |  | 57.47 | 21.96 | 55 | 36.22 | 170.65
4 |  | 2X63MVA, 132/33kV GIS at Badagada, BBSR | [8 empty] | WIP
5 |  | 2X63MVA, 220/33kV GIS at Kantabada, Gothapatna | 95.34 (Kantabada+ Godishahi) |  |  | 95.34 |  |  |  | 02/2019 | WIP |  |  | 48.04 |  |  |  | 60.63 | 35.02 | 15 |  | 110.34
7 |  | Construction of 2 X 40 MVA, 132/33 KV GIS, CHANDBALI with associated line. Deposit Work,Under DRPS Scheme | 39.75 |  |  | 39.75 |  |  |  |  | WIP |  |  | 39.75 |  |  |  | 12.4516 | 6.2397 | 2.12 | 18.9387 | 39.75
9 | RRCP | 132kV D/C line from Parlakhemundi to R.Udayagiri. | 41.82 |  |  | 41.82 |  |  |  | 03/2018 | WIP |  |  | 41.82 |  |  |  | 24.44 | 7.1 | 4.33 | 5.95 | 41.82
10 |  | 132kV D/C line from Lapanga to Brajrajnagar with diversion of 220kV IB - Budhipdara DC line. | 12.84 |  |  | 12.44 |  |  |  | 02/2017 | WIP |  |  | 12.44 |  |  |  | 5.93 | 6.91 | 0 |  | 12.84
11 |  | 220kV LILO line from 220kV Theruvalli-Narendrapur DC line to 220/132/33kV Grid S/S at Aska | 39.09 |  |  | 39.08 |  |  |  | 12/2018 | WIP |  |  | 39.08 |  |  |  | 27.79 | 5.85 | 5.45 |  | 39.09
12 |  | 132kV Boudh-Phulbani DC line with bay extn. at both ends | 56.08 |  |  | 56.08 |  |  |  | 03/2016 | WIP |  |  | 56.08 |  |  |  | 43.93 | 4.94 | 7.21 |  | 56.08
13 | DRC | Installation of 3rd ICT with 400kV & 220kV bay extension at New Duburi | 21.49 |  |  | 21.49 |  |  |  | 05/2018 | WIP |  |  | 21.49 |  |  |  | 18.49 | 3 | 0 |  | 21.49
14 | Own | Diversion of 400kV & 220kV lines with 220kV LILO arrangement for connectivity with 400/220kV GIS at Meramundali-B. | 41.53 | 0 | 29.071 |  |  | 12.459 |  | 03/2019 | WIP | 0 |  |  | 13.08 |  |  | 22.96 | 5.98 | 2 | 10.59 | 41.53
15 | GoO Rs. 300 Cr. Equity Support | 132kV Jayanagar-Sunabeda line | 26.38 | 7.7289 | 18.6511 |  |  |  |  | 07/2013 | WIP | 7.7289 | 13.1627 |  |  |  |  | 24.48 | 1 | 0.9 |  | 26.38
16 | Paradeep | 2x500MVA, 400/220/33kV GIS at Paradeep and associated line | 686.82 | 191.24 | 495.58 |  |  |  |  | Line:12/2021,GSS:12/2022 | WIP |  |  | 186.24 |  |  |  | 0.39 | 99.76 | 110 | 476.67 | 686.82
17 | 100% Govt. Support | 2X20MVA, 132/33KVGSS at Brundabahal with associated line | 45.54 | 58.12 | [5 empty] | 02/2021 | WIP |  |  | 58.12 |  |  |  | 5.32 | 17.04 | 14.7 | 8.48 | 45.54
18 | 100% Govt. Support | 132/33 KV S/S at Tarabha with associated 132kV LILO Line | 26.53 | 26.53 | [5 empty] | 12/2021 | WIP |  |  | 13.69 |  |  |  | 1.44 | 10 | 12 | 3.09 | 26.53
19 | JICA | 2x20 MVA, 220/33kV S/S at Dasapalla with associated line | 61.21 |  | 42.847 |  | 8.1429 | 10.2201 | 61.21 | 01/2018 | WIP |  | 28.42 |  | 8.1429 |  |  | 40.6 | 10 | 10.61 |  | 61.21
20 | JICA | 2X20MVA, 132/33kV Grid S/S at Kudaloi, Lakhanpur with associated lines | 46.88 |  | 32.816 |  | 8.1429 | 5.9211 | 46.88 | 05/2017 | WIP |  | 28.924 |  | 8.1429 |  |  | 41.32 | 5.42 | 0.14 | 2.3315e-15 | 46.88
21 | JICA | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga with associated line. | 110.51 |  | 77.357 |  | 8.1429 | 25.0101 | 110.51 | 02/2019 | WIP |  | 47.796 |  | 8.1429 |  |  | 68.28 | 20 | 22.23 | 0 | 110.51
(ii) CWIP position of project started on or after 01.04.2022 to till date
Sl.No. | Scheme Name | Project Name | Contract/ Award Cost (Rs. In Cr.) | Source of Funding(Rs. In Cr.) | [5 empty] | Project Period |  | Actual fund received till date(Rs. In Cr.) | [5 empty] | Expenditure incurred/to be incurred(Rs. In Cr.)
|  |  |  | Equity | Debt | Grant | Other |  | Total | Start | Complete | Equity | Debt | Grant | Other |  | Total | Till date of FY 2022-23 | Total in FY2022-23 | FY2023-24 |  | Total
1 | RRCP-II | 132kV LILO of one ckt of Budhipadar-Sundergarh line at Bamra | 31.3 | 9.39 | 21.91 |  |  |  |  | 11/2022 | 11/2025 | 4.94 | [5 empty] | 0 | 8.37 | 15.07 | 7.86 | 31.3
2 | RRCP-II | 132kV SC on DC Tower from Kantabanji to Patnagarh | 24.25 | 7.275 | 16.975 |  |  |  |  | 11/2022 | 11/2024 | 4.94 | [5 empty] | 0 | 2.5 | 12 | 9.75 | 24.25
3 | RRCP-II | 132kV SC Line on DC Tower from Ghense to Padampur | 22.94 | 6.882 | 16.058 |  |  |  |  | 12/2022 | 12/2024 | 3.96 | [5 empty] | 0 | 2.61 | 12 | 8.33 | 22.94
4 | LVMS | 132/33kV Athamallick S/s with associated line | 39.65 | 11.895 | 27.755 |  |  |  |  | 10/2022 | 10/2024 | 7.51 | [5 empty] | 0.11 | 2 | 15 | 22.54 | 39.65
5 |  | State Transmission Assets Management System (STAMPS) | [17 empty] | 50 |  | 50