| Sl no | Name of The project | Justification. | Estimated/ Rough Cost | Expenditure proposed in FY 24-25 | Expenditure in other FY | Expenditure till date 31/12/ 2023. | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Construction of Multi-Storied Office Complex at SLDC, Bhubaneswar. | The hon’ble Commission has given the approval for construction of this building | Rs. 29.80 crores | Rs. 22.73 crores | FY:18-19 Rs. 0.31 crores Architect fees FY:23-24 Rs. 3.35 Cr. | Rs.3.66 Crores | 3rd Floor Casting complete. |
| 2 | Construction of BCDD-II at Nayapalli. | In order to create space for GIS, Nayapalli, an existing office complex of erstwhile CESU was demolished. As such, a new Office Complex has to be constructed for them. | Rs. 10 crores | Rs. 9.85 crores | FY:19-20 Rs. 0.13 crores | Architect fees Rs.13lakhs | Decision pending. |
| 3 | Improvement to FW building at OPTCL, BBSR. | Contract awarded. Special repair was needed for the old structure. | Rs.0.13 Crores | Rs.0.08 Crores | Nil | Nil | Work is in progress and nearing completion. |
| 4 | Construction of MS building at OPTCL, Malkangiri. | The proposal was for construction of an office complex for accommodating multiple offices within a single complex. | Rs.2.20 Crores | Rs.2.18 Crores | Nil | Nil | Proposal yet to be finalised. |
| 5 | Providing Furniture and fixture for MS building , OPTCL , Berhampur. | Furniture was not in the original contract. | Rs.0.50 Crores | Rs.0.49 Crores | Nil | Nil | Finalisation of furniture models. |
| 6 | Providing HVAC system for MS building , OPTCL , Berhampur. | HVAC system was not in the original contract. | Rs.1.00 Crores | Rs.0.99 Crores | Nil | Nil | Technical evaluation in progress. |
| 7 | Construction of an additional room for GM, EHT ( O & M ) circle , OPTCL,Berhampur | As presently there is no specific room available for GM. | Rs.0.20 Crores | Rs.0.19 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 8 | Improvement of EMR Sub Division at Choudwar | Special repair is needed for the old structure. | Rs.0.12 Crores | Rs.0.04 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 9 | Renovation of EHT Construction sub division at Bidanasi, Cuttack | Special repair is needed for the old structure. | Rs.0.15 Crores | Rs.0.05 Crores | Nil | Nil | Work Tendered. |
| 10 | Improvement to SLDC Building at Mancheswar. (providing paver block and outside repairing and painting) | Special repair was needed for few of the offices proposed to continue in the old SLDC building. | Rs.0.25 Crores | Rs.0.05 Crores | Nil | Nil | Work Tendered. |
| 11 | Improvement to multistoried office complex, finance wing and technical wing at OPTCL, BBSR | Special repair is needed for the old structure. | Rs.0.45 Crores | Rs.0.45 Crores | Nil | Nil | Work to be tendered shortly. |
| 12 | Providing an additional room for EMR SD , Jeypore to be functioned as laboratarory testing room | There is no laboratory available in the locality. | Rs.0.10 Crores | Rs.0.10 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 13 | Construction of office building of OPTCL in 220 KV GSS Premises at tarkara-Rourkela(Provision for office buildings for EHT(O&M) Division,E & MR and Tele communication sub Division) | The proposal was for construction of an office complex for accommodating multiple offices within a single complex. | Rs.2.50 Crores | Rs.2.50 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 14 | Construction of office building of OPTCL in Bolangir (Provision for office buildings like EHT(O&M) Circle, EHT(Const.) E & MR and Tele communication Divisions) | The proposal was for construction of an office complex for accommodating multiple offices within a single complex.. | Rs.4.50 Crores | Rs.4.50 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 15 | Construction of office buildings for Executive Director(ED) of western zone of OPTCL at Burla | For accommodation of the ED and associated office. | Rs.2.50 Crores | Rs.2.50 Crores | Nil | Nil | Proposal Yet to be finalised. |
| 16 | Construction of office buildings for like EHT (O&M) Circle and Telecom Division of OPTCL at Burla | The proposal was for construction of an office complex for accommodating multiple offices within a single complex. | Rs.2.00 Crores | Rs.2.00 Crores | Nil | Nil | Proposal Yet to be finalised. |
| TOTAL |  |  |  | Rs. 48.70 Crs |  |  |  |