## 2022-23
PROJECTS COMPLETED DURING FY 2022-2023 (April' 22 to Mar'23)
Sl. No. | Name of the Project | Scheduled date of completion | Approval of Commission (Transmission Plan, Business Plan & Investment Proposal) | Revised date of completion | Actual Date of completion | Original Estimated cost of the project (Rs. Cr.) / work order no. & date | Award Cost (Rs. Cr.) | Actual expenditure (Rs. Cr.)
1 | 2x20MVA, 132/33kV Grid S/S at BIRMAHARAJPUR (Sonepur) with associated line | 12/2020 | 45/2021 (IP) 05/2016 (BP) | 04/2022 | 13.05.2022 | 32.52 | 32.52 | 32.48
2 | 2X63MVA, 220/33kV GIS at Godisahi (SCRIPS) | 08/2020 | 58/2022 (IP) 18/2017 (TP) 63/2020 (BP) | 08/2022 | 21.06.2022 | 95.34 (for both Godishahi & Kantabada) | 47.57 | 44.84
3 | 2X40MVA,132/33kV GIS at Hinjili. | 02/2020 | 57/2021 (IP) 49/2021 (TP) 63/2020 (BP) | 01/2022 | 29.07.2022 | 35.72 | 35.72 | 27.49
4 | 2X40MVA, 132/33kV Grid S/S at , Bahugram (Atuda) with associated 132kV line.(JICA) | 03/2021 | 60/2016 (IP) 18/2017 (TP) 63/2020 (BP) | 06/2022 | 03.08.2022 | 36.61 | 33.59 | 26.94
5 | 2X20MVA, 132/33kV Grid S/S at Chandipur with associated 132kV line. (JICA) | 02/2021 | 52/2022 (IP) 05/2016 (BP) | 02/2022 | 30.08.2022 | 46.84 | 41.8 | 31.75
6 | 2x160MVA + 2x20MV, 220/132/33kV Grid S/S with SAS at Bamra and associated line. | 05/2020 | 52/2022 (IP) 18/2017 (TP) 63/2020 (BP) | 08/2022 | 04.09.2022 | 81.87 | 77.76 | 74.33
7 | 220kV Pandiabil -Pratapasasan DC line. | 09/2017 | 58/2022 (IP) 05/2016 (BP) | 04/2019 | 19.05.2022 | 29.15 | 27.95 | 27.13 | 21.18
8 | 2x20MVA, 220/33kV Grid S/S at Kalimela ( Malkangiri ) with associated line. | 02/2018 | 60/2016 (IP) 18/2017 (TP) 63/2020 (BP) | 04/2022 | 13.11.2022 | 56.66 | 52.89 | 52.33
9 | 2x160 MVA + 2 x 40 MVA, 220/132/33kV S/S at Kuanrmunda (Mandiakudar) with associated LILO. | 05/2020 | 22/2010 (IP) 05/2016 (BP) | 03/2023 | 25.01.2023 | 90.52 | 90.52 | 81.52
10 | 132KV ABRELSwitching station | 02/2020 | Made by Benificiary |  | 29.07.2022 |  | 35.72
11 | JSW (Siva) Switching station | 03/2021 | Made by Benificiary |  | 03.08.2022 |  | 33.59
12 | Ultratech Switching station | 02/2021 | Made by Benificiary |  | 30.08.2022 |  | 41.8

## 2023-24
PROJECTS COMPLETED DURING (April' 23 to Dec' 23)
Sl. No. | Name of the Project | Scheduled date of completion | Approval of Commission (Transmission Plan, Business Plan & Investment Proposal) | Revised date of completion | Actual Date of completion | Original Estimated cost of the project (Rs. Cr.) / work order no. & date | Award Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 09/2023 (Rs. Cr.)
1 | 2X63MVA, 220/33kV GIS at Kantabada, Gothapatna | 08/2020 | 69/2023 (IP) 18/2017(TP) | 01/2023 | 16.04.2023 | 47.67 | 47.67 | 41.84
2 | 2x160MVA+2x40MVA, 220/132/33kV Grid S/S, Dhamara with associated 220kV LILO line | 06/2020 | 78/2011 (IP) 05/2016 (BP) | 03/2023 | 24.04.2023 | 89.77 | 72.32 (Excluding Transformer) | 82.88
3 | 2x20MVA, 132/33kV Grid S/S at Boriguma in Koraput Distict and associated 132kV LILO line from 132kV S/C Jayanagar- Tentulikhunti. | 05/2019 | 02/2013 (IP) 05/2016 (BP) | 06/2022 | 24.04.2023 | 32.11 | 33.54 | 32.74
4 | 2X20MVA, 132/33kV Grid S/S at Kudaloi, Lakhanpur alongwith Construction of 132kV D/C line from Brajrajnagar to Lakhanpur.(JICA) | 05/2019 | 52/2022 (IP) 05/2016 (BP) | 02/2023 | 29.04.2023 | 36.97 | 45.46 | 53.31
5 | 2X40MVA, 132/33kV Grid S/S at Bhatli along with its 132kV DC line from 220/132/33kV S/S Bargarh(New) | 11/2020 | 57/2021 (IP) 05/2016 (BP) | 01/2023 | 23.06.2023 | 51.93 | 45.3 (Excluding Transformer) | 48.63
6 | 132KV Lapanga-Brajarajnagar Line | 05/2018 | 52/2022 (IP) 05/2016 (BP) | 06/2023 | 22.06.2023 (Charged: 132kV LILO from 132kV Budhipadar-Jurabag (Ckt-II) to 132/33kV Brajarajnagar GSS | 12.15 | 12.44 | 8.12