## Annexure-13(A)
Annexure-13 (A)
Details of Equity Share infused by the OPTCL during the FY 2022-23
Sl No | Name of the Projects | Equity (Amount) | Amount Received upto 30.03.2022 | Amount Receivd | Date | Total Equity Received | Sanction Order /Date | Present Status
Equity Share Capital as on 01.04.2022 againt the project/ scheme other than below list |  | 1746.7693 | 1746.7693 |  |  | 1746.7693
Low Voltage Mitigation System (LVMS) Rs.77.83Cr.
1 | 2X20 MVA, 132/33 kV s/s with SAS at Agalpur, Rampur & associated line | 11.025 | 0 | 7.0827 | 2022-11-24 | 7.0827 | 202227471194/18-11-2022 | CWIP-Expected date of Charging 06/2025
2 | 2X20 MVA, 132/33 kV grid s/s at Athamallik with associated line | 11.7 | 0 | 7.5164 |  | 7.5164 |  | CWIP-Expected date of Charging 10/2024
3 | 2X20MVA, 220/33 kV Grid Sub-Station at Madanpur Rampur along with lines | 18.954 | 0 | 12.1765 |  | 12.1765 |  | Under Tendering
4 | 220/33kV S/s at Chitalo (Ranua) & line | 27 | 0 | 17.3455 |  | 17.3455 |  | To be tendered
5 | 132kV line from Turumunga to Dhenkikote | 9.15 | 0 | 5.8782 |  | 5.8782 |  | CWIP-Expected date of Charging 02/2025
| TOTAL LVMS | 77.829 |  | 49.9994 |  | 49.9994
Radial to Ring Conversion Projects (RRCP) Rs.28.745 Cr.
6 | 220 kV Balimela – Jayjanagar LILO at Govindpalli(SC) | 2.2656 | 0.52404 | 0.78803 | 2022-11-23 | 1.3121 | 202227471290/18-11-2022 | CWIP-Expected date of Charging 02/2024
7 | 132kV SC on DC Tower from Kantabanji to Patnagarh | 8.5314 | 1.9733 | 2.9674 |  | 4.9408 |  | CWIP-Expected date of Charging 11/2024
8 | 132kV LILO of one CKT of Budhipadar-Sundargarh line at bamra | 8.5314 | 1.9733 | 2.9674 |  | 4.9408 |  | CWIP-Expected date of Charging 11/2025
9 | 132kV SC Line on DC Tower from Ghense to Padampur | 6.8322 | 1.5803 | 2.3764 |  | 3.9567 |  | CWIP-Expected date of Charging 12/2024
10 | 132 kV LILO of Chhend-Nuagaon line at Kuanarmunda | 2.5923 | 0.59961 | 0.90167 |  | 1.5013 |  | CWIP-Expected date of Charging 04/2024
| TOTAL RRCP-II | 28.7529 | 6.6507 | 10.001 |  | 16.6517
11 | 132/33 Kv Grid S/s at Tarabha | 31.69 | 4 | 9.69 | 2022-11-23 | 13.69 | 202227471951/18-11-2022 | CWIP-Expected date of Charging 06/2024
12 | 132/33 Kv Grid S/s at Brundabahal | 58.12 | 35.29 | 22.83 | 2022-11-23 | 58.12 | 202227471252/18-11-2022 | CWIP-Expected date of Charging 03/2024
13 | 400/220/132 KV GSS at Paradeep | 191.235 | 94 | 92.24 | 2022-11-24 | 186.24 | 202227471090/ 18-11-2022 | CWIP-Expected date of Charging 12/2024
| Grand Total | 2134.3962 | 1886.71 | 184.7604 |  | 2071.4704

## Annexure-13(B)
Annexure-13 (B)
Details of Equity Share infused by the OPTCL during the FY 2023-24 (Upto 31.12.2023)
Sl No | Name of the Projects | Equity (Amount) | Amount Received upto 30.03.2023 | Amount Receivd | Date | Total Equity Received | Sanction Order /Date | Present Status
Equity Share Capital as on 01.04.2022 againt the project/ scheme other than below list |  | 1804.8893 | 1804.8893 |  |  | 1804.8893
Low Voltage Mitigation System (LVMS) Rs.77.83Cr.
1 | 2X20 MVA, 132/33 kV s/s with SAS at Agalpur, Rampur & associated line | 11.025 | 7.0827 | 1.9718 | 2023-10-05 | 9.0546 | 202331297833/26.09.2023 | CWIP-Expected date of Charging 06/2025
2 | 2X20 MVA, 132/33 kV grid s/s at Athamallik with associated line | 11.7 | 7.5164 | 2.0926 |  | 9.6089 |  | CWIP-Expected date of Charging 10/2024
3 | 2X20MVA, 220/33 kV Grid Sub-Station at Madanpur Rampur along with lines | 18.954 | 12.1765 | 3.3899 |  | 15.5665 |  | Under Tendering
4 | 220/33kV S/s at Chitalo (Ranua) & line | 27 | 17.3455 | 4.829 |  | 22.1745 |  | To be tendered
5 | 132kV line from Turumunga to Dhenkikote | 9.15 | 5.8782 | 1.6365 |  | 7.5147 |  | CWIP-Expected date of Charging 02/2025
| TOTAL LVMS | 77.829 | 49.9994 | 13.9198 |  | 63.9192
Radial to Ring Conversion Projects (RRCP) Rs.28.745 Cr.
6 | 220 kV Balimela – Jayjanagar LILO at Govindpalli(SC) | 2.2656 | 1.3121 | 0.95352 | 2023-09-18 | 2.2656 | 202331276284/14.09.2023 | CWIP-Expected date of Charging 02/2024
7 | 132kV SC on DC Tower from Kantabanji to Patnagarh | 8.5314 | 4.9408 | 3.5906 |  | 8.5314 |  | CWIP-Expected date of Charging 11/2024
8 | 132kV LILO of one CKT of Budhipadar-Sundargarh line at bamra | 8.5314 | 4.9408 | 3.5906 |  | 8.5314 |  | CWIP-Expected date of Charging 11/2025
9 | 132kV SC Line on DC Tower from Ghense to Padampur | 6.8322 | 3.9567 | 2.8755 |  | 6.8322 |  | CWIP-Expected date of Charging 12/2024
10 | 132 kV LILO of Chhend-Nuagaon line at Kuanarmunda | 2.5923 | 1.5013 | 1.091 |  | 2.5923 |  | CWIP-Expected date of Charging 04/2024
| TOTAL RRCP-II | 28.7529 | 16.6517 | 12.1012 |  | 28.7529
11 | 132/33 Kv Grid S/s at Tarabha | 31.69 | 13.69 | 18 | 2023-09-18 | 31.69 | 202331276395/14.09.2023 | CWIP-Expected date of Charging 06/2024
12 | 400/220/132 KV GSS at Paradeep | 191.235 | 186.24 | 4.995 | 2023-09-18 | 191.235 | 202331276355/14.09.2023 | CWIP-Expected date of Charging 12/2024
Special Assistance to state for Capital Investments Rs.145.6950 Cr. (alloted in FY 2023-24)
14 | 400/220/33 KV Meramundali-B GIS | 26.575 |  | 26.575 | 2022-11-22 | 26.575 | 202227470743/17-11-2022 | 2022-01-08
15 | 2X20MVA, 132/33kV Grid Sub- Station at Chandipur along with its associated transmission line | 13.46 |  | 13.46 | 2022-11-23 | 13.46 | 202227470600/17.11.2022 | 2022-08-31
16 | 132/33 KV GRID S/S, Bahugram | 10.26 |  | 10.26 |  | 10.26 |  | 2022-08-03
17 | 132/33 KV GRID S/S, Gondia | 11.72 |  | 11.72 |  | 11.72 |  | 2021-10-31
18 | 2x20MVA, 132/33kV Grid Sub-station at Rajnagar along with associated line | 10.76 |  | 10.76 |  | 10.76 |  | 2021-08-28
19 | 2X20MVA, 132/33kV Grid Sub- station at Lakhanpur along with associated its transmission line. | 8.49 |  | 8.49 |  | 8.49 |  | 2023-04-29
20 | 2X20MVA, 132/33kV Grid Sub-Station at Thuapali along with associated line | 9.67 |  | 9.67 |  | 9.67 |  | 2021-07-14
21 | 2x160MVA (Auto) and 2x20MVA, 220/132/33 Kv Grid Sub-Station at Gunupur along with associated line | 17.24 |  | 17.24 |  | 17.24 |  | 2022-03-30
22 | 220/132/33 KV GRID S/S, Kiakata | 37.52 |  | 37.52 |  | 37.52 |  | CWIP-Expected date of Charging 07/2024
| Sub Total | 145.695 | 0 | 145.695 |  | 145.695
| Grand Total | 2280.0912 | 2071.4704 | 194.711 |  | 2266.1814