## ODSSP
List of 33/11kV Sub-stations completed & commissioned by OPTCL under ODSSP Scheme (Phase I, II & III) as on 20.01.2023
Sl. No | District | Constituency | Name of Substation | Phase No/ Pkg No | S/s Charged on
1 | KHURDA | BBSR Central | Vani Vihar Campus | PH-IA (R )/ PKG-4 | 16.05.2018
2 | KHURDA | BBSR Central | IMMT (RRL Campus) | PH-IA (R )/ PKG-4 | 07.04.2016
3 | KHURDA | BBSR Central | Unit-II | PH-I(B) | 22.07.2016
4 | KHURDA | BBSR North | Chakeisiani | PH-II (R )/ PKG-5 | 01.09.2017
5 | KHURDA | BBSR North | Sailashree Vihar | PH-III/ PKG-5 | 11.06.2021
6 | KHURDA | BBSR North | Niladri Vihar | PH-III/ PKG-5 | 15.04.2022
7 | KHURDA | Ekamra | Lingipur | PH-IA (R )/ PKG-4 | 25.04.2018
8 | KHURDA | Ekamra | Kalpana | PH-II (A ) | 19.05.2018
9 | KHURDA | Ekamra | Dumuduma | PH-II (R )/ PKG-5 | 22.09.2017
10 | KHURDA | Ekamra | Mulapadia | PH-II (A ) | 04.04.2019
11 | KHURDA | Jaydev | Bhingarpur | PH-IA (R )/ PKG-1 | 31.08.2016
12 | KHURDA | Jaydev | Banamalipur | PH-IA (R )/ PKG-1 | 05.04.2018
13 | KHURDA | Jaydev | Abhayamukhi | PH-II (R )/ PKG-1 | 29.07.2021
14 | KHURDA | Jaydev | Trahi Achyuta Nagar | PH-II (R )/ PKG-1 | 01.10.2018
15 | KHURDA | Jatani | Chatabar | PH-IA (R )/ PKG-1 | 21.06.2016
16 | KHURDA | Jatani | Mendhasal | PH-IA (R )/ PKG-1 | 30.10.2017
17 | KHURDA | Jatani | Chandaka | PH-IA (R )/ PKG-4 | 14.08.2019
18 | KHURDA | Jatani | Ranasinghpur (Sijua) | PH-IA (R )/ PKG-4 | 19.12.2016
19 | KHURDA | Jatani | Pradhan Sahi | PH-II (R )/ PKG-5 | 18.09.2021
20 | KHURDA | Jatani | Gothapatna | PH-IA (R )/ PKG-4 | 22.12.2016
21 | KHURDA | Jatani | Jatani Nuagaoun | PH-III/ PKG-1 | 13.04.2021
22 | KHURDA | Khurda | Chhanagiri | PH-III/ PKG-1 | 21.01.2019
23 | KHURDA | Begunia | Gediapali | PH-IA (R )/ PKG-1 | 28.06.2016
24 | KHURDA | Begunia | Sarua | PH-II (R )/ PKG-1 | 04.09.2016
25 | KHURDA | Chilika | Gangadharapur | PH-IA (R )/ PKG-1 | 15.03.2018
26 | CUTTACK | Barabati Cuttack | Satichaura | PH-IA (R )/ PKG-4 | 22.05.2017
27 | CUTTACK | Barabati Cuttack | OSEB Colony, Palamandap | PH-IA (R )/ PKG-4 | 17.08.2019
28 | CUTTACK | Barabati Cuttack | Mahanadi Vihar | PH-IA (R )/ PKG-4 | 16.12.2017
29 | CUTTACK | Barabati Cuttack | CDA-10 & 11 | PH-I(B) | 29.03.2016
30 | CUTTACK | Barabati Cuttack | CDA-13 | PH-I(B) | 08.08.2016
31 | CUTTACK | Choudwar | Ipicol,Jagatpur | PH-IA (R )/ PKG-4 | 31.07.2017
32 | CUTTACK | Niali | Govindpur | PH-IA (R )/ PKG-1 | 29.05.2018
33 | CUTTACK | Niali | Kula Kapasi | PH-II (R )/ PKG-1 | 28.10.2020
34 | CUTTACK | Salipur | Raisunguda | PH-IA (R )/ PKG-1 | 18.10.2017
35 | CUTTACK | Salipur | Japakuda | PH-II (R )/ PKG-1 | 18.11.2020
36 | CUTTACK | Mahanga | Erakana | PH-IA (R )/ PKG-1 | 26.03.2018
37 | CUTTACK | Mahanga | Asureswar | PH-II (R )/ PKG-1 | 18.11.2020
38 | CUTTACK | Athagarh | Sankarpur | PH-IA (R )/ PKG-1 | 31.10.2016
39 | CUTTACK | Badamba | Mardamukha | PH-IA (R )/ PKG-1 | 06.07.2018
40 | CUTTACK | Badamba | Gopapur | PH-II (R )/ PKG-1 | 02.08.2017
41 | CUTTACK | Badamba | Bandalo (Baunsaput) | PH-II (R )/ PKG-1 | 11.09.2020
42 | CUTTACK | Badamba | Dhobaninala | PH-III/ PKG-1 | 24.01.2019
43 | CUTTACK | Cuttack Sadar | Somapur | PH-II (R )/ PKG-1 | 15.05.2017
44 | CUTTACK | Banki | Godisahi (Ramdaspur) | PH-IA (R )/ PKG-1 | 10.06.2016
45 | CUTTACK | Banki | Saranda | PH-II (R )/ PKG-1 | 26.06.2021
46 | PURI | Kakatpur | Patalda | PH-IA (R )/ PKG-1 | 02.05.2018
47 | PURI | Kakatpur | Bangurigaon | PH-II (R )/ PKG-1 | 04.08.2018
48 | PURI | Kakatpur | Sutan | PH-II (R )/ PKG-1 | 06.07.2021
49 | PURI | Nimapara | Jogeswarpur (Gada amaraprasad) | PH-III/ PKG-1 | 17.06.2018
50 | PURI | Nimapara | Bamanal | PH-IA (R )/ PKG-1 | 26.02.2019
51 | PURI | Nimapara | Khelar | PH-III/ PKG-1 | 09.11.2021
52 | PURI | Nimapara | Nagapur | PH-III/ PKG-1 | 20.05.2018
53 | PURI | Pipili | Bhartipur | PH-IA (R )/ PKG-1 | 23.04.2021
54 | PURI | Pipili | Kalyanpur | PH-II (R )/ PKG-1 | 11.08.2021
55 | PURI | Pipili | Siula | PH-III/ PKG-5 | 06.10.2021
56 | PURI | Pipili | Mangalpur | PH-III/ PKG-5 | 10.03.2022
57 | PURI | Puri Sadar | Chalisbatia | PH-IA (R )/ PKG-1 | 14.02.2022
58 | PURI | Puri Sadar | Samanga | PH-IA (R )/ PKG-4 | 25.09.2020
59 | PURI | Puri Sadar | Charinala | PH-I(B) | 19.02.2020
60 | PURI | Satyabadi | Balipada | PH-III/ PKG-1 | 18.12.2022
61 | PURI | Satyabadi | Gabakunda | PH-IA (R )/ PKG-1 | 31.07.2017
62 | PURI | Satyabadi | Jamalgada | PH-III/ PKG-1 | 30.12.2022
63 | PURI | Bramhagiri | Panaspada | PH-IA (R )/ PKG-1 | 06.02.2018
64 | NAYAGARH | Ranapur | Khandisi | PH-IA (R )/ PKG-1 | 08.09.2016
65 | NAYAGARH | Ranapur | Godipada | PH-IA (R )/ PKG-1 | 11.01.2018
66 | NAYAGARH | Nayagarh | Machhipada | PH-IA (R )/ PKG-1 | 24.03.2018
67 | NAYAGARH | Nayagarh | Balugaon | PH-IA (R )/ PKG-1 | 06.09.2016
68 | NAYAGARH | Nayagarh | Kurala | PH-IA (R )/ PKG-1 | 29.09.2016
69 | NAYAGARH | Nayagarh | Lathipada | PH-II (R )/ PKG-1 | 25.01.2018
70 | NAYAGARH | Khandapada | Dhalabadha | PH-IA (R )/ PKG-1 | 03.07.2016
71 | NAYAGARH | Khandapada | Bijipur | PH-II (R )/ PKG-1 | 27.05.2017
72 | NAYAGARH | Khandapada | Barakoli | PH-II (R )/ PKG-1 | 18.05.2021
73 | NAYAGARH | Dasapalla | Chamundia | PH-IA (R )/ PKG-1 | 20.08.2017
74 | NAYAGARH | Nayagarh | Haripur | PH-III/ PKG-1 | 25.01.2019
75 | NAYAGARH | Dasapalla | Kirialanji | PH-III/ PKG-1 | 18.02.2021
76 | KENDRAPADA | Kendrapara | Chaudakulata | PH-IA (R )/ PKG-1 | 05.07.2017
77 | KENDRAPADA | Kendrapara | Chokada | PH-II (R )/ PKG-1 | 27.02.2019
78 | KENDRAPADA | Kendrapara | Khamar Keshpur | PH-III/ PKG-1 | 10.11.2021
79 | KENDRAPADA | Rajnagar | Badadia | PH-IA (R )/ PKG-1 | 28.08.2020
80 | KENDRAPADA | Aul | Madhubana | PH-IA (R )/ PKG-1 | 24.01.2020
81 | KENDRAPADA | Aul | Ayatan | PH-II (R )/ PKG-1 | 05.05.2021
82 | KENDRAPADA | Patakura | Gaudagaon | PH-IA (R )/ PKG-1 | 24.06.2022
83 | KENDRAPADA | Patakura | Jahara Barimula | PH-II (R )/ PKG-1 | 27.06.2017
84 | KENDRAPADA | Patakura | Bedari | PH-III/ PKG-1 | 30.09.2020
85 | KENDRAPADA | Mahakalapada | Thauri | PH-IA (R )/ PKG-1 | 26.07.2019
86 | JAGATSINGHPUR | Paradeep | Bijayachandrapur | PH-IA (R )/ PKG-1 | 02.06.2017
87 | JAGATSINGHPUR | Paradeep | Jhimani | PH-II (R )/ PKG-1 | 11.05.2021
88 | JAGATSINGHPUR | Paradeep | Gorada | PH-III/ PKG-1 | 10.06.2020
89 | JAGATSINGHPUR | Balikuda-Erasama | Jagannathpur | PH-IA (R )/ PKG-1 | 25.11.2017
90 | JAGATSINGHPUR | Balikuda-Erasama | Duvalo (Borikina) | PH-II (R )/ PKG-1 | 31.01.2018
91 | JAGATSINGHPUR | Balikuda-Erasama | Dusbatia | PH-III/ PKG-1 | 22.06.2021
92 | JAGATSINGHPUR | Balikuda-Erasama | Gada Bishnupur | PH-III/ PKG-1 | 12.12.2022
93 | JAGATSINGHPUR | Jagatsinghpur | Derik-Gangada | PH-IA (R )/ PKG-1 | 28.04.2021
94 | JAGATSINGHPUR | Jagatsinghpur | Bhatapada | PH-II (R )/ PKG-1 | 24.04.2017
95 | JAGATSINGHPUR | Jagatsinghpur | Markandapur | PH-III/ PKG-1 | 07.07.2021
96 | JAGATSINGHPUR | Tirtol | Kanakpur | PH-IA (R )/ PKG-1 | 04.12.2017
97 | JAGATSINGHPUR | Tirtol | Balia (Adhanga) | PH-II (R )/ PKG-1 | 26.04.2017
98 | JAGATSINGHPUR | Tirtol | Krishnandapur | PH-II (R )/ PKG-1 | 30.09.2019
99 | JAGATSINGHPUR | Tirtol | Chikinia (Erandapal) | PH-III/ PKG-1 | 19.06.2021
100 | DHENKANAL | Parjanga | Sanda | PH-I/ PKG-1 | 17.03.2017
101 | DHENKANAL | Parjanga | Saranga | PH-II (R )/ PKG-1 | 07.10.2016
102 | DHENKANAL | Parjanga | Mahabir road | PH-III/ PKG-1 | 13.12.2021
103 | DHENKANAL | Parjanga | Birasal | PH-III/ PKG-1 | 09.09.2021
104 | DHENKANAL | Parjanga | Banarapala | PH-III/ PKG-1 | 08.02.2021
105 | DHENKANAL | Hindol | Meramundali | PH-I/ PKG-1 | 05.05.2021
106 | DHENKANAL | Hindol | Ghatipiri | PH-III/ PKG-1 | 03.11.2022
107 | DHENKANAL | Hindol | Pada | PH-III/ PKG-1 | 19.02.2022
108 | DHENKANAL | Hindol | Nuabag | PH-III/ PKG-1 | 16.03.2019
109 | DHENKANAL | Kamakhayanagar | Pandua | PH-I/ PKG-1 | 11.03.2019
110 | DHENKANAL | Kamakhayanagar | Mahulpal (Bhuban) | PH-II (R )/ PKG-1 | 09.03.2021
111 | DHENKANAL | Kamakhayanagar | Jiral | PH-II (R )/ PKG-1 | 12.08.2017
112 | DHENKANAL | Kamakhayanagar | Jiridamali | PH-II (R )/ PKG-1 | 27.02.2017
113 | DHENKANAL | Dhenkanal Sadar | Banasingh | PH-I/ PKG-1 | 31.12.2018
114 | DHENKANAL | Dhenkanal Sadar | Muktapasi | PH-II (R )/ PKG-1 | 30.09.2020
115 | DHENKANAL | Dhenkanal Sadar | Sadangi | PH-III/ PKG-1 | 08.05.2020
116 | ANUGUL | Talcher | Danara | PH-I/ PKG-1 | 03.01.2017
117 | ANUGUL | Talcher | Talcher Town | PH-II (R )/ PKG-5 | 07.02.2019
118 | ANUGUL | Pallahara | Kunjam | PH-I/ PKG-1 | 16.12.2017
119 | ANUGUL | Pallahara | Hanumanpur | PH-II (R )/ PKG-1 | 28.04.2017
120 | ANUGUL | Pallahara | Kantala | PH-III/ PKG-1 | 17.02.2022
121 | ANUGUL | Angul | Badakera | PH-I/ PKG-1 | 07.12.2016
122 | ANUGUL | Angul | Phulpada | PH-III/ PKG-1 | 10.02.2021
123 | ANUGUL | Angul | Kulad | PH-II (R )/ PKG-1 | 31.10.2017
124 | ANUGUL | Athamallik | Daurapalli | PH-I/ PKG-1 | 13.10.2017
125 | ANUGUL | Athamallik | Nakchi | PH-II (R )/ PKG-1 | 12.07.2017
126 | ANUGUL | Chendipada | Kosala | PH-I/ PKG-1 | 22.08.2019
127 | JAJPUR | Badachana | Kaimatia | PH-IA (R )/ PKG-1 | 12.08.2020
128 | JAJPUR | Badachana | Kundala | PH-II (R )/ PKG-1 | 28.02.2022
Total (TPCODL) |  |  |  |  | 128
129 | KEONJHAR | Keonjhar Sadar | Raisuan | PH-I/ PKG-7 | 05.02.2016
130 | KEONJHAR | Keonjhar Sadar | Naranpur | PH-I/ PKG-7 | 28.12.2015
131 | KEONJHAR | Champua | Bhadrasahi | PH-I/ PKG-7 | 13.08.2016
132 | KEONJHAR | Champua | Joda Hirakud Colony (New) | PH-I/ PKG-7 | 21.04.2016
133 | KEONJHAR | Champua | Jyotipur | PH-II R/ PKG-3 | 16.03.2018
134 | KEONJHAR | Champua | Kanjiasola | PH-II R/ PKG-3 | 17.03.2022
135 | KEONJHAR | Champua | Basudevpur | PH-II R/ PKG-3 | 05.06.2018
136 | KEONJHAR | Ghasipura | Chhenapadi | PH-I/ PKG-6 | 19.06.2018
137 | KEONJHAR | Ghasipura | Pipilia | PH-II R/ PKG-3 | 01.07.2017
138 | KEONJHAR | Ghasipura | Rekutia | PH-II R/ PKG-3 | 23.09.2018
139 | KEONJHAR | Ghasipura | Sainkul | PH-II R/ PKG-3 | 24.08.2018
140 | KEONJHAR | Ghasipura | Janghira (Buxi-barigaon) | PH-II R/ PKG-3 | 07.01.2022
141 | KEONJHAR | Ghasipura | Pandapada | Ph-III/ PKG-3 | 07.09.2021
142 | KEONJHAR | Patna | Khireitangiri | PH-II R/ PKG-3 | 30.06.2018
143 | KEONJHAR | Patna | Kendeiposhi | PH-II R/ PKG-3 | 24.09.2018
144 | KEONJHAR | Patna | Musakhori | PH-II R/ PKG-3 | 30.03.2017
145 | KEONJHAR | Patna | Machhagarh | PH-II R/ PKG-3 | 27.08.2018
146 | KEONJHAR | Patna | Begunaposi | Ph-III/ PKG-3 | 02.02.2022
147 | KEONJHAR | Patna | Ukhunda | PH-I/ PKG-6 | 10.08.2016
148 | KEONJHAR | Telkoi | Jagmohanpur | PH-II R/ PKG-3 | 03.03.2021
149 | KEONJHAR | Telkoi | Suakati | PH-I/ PKG-6 | 29.03.2017
150 | KEONJHAR | Telkoi | Bhagamunda | PH-II R/ PKG-3 | 10.08.2022
151 | KEONJHAR | Anandapur | Salabani | PH-II R/ PKG-3 | 03.10.2018
152 | KEONJHAR | Anandapur | Salania | PH-II R/ PKG-3 | 04.09.2018
153 | KEONJHAR | Anandapur | Dhenka | PH-II R/ PKG-3 | 24.03.2018
154 | KEONJHAR | Anandapur | Ghatagaon | PH-I/ PKG-6 | 27.09.2016
155 | MAYURBHANJ | Baripada | Raghunathpur | PH-I/ PKG-7 | 05.03.2016
156 | MAYURBHANJ | Bangiriposhi | Randasahi (Kanjiasole) | PH-I/ PKG-6 | 13.05.2016
157 | MAYURBHANJ | Bangiriposhi | Sapanichua | PH-II R/ PKG-3 | 30.06.2018
158 | MAYURBHANJ | Morada | Bhaliasole (Suliapada HQ) | PH-I/ PKG-6 | 26.07.2016
159 | MAYURBHANJ | Morada | Merda(Dambarudhara) | PH-I/ PKG-6 | 03.07.2017
160 | MAYURBHANJ | Morada | Amarda | PH-II R/ PKG-3 | 21.03.2018
161 | MAYURBHANJ | Udala | Nududiha | PH-I/ PKG-6 | 10.08.2016
162 | MAYURBHANJ | Udala | Sarat (Gourichandrapur) | PH-I/ PKG-6 | 19.05.2018
163 | MAYURBHANJ | Rairangpur | Gorumuhasuni (Badmouda) | PH-I/ PKG-6 | 14.07.2016
164 | MAYURBHANJ | Jashipur | Angarapada (Badraruan) | PH-I/ PKG-6 | 15.03.2016
165 | MAYURBHANJ | Saraskana | Sirsa | PH-II R/ PKG-3 | 04.06.2020
166 | MAYURBHANJ | Saraskana | Saragachida | PH-I/ PKG-6 | 07.04.2017
167 | MAYURBHANJ | Saraskana | Manada | PH-II R/ PKG-3 | 12.02.2021
168 | MAYURBHANJ | Badasahi | Salabanisahi (Nahandasole) | PH-II R/ PKG-3 | 04.10.2018
169 | MAYURBHANJ | Badasahi | Ambadalli | PH-II R/ PKG-3 | 27.07.2017
170 | BALASORE | Bhogarai | Mahagab | PH-IAR/ PKG-3 | 03.05.2018
171 | BALASORE | Remuna | Rasalpur | PH-IAR/ PKG-3 | 05.08.2017
172 | BALASORE | Remuna | Swadhinpadia | PH-IA (R )/ PKG-4 | 05.04.2019
173 | BALASORE | Remuna | Durgadevi (Hatiagand Chhak) | PH-II R/ PKG-3 | 31.07.2019
174 | BALASORE | Balasore Sadar | Rameswar Mandir | PH-I(B) | 03.01.2019
175 | BALASORE | Balasore Sadar | Kusudiha | PH-II R/ PKG-3 | 27.06.2018
176 | BALASORE | Balasore Sadar | Chhanua | PH-III/ PKG-5 | 07.08.2022
177 | BALASORE | Nilagiri | Khantapada | PH-II R/ PKG-3 | 28.08.2018
178 | BALASORE | Nilagiri | Ajodhya | PH-II R/ PKG-3 | 14.01.2019
179 | BALASORE | Nilagiri | Badapokhari | Ph-III/ PKG-3 | 09.02.2022
180 | BALASORE | Nilagiri | Berhampur | PH-IAR/ PKG-3 | 16.10.2019
181 | BALASORE | Simulia | Jamujhadi | PH-II R/ PKG-3 | 01.02.2022
182 | BALASORE | Simulia | Ada | PH-II R/ PKG-3 | 01.03.2018
183 | BALASORE | Simulia | Balikhanda | PH-IAR/ PKG-3 | 17.03.2021
184 | BALASORE | Soro | Pitakalia | PH-IAR/ PKG-3 | 26.08.2016
185 | BALASORE | Soro | Bishnupur | PH-II R/ PKG-3 | 08.11.2016
186 | BALASORE | Soro | Kacheripada | PH-II R/ PKG-3 | 15.03.2021
187 | BALASORE | Jaleswar | Bartana | PH-II R/ PKG-3 | 23.01.2020
188 | BALASORE | Jaleswar | Chapala (Shyamnagar) | PH-IAR/ PKG-3 | 25.09.2016
189 | BALASORE | Jaleswar | M. Simulia | PH-IAR/ PKG-3 | 07.09.2016
190 | BALASORE | Basta | Bagada | Ph-III/ PKG-3 | 07.02.2022
191 | BALASORE | Basta | Kalipada | PH-IAR/ PKG-3 | 15.07.2017
192 | BHADRAK | Chandbali | Gadi | PH-IAR/ PKG-3 | 30.05.2019
193 | BHADRAK | Chandbali | Sindol (In place of Sunapenta) | PH-II R/ PKG-3 | 28.05.2018
194 | BHADRAK | Chandbali | Matto | PH-II R/ PKG-3 | 26.07.2018
195 | BHADRAK | Basudevpur | Padampur | PH-IAR/ PKG-3 | 20.12.2022
196 | BHADRAK | Dhamnagar | Ranipokhari (Khadipada) | PH-IAR/ PKG-3 | 23.08.2020
197 | BHADRAK | Dhamnagar | Bilana | PH-II R/ PKG-3 | 29.05.2019
198 | BHADRAK | Bhadrak | Bijegangadharpur | PH-IA (R )/ PKG-4 | 04.02.2020
199 | BHADRAK | Bhadrak | Kundibag | PH-II R/ PKG-3 | 09.12.2016
200 | BHADRAK | Bhadrak | Asura | PH-II R/ PKG-3 | 14.03.2018
201 | BHADRAK | Bhandaripokhari | Manjuri Road | PH-II R/ PKG-3 | 09.11.2017
202 | BHADRAK | Bhandaripokhari | Malda | PH-II R/ PKG-3 | 17.07.2018
203 | BHADRAK | Bhandaripokhari | Nilak | PH-IAR/ PKG-3 | 28.02.2018
204 | JAJPUR | Binjharpur | Pritipur | PH-IAR/ PKG-3 | 18.01.2018
205 | JAJPUR | Binjharpur | Lalbag | Ph-III/ PKG-3 | 19.11.2022
206 | JAJPUR | Bari | Balia | PH-IAR/ PKG-3 | 28.01.2018
207 | JAJPUR | Dharmasala | Barabati | PH-IAR/ PKG-3 | 28.09.2016
208 | JAJPUR | Dharmasala | Chadeidhara | PH-IAR/ PKG-3 | 05.09.2016
209 | JAJPUR | Dharmasala | Narasinghpur | PH-II R/ PKG-3 | 31.05.2021
210 | JAJPUR | Korei | Marthapur | PH-IAR/ PKG-3 | 25.01.2018
211 | JAJPUR | Korei | Ragadi | PH-IA (R )/ PKG-4 | 11.07.2018
212 | JAJPUR | Sukinda | Haripur | PH-IAR/ PKG-3 | 11.09.2016
213 | JAJPUR | Sukinda | Damodarpur | PH-II R/ PKG-3 | 19.11.2019
214 | JAJPUR | Sukinda | Manpur | Ph-III/ PKG-3 | 07.01.2022
215 | JAJPUR | Sukinda | Mantira | Ph-III/ PKG-3 | 21.06.2019
216 | JAJPUR | Jajpur | Baruan | Ph-III/ PKG-3 | 28.09.2020
217 | JAJPUR | Jajpur | Sundaramuhin | Ph-III/ PKG-3 | 04.02.2022
218 | JAJPUR | Jajpur | Basantipadia | PH-IAR/ PKG-3 | 10.09.2016
Total (TPNODL) |  |  |  |  | 90
219 | BOLANGIR | Loisingha | Salebhata | PH-I/ PKG-4 | 04.09.2016
220 | BOLANGIR | Loisingha | Bhadra | PH-II (R )/ PKG-4 | 27.07.2018
221 | BOLANGIR | Loisingha | Bharsuja | PH-III/ PKG-4 | 30.12.2019
222 | BOLANGIR | Loisingha | Kasabahal | PH-III/ PKG-4 | 28.11.2020
223 | BOLANGIR | Titilagarh | Pipalpadar | PH-I/ PKG-4 | 27.10.2016
224 | BOLANGIR | Titilagarh | Budhabahal | PH-II (R )/ PKG-4 | 19.12.2020
225 | BOLANGIR | Titilagarh | Karamtala | PH-II (R )/ PKG-4 | 02.06.2020
226 | BOLANGIR | Patnagarh | Dhumabhta | PH-I/ PKG-4 | 14.05.2018
227 | BOLANGIR | Patnagarh | Juria (Luhasingha) | PH-II (R )/ PKG-4 | 29.07.2018
228 | BOLANGIR | Patnagarh | Kanut | PH-III/ PKG-4 | 05.01.2019
229 | BOLANGIR | Bolangir | Power House | PH-I/ PKG-7 | 07.03.2016
230 | BOLANGIR | Bolangir | Balangir Jail | PH-I/ PKG-7 | 29.12.2015
231 | BOLANGIR | Bolangir | Madiapali | PH-II (R )/ PKG-5 | 24.01.2019
232 | BOLANGIR | Bolangir | Jarasingha | PH-III/ PKG-4 | 14.08.2018
233 | BOLANGIR | Kantabanji | Dabri | PH-I/ PKG-4 | 28.02.2017
234 | BOLANGIR | Kantabanji | Bagbahal (Belpada) | PH-II (R )/ PKG-4 | 23.08.2017
235 | BOLANGIR | Kantabanji | Gudighat | PH-II (R )/ PKG-4 | 30.06.2018
236 | BOLANGIR | Kantabanji | Pandripani | PH-II (R )/ PKG-4 | 01.09.2017
237 | KALAHANDI | Dharmagarh | Behera | PH-I/ PKG-4 | 14.05.2018
238 | KALAHANDI | Dharmagarh | Kalampur | PH-I/ PKG-4 | 05.09.2016
239 | KALAHANDI | Dharmagarh | Ladugaon | PH-II (R )/ PKG-4 | 12.04.2018
240 | KALAHANDI | Dharmagarh | Kasibahal | PH-III/ PKG-4 | 14.09.2019
241 | KALAHANDI | Dharmagarh | Temra | PH-III/ PKG-4 | 28.11.2019
242 | KALAHANDI | Bhawanipatna | College | PH-I/ PKG-7 | 31.08.2016
243 | KALAHANDI | Bhawanipatna | Atanguda | PH-II (R )/ PKG-4 | 25.12.2017
244 | KALAHANDI | Bhawanipatna | Karlapara | PH-III/ PKG-4 | 12.10.2019
245 | KALAHANDI | Narla | Rupara Road | PH-I/ PKG-4 | 17.02.2017
246 | KALAHANDI | Narla | Jura Dubra | PH-II (R )/ PKG-4 | 20.02.2020
247 | KALAHANDI | Narla | Raisinghpur | PH-II (R )/ PKG-4 | 30.10.2018
248 | KALAHANDI | Junagarh | Mahichala | PH-I/ PKG-4 | 01.11.2016
249 | KALAHANDI | Junagarh | Daspur | PH-II (R )/ PKG-4 | 25.06.2020
250 | KALAHANDI | Junagarh | Chichiguda | PH-III/ PKG-4 | 21.03.2019
251 | KALAHANDI | Kesinga | Nunmath | PH-III/ PKG-4 | 21.05.2019
252 | NUAPADA | Khariar | Bargaon | PH-I/ PKG-4 | 24.08.2016
253 | NUAPADA | Khariar | Lesunpali(Rokal) | PH-II (R )/ PKG-4 | 14.06.2022
254 | NUAPADA | Khariar | Chalna | PH-II (R )/ PKG-4 | 05.09.2018
255 | NUAPADA | Khariar | Mahulpada(Timanpur) | PH-III/ PKG-4 | 13.11.2019
256 | NUAPADA | Khariar | Khariar (Badi) | PH-III/ PKG-4 | 01.11.2018
257 | SONEPUR | Sonepur | Bisalpali | PH-I/ PKG-5 | 03.02.2018
258 | SONEPUR | Sonepur | Hedkitikira (Babupali) | PH-II (R )/ PKG-4 | 06.11.2016
259 | SONEPUR | Sonepur | Dubula | PH-III/ PKG-4 | 07.09.2018
260 | SONEPUR | Birmaharajpur | SUBLAYA | PH-I/ PKG-5 | 20.09.2017
261 | SONEPUR | Birmaharajpur | Raxa Chowk, Bhagalpur | PH-II (R )/ PKG-4 | 01.12.2018
262 | SONEPUR | Birmaharajpur | Ainlachhat | PH-III/ PKG-4 | 26.04.2022
263 | SONEPUR | Birmaharajpur | Mursudi | PH-III/ PKG-4 | 02.01.2019
264 | SONEPUR | Birmaharajpur | Seledi | PH-III/ PKG-4 | 04.05.2019
265 | BARGARH | Attabira | Tangarpali | PH-I/ PKG-4 | 11.03.2022
266 | BARGARH | Attabira | Gandturum (Mahulpali) | PH-II (R )/ PKG-4 | 19.01.2019
267 | BARGARH | Attabira | Dhatukpali | PH-III/ PKG-4 | 13.01.2020
268 | BARGARH | Attabira | Patrapali | PH-III/ PKG-4 | 04.08.2020
269 | BARGARH | Bargarh | Khedapali | PH-I/ PKG-4 | 29.09.2016
270 | BARGARH | Bargarh | Tora | PH-I/ PKG-7 | 31.03.2016
271 | BARGARH | Bhatli | Ghenss | PH-I/ PKG-4 | 15.10.2017
272 | BARGARH | Bhatli | Kandapala | PH-II (R )/ PKG-4 | 07.06.2018
273 | BARGARH | Bhatli | Udeypali | PH-II (R )/ PKG-4 | 26.12.2017
274 | BARGARH | Bhatli | Dasmail | PH-II (R )/ PKG-4 | 09.11.2016
275 | BARGARH | Bhatli | Raisobha | PH-III/ PKG-4 | 15.01.2019
276 | BARGARH | Bhatli | Ambabhona | PH-III/ PKG-4 | 14.08.2018
277 | BARGARH | Bijepur | Balitikra | PH-II (R )/ PKG-4 | 05.08.2017
278 | BARGARH | Bijepur | Laumunda (Arda) | PH-I/ PKG-4 | 04.07.2017
279 | BARGARH | Bijepur | Sarandapali | PH-II (R )/ PKG-4 | 26.11.2016
280 | BARGARH | Bijepur | Kundakhai | PH-II (R )/ PKG-4 | 14.12.2017
281 | BARGARH | Bijepur | Charmunda | PH-III/ PKG-4 | 23.08.2018
282 | BARGARH | Padampur | Dava | PH-I/ PKG-4 | 20.09.2017
283 | BARGARH | Padampur | Lakhamara | PH-II (R )/ PKG-4 | 11.02.2019
284 | BARGARH | Padampur | Jhitiki | PH-III/ PKG-4 | 30.12.2020
285 | BARGARH | Padampur | Dahita | PH-III/ PKG-4 | 20.07.2020
286 | BARGARH | Padampur | Mandosil | PH-III/ PKG-4 | 04.01.2021
287 | BARGARH | Padampur | Dungripali | PH-III/ PKG-4 | 22.01.2020
288 | DEOGARH | Deogarh | Bhakta Bad Kudar | PH-I/ PKG-5 | 29.08.2016
289 | DEOGARH | Deogarh | Reamal | PH-II (R )/ PKG-4 | 03.09.2018
290 | DEOGARH | Deogarh | Parposi | PH-III/ PKG-4 | 31.10.2022
291 | JHARSUGUDA | Brajrajnagar | Dhulunda | PH-I/ PKG-5 | 05.10.2018
292 | JHARSUGUDA | Brajrajnagar | Brajrajnagar | PH-I/ PKG-7 | 05.03.2016
293 | JHARSUGUDA | Brajrajnagar | Lakhanpur | PH-II (R )/ PKG-4 | 12.11.2020
294 | JHARSUGUDA | Brajrajnagar | Gandhi Chowk | PH-II (R )/ PKG-5 | 18.03.2022
295 | JHARSUGUDA | Brajrajnagar | Pandri | PH-III/ PKG-4 | 03.09.2020
296 | JHARSUGUDA | Jharsuguda | Purna | PH-I/ PKG-5 | 03.06.2016
297 | JHARSUGUDA | Jharsuguda | Jhadeswar Mandir(Sarbhal) | PH-I/ PKG-7 | 09.10.2015
298 | JHARSUGUDA | Jharsuguda | Durlaga | PH-II (R )/ PKG-5 | 24.01.2019
299 | JHARSUGUDA | Jharsuguda | Arda | PH-III/ PKG-4 | 30.11.2018
300 | JHARSUGUDA | Jharsuguda | Jhariabahal | PH-III/ PKG-4 | 03.11.2021
301 | JHARSUGUDA | Jharsuguda | Sodamal | PH-III/ PKG-4 | 28.01.2020
302 | JHARSUGUDA | Jharsuguda | Kirmira | PH-III/ PKG-4 | 13.01.2020
303 | JHARSUGUDA | Jharsuguda | Buromal | PH-III/ PKG-5 | 08.12.2021
304 | SAMBALPUR | Rairakhol | Jujumura | PH-I/ PKG-5 | 21.08.2016
305 | SAMBALPUR | Rairakhol | Kisinda | PH-I/ PKG-5 | 27.04.2018
306 | SAMBALPUR | Rairakhol | Padiabahal | PH-I/ PKG-7 | 07.03.2016
307 | SAMBALPUR | Rairakhol | Kadaligarh | PH-II (R )/ PKG-4 | 07.01.2023
308 | SAMBALPUR | Rairakhol | Katarbaga | PH-II (R )/ PKG-4 | 15.03.2019
309 | SAMBALPUR | Rairakhol | Batagaon | PH-III/ PKG-4 | 29.08.2022
310 | SAMBALPUR | Rairakhol | Hero | PH-III/ PKG-4 | 26.12.2018
311 | SAMBALPUR | Sambalpur | Badabazar | PH-I/ PKG-7 | 22.03.2017
312 | SAMBALPUR | Sambalpur | Burla University (Jyotivihar) | PH-I(B) | 02.07.2020
313 | SAMBALPUR | Sambalpur | Kainsar | PH-II (R )/ PKG-5 | 08.01.2022
314 | SAMBALPUR | Kuchinda | Garposh | PH-I/ PKG-5 | 29.11.2016
315 | SAMBALPUR | Kuchinda | Fasimal | PH-II (R )/ PKG-4 | 11.07.2018
316 | SAMBALPUR | Kuchinda | Kusumi | PH-II (R )/ PKG-4 | 21.11.2019
317 | SAMBALPUR | Kuchinda | Jhariabahal | PH-III/ PKG-4 | 29.10.2018
318 | SAMBALPUR | Kuchinda | Bhojpur | PH-III/ PKG-4 | 01.11.2018
319 | SAMBALPUR | Kuchinda | Guchura | PH-III/ PKG-4 | 23.10.2019
320 | SAMBALPUR | Kuchinda | Khandakata | PH-III/ PKG-4 | 25.01.2019
321 | SAMBALPUR | Kuchinda | Lahasa | PH-III/ PKG-4 | 10.06.2019
322 | SAMBALPUR | Kuchinda | Rangiatikra | PH-III/ PKG-4 | 11.01.2023
323 | SAMBALPUR | Rengali | Parmanpur | PH-III/ PKG-4 | 09.07.2018
324 | SAMBALPUR | Rengali | Gunderpur | PH-III/ PKG-4 | 25.02.2020
325 | SAMBALPUR | Rengali | Chipilima | PH-III/ PKG-5 | 15.01.2021
326 | SAMBALPUR | Rengali | Lapanga | PH-I/ PKG-5 | 07.06.2017
327 | SAMBALPUR | Rengali | Maneswar | PH-III/ PKG-5 | 30.11.2021
328 | SUNDARGARH | Bonai | Tuniapali | PH-I/ PKG-5 | 16.10.2016
329 | SUNDARGARH | Bonai | Burda/Malda (Oraghat) | PH-II (R )/ PKG-4 | 24.05.2022
330 | SUNDARGARH | Bonai | K.Balang | PH-III/ PKG-4 | 13.11.2020
331 | SUNDARGARH | Bonai | Singhapada | PH-III/ PKG-4 | 12.06.2019
332 | SUNDARGARH | Talasara | Karamdihi | PH-I/ PKG-5 | 14.07.2016
333 | SUNDARGARH | Talasara | Balisankara | PH-II (R )/ PKG-4 | 16.08.2017
334 | SUNDARGARH | Talasara | Jarangloi | PH-III/ PKG-4 | 29.11.2018
335 | SUNDARGARH | Talasara | Sahajbahal | PH-III/ PKG-4 | 01.11.2019
336 | SUNDARGARH | Birmitrapur | Raibaga | PH-I/ PKG-5 | 14.01.2019
337 | SUNDARGARH | Biramitapur | Jareikela | PH-II (R )/ PKG-4 | 22.01.2019
338 | SUNDARGARH | Rourkela | Bandamunda | PH-I/ PKG-7 | 05.08.2016
339 | SUNDARGARH | Rourkela | Gopabandhupalli | PH-I/ PKG-7 | 31.07.2017
340 | SUNDARGARH | Rourkela | Civil Township, Rourkela | PH-I(B) | 30.01.2017
341 | SUNDARGARH | Rourkela | Hamirpur (Municipality) | PH-II (R )/ PKG-4 | 25.09.2018
342 | SUNDARGARH | Rourkela | Kalingavihar | PH-II (R )/ PKG-5 | 16.01.2018
343 | SUNDARGARH | Raghunathpali | Jalda | PH-I/ PKG-7 | 09.09.2016
344 | SUNDARGARH | Raghunathpali | Dalposh | PH-II (R )/ PKG-4 | 23.09.2017
345 | SUNDARGARH | Rajgangpur | Alanda | PH-I/ PKG-5 | 01.10.2017
346 | SUNDARGARH | Rajgangpur | Biringtoli | PH-III/ PKG-4 | 15.03.2019
347 | SUNDARGARH | Rajgangpur | Balanda | PH-II (R )/ PKG-4 | 28.08.2020
348 | SUNDARGARH | Rajgangpur | Jharbeda (Jampali) | PH-III/ PKG-4 | 24.04.2021
349 | SUNDARGARH | Sundargarh | Majhapara | PH-I/ PKG-5 | 10.01.2019
350 | SUNDARGARH | Sundargarh | Bileimunda | PH-II (R )/ PKG-4 | 11.02.2021
351 | SUNDARGARH | Sundargarh | Tumbapali | PH-II (R )/ PKG-4 | 03.11.2016
352 | SUNDARGARH | Sundargarh | Darlipali | PH-III/ PKG-4 | 10.06.2020
353 | SUNDARGARH | Sundargarh | Hemgir | PH-III/ PKG-4 | 27.07.2021
354 | SUNDARGARH | Sundargarh | Mangaspur | PH-III/ PKG-4 | 19.11.2020
355 | SUNDARGARH | Sundargarh | Kundukela | PH-III/ PKG-4 | 24.03.2021
Total (TPWODL) |  |  |  |  | 137
356 | GANJAM | K.S. Nagar | Sumandala | PH-IA(R )/ PKG-2 | 03.05.2017
357 | GANJAM | K.S. Nagar | Odialapur (Rajpur/Dasiamarpalli) | PH-III/ PKG-2 | 21.01.2022
358 | GANJAM | Hinjlicut | Pudingi | PH-IA(R )/ PKG-2 | 04.08.2017
359 | GANJAM | Hinjlicut | K.Karadkana | PH-IA(R )/ PKG-2 | 07.04.2017
360 | GANJAM | Hinjlicut | Nandika (Sasan Ambagaon) | PH-IA(R )/ PKG-2 | 11.04.2017
361 | GANJAM | Hinjlicut | M.J. Pur | PH-III/ PKG-2 | 20.11.2019
362 | GANJAM | Aska | Paikajamuna | PH-IA(R )/ PKG-2 | 15.07.2017
363 | GANJAM | Sanakhemundi | Kheriguma in place of Dhaugaon | PH-IA(R )/ PKG-2 | 02.03.2017
364 | GANJAM | Sanakhemundi | Jahada (Putu) | PH-III/ PKG-2 | 02.12.2021
365 | GANJAM | Sanakhemundi | Palaspur | PH-III/ PKG-2 | 22.07.2021
366 | GANJAM | Digaphandi | Sidheswar | PH-IA(R )/ PKG-2 | 18.03.2017
367 | GANJAM | Chikiti | Jarada | PH-IA(R )/ PKG-2 | 22.07.2017
368 | GANJAM | Chikiti | Surangi | PH-IA(R )/ PKG-2 | 03.03.2017
369 | GANJAM | Chikiti | Pitatali | PH-III/ PKG-2 | 04.02.2019
370 | GANJAM | Chikiti | Nuapada | PH-III/ PKG-2 | 29.01.2021
371 | GANJAM | Gopalpur | Mantridi (Golanthara) | PH-IA(R )/ PKG-2 | 12.11.2016
372 | GANJAM | Gopalpur | Nimakhandi | PH-IA (R )/ PKG-4 | 28.07.2020
373 | GANJAM | Gopalpur | Gopalpur | PH-III/ PKG-2 | 27.07.2022
374 | GANJAM | Berhampur | Vidyutpur Colony | PH-I(B) | 22.10.2016
375 | GANJAM | Khalikote | Balia (Patrapur) | PH-IA(R )/ PKG-2 | 28.06.2017
376 | GANJAM | Khalikote | Sakiri | PH-II (R )/ PKG-5 | 06.09.2017
377 | GANJAM | Polasara | Chirikipada (Narasinghapalli) | PH-IA(R )/ PKG-2 | 07.02.2017
378 | GANJAM | Polasara | Hatiota | PH-III/ PKG-2 | 23.07.2021
379 | GANJAM | Chatrapur | Baulagaon | PH-IA(R )/ PKG-2 | 24.08.2017
380 | GANJAM | Chatrapur | Khandadeuli | PH-III/ PKG-2 | 24.07.2021
381 | GANJAM | Bhanjanagar | B.D.Pur | PH-IA(R )/ PKG-2 | 07.01.2017
382 | GANJAM | Bhanjanagar | Gayaganda | PH-III/ PKG-2 | 29.12.2021
383 | GANJAM | Bhanjanagar | Daha | PH-III/ PKG-2 | 28.01.2021
384 | GANJAM | Bhanjanagar | Gallary | PH-III/ PKG-2 | 03.10.2020
385 | GANJAM | Soroda | Banka | PH-III/ PKG-2 | 13.06.2021
386 | GANJAM | Soroda | Kanteipalli (Netagam) | PH-IA(R )/ PKG-2 | 31.07.2017
387 | GANJAM | Soroda | Asurbandha (Gajalbadi) | PH-III/ PKG-2 | 09.10.2021
388 | GAJAPATI | Mohona | R.Udayagiri | PH-IA(R )/ PKG-2 | 02.08.2017
389 | GAJAPATI | Mohona | Nuagada | PH-IA(R )/ PKG-2 | 04.01.2017
390 | GAJAPATI | Mohona | Adava | PH-II (R )/ PKG-5 | 09.09.2019
391 | GAJAPATI | Mohona | Ramagiri | PH-III/ PKG-2 | 27.07.2018
392 | GAJAPATI | Mohona | Chandragiri | PH-III/ PKG-2 | 20.06.2019
393 | GAJAPATI | Paralakhemundi | Sobara | PH-IA(R )/ PKG-2 | 30.12.2016
394 | GAJAPATI | Paralakhemundi | Paniganda | PH-III/ PKG-2 | 30.06.2021
395 | GAJAPATI | Paralakhemundi | Kharada | PH-III/ PKG-2 | 18.04.2018
396 | GAJAPATI | Paralakhemundi | Ambajhari/Jiranga | PH-III/ PKG-2 | 31.07.2019
397 | BOUDH | Boudh | Baghiapada | PH-I/ PKG-2 | 29.01.2015
398 | BOUDH | Boudh | Rambhikuta | PH-III/ PKG-2 | 27.02.2019
399 | BOUDH | Kantamal | Ghantapada (Back side of Medical) | PH-I/ PKG-2 | 01.03.2016
400 | KANDHAMAL | Baliguda | Sarangagada | PH-I/ PKG-2 | 02.02.2016
401 | KANDHAMAL | Baliguda | Barakhama | PH-III/ PKG-2 | 14.09.2022
402 | KANDHAMAL | Phulbani | Ganjuguda (dahapadar) | PH-I/ PKG-2 | 02.02.2016
403 | KANDHAMAL | Phulbani | Gochhapada | PH-III/ PKG-2 | 08.04.2022
404 | KANDHAMAL | Phulbani | Nuapadar | PH-III/ PKG-2 | 05.10.2020
405 | KANDHAMAL | G.Udayagiri | Karada | PH-I/ PKG-2 | 31.07.2016
406 | KANDHAMAL | G.Udayagiri | Gutingia | PH-III/ PKG-2 | 07.09.2019
407 | RAYAGADA | Rayagada | Jimilipeta | PH-I/ PKG-2 | 23.11.2015
408 | RAYAGADA | Rayagada | Amlabhata | PH-II (R )/ PKG-5 | 24.12.2020
409 | RAYAGADA | Rayagada | Pitamahal | PH-III/ PKG-2 | 31.12.2018
410 | RAYAGADA | Rayagada | Pipalguda | PH-III/ PKG-2 | 10.09.2021
411 | RAYAGADA | Gunupur | Dambasora | PH-I/ PKG-2 | 21.11.2015
412 | RAYAGADA | Gunupur | Seriguda | PH-II (R )/ PKG-5 | 06.04.2022
413 | RAYAGADA | Gunupur | Kailaspur (Dhepaguda) | PH-III/ PKG-2 | 21.11.2018
414 | RAYAGADA | Gunupur | Luhagadi (Kenduguda) | PH-III/ PKG-2 | 15.11.2019
415 | RAYAGADA | Gunupur | Jaltara | PH-III/ PKG-2 | 06.12.2020
416 | RAYAGADA | Bissam Cuttack | K.Singpur | PH-I/ PKG-2 | 28.11.2015
417 | RAYAGADA | Bissam Cuttack | Ambadola | PH-I/ PKG-2 | 31.03.2016
418 | RAYAGADA | Bissam Cuttack | Chandrapur | PH-III/ PKG-2 | 31.01.2019
419 | RAYAGADA | Bissam Cuttack | Keutaguda/Antamuda | PH-III/ PKG-2 | 25.07.2019
420 | RAYAGADA | Bissam Cuttack | Hatadahikal | PH-III/ PKG-2 | 28.02.2019
421 | KORAPUT | Koraput | Dasmantapur | PH-I/ PKG-3 | 05.07.2016
422 | KORAPUT | Koraput | Marthamput | PH-III/ PKG-2 | 18.08.2021
423 | KORAPUT | Koraput | Ramagiri | PH-III/ PKG-2 | 04.11.2020
424 | KORAPUT | Laxmipur | Podagada | PH-I/ PKG-3 | 17.06.2017
425 | KORAPUT | Laxmipur | Kumbhariput (Nialabadi) | PH-III/ PKG-2 | 29.01.2022
426 | KORAPUT | Patangi | Kunduli (Sosorisapadar) | PH-I/ PKG-3 | 04.04.2017
427 | KORAPUT | Patangi | Padua | PH-III/ PKG-2 | 17.10.2022
428 | KORAPUT | Jeypore | Kamta | PH-I/ PKG-3 | 08.05.2016
429 | KORAPUT | Jeypore | Kebidi | PH-III/ PKG-2 | 03.07.2019
430 | KORAPUT | Jeypore | Kaliagoan | PH-III/ PKG-2 | 10.01.2019
431 | KORAPUT | Jeypore | Haraduli/ Jammunda | PH-III/ PKG-2 | 17.05.2021
432 | KORAPUT | Jeypore | Balia | PH-III/ PKG-2 | 28.05.2020
433 | KORAPUT | Kotpad | Chalanguda | PH-I/ PKG-3 | 31.03.2016
434 | KORAPUT | Kotpad | Digapur | PH-III/ PKG-2 | 14.05.2020
435 | KORAPUT | Kotpad | Bagderi | PH-III/ PKG-2 | 09.07.2021
436 | KORAPUT | Kotpad | S.B.Nuagaon | PH-III/ PKG-2 | 05.06.2021
437 | MALKANGIRI | Chitrakonda | Govindapalli | PH-I/ PKG-3 | 29.08.2016
438 | MALKANGIRI | Chitrakonda | Padmagiri (Mahupadar) | PH-III/ PKG-2 | 19.04.2022
439 | MALKANGIRI | Malkangiri | Podia | PH-I/ PKG-3 | 15.11.2017
440 | MALKANGIRI | Malkangiri | MV-27 | PH-III/ PKG-2 | 25.02.2019
441 | MALKANGIRI | Malkangiri | Badili | PH-III/ PKG-2 | 27.12.2018
442 | NABARANGPUR | Umarkote | Adhikariguda | PH-I/ PKG-3 | 24.12.2016
443 | NABARANGPUR | Umarkote | Murtuma | PH-I/ PKG-3 | 28.09.2016
444 | NABARANGPUR | Dabugaon | Medena | PH-I/ PKG-3 | 26.09.2017
445 | NABARANGPUR | Dabugaon | Kodinga | PH-III/ PKG-2 | 30.07.2019
446 | NABARANGPUR | Dabugaon | Babajiguda (Antasara) | PH-III/ PKG-2 | 17.11.2020
447 | NABARANGPUR | Nabarangapur | Sanamasigaon | PH-I/ PKG-3 | 02.12.2016
448 | NABARANGPUR | Nabarangapur | Chutiguda | PH-III/ PKG-2 | 25.03.2019
449 | NABARANGPUR | Nabarangapur | Anchalguma | PH-III/ PKG-2 | 16.11.2020
Total (TPSODL) |  |  |  |  | 94
Grand Total |  |  |  |  | 449

## IPDS
LIST OF NEW 33/11 K SUB STATIONS CONSTRUCTED & COMMISIONED UNDER IPDS PROJECT.
As per scope :- 14 nos PSS
Sl No. | Discom | District | Town Name | Name of the substation already commisioned | EPC name | Handing over Status | Control Room Building | Erection of equipments | Tesing & Pre commissioning | Charged | Target | Inspection by Electrical Inspector | Incoming 33 Kv line | Outgoing 11 KV feeders | Issues |  |  | Capacity of PSS | Amount spend on PSS in Rs. Cr.
1 | TPCODL | Khordha | Bhubaneswar | Baranga | M/S Sterling & Wilson Pvt Ltd. | Yet to be taken over | Completed | Completed |  | Yes | [7 empty] | 2X8 MVA | 4.21
2 | TPCODL | Khordha | Bhubaneswar | Pandra | M/S Sterling & Wilson Pvt Ltd. | Handed over | Completed | Completed |  | yes | [7 empty] | 2X8 MVA | 4.21
3 | TPCODL | Cuttack | Cuttack | Chauliaganj | M/S Sterling & Wilson Pvt Ltd. | Yet to be taken over | Completed | Completed |  | yes | [7 empty] | 2X8 MVA | 4.21
4 | TPCODL | Cuttack | Cuttack | Ranihat | M/S Sterling & Wilson Pvt Ltd. | Yet to be taken over | Completed | Completed |  | yes | [7 empty] | 2X8 MVA | 4.21
5 | TPNODL | Balasore | Balasore | Kashimabad | M/S OSIC | Completed/Inspection pending | WIP | WIP | No | No | 31.01.2019 | NO | 1.2 K.M Line work (Pole erection complete ) | 4 feeders- 1.63 K.M |  |  |  | 2 X 5 MVA | 4.8871
6 | TPNODL | Balasore | Balasore | Kalimandir | M/S OSIC | Completed/Inspection pending | WIP | WIP | No | No | 15.02.2019 | NO | 0.230 KM Line work (No work done) | 2 Feeder (Pole erection completed) |  |  |  | 2 X 5 MVA | 4.8871
7 | TPNODL | Bhadrak | Bhadrak | Dhamnagar | M/S OSIC | Handed Over | Completed | Completed | Yes | yes | 31.12.2019 | NO | 2 KM 33 KV line work completed | 3 feeder- 10 K.M ( Pole erection completed) | Stringing can only be carried out after harvesting | CESU | 8.4 | 2 X 5 MVA | 4.8871
8 | TPNODL | Bhadrak | Bhadrak | Charigharia | M/S OSIC | Completed/Inspection pending | WIP | WIP | No | No | 31.01.2019 | NO | 2.81 KM line work pending | 4 feeder- 8 K.M ( pole erection completed for only 2 K.M |  |  |  | 2 X 5 MVA | 4.8871
9 | TPNODL | Jajpur | Jajpur | Fire Station | M/S OSIC | Handed Over | Completed | Completed | Yes | yes | 15.12.2019 | NO | 0.9 K.M Line work (Work complete except one road crossing) | 4 Feeders-14.23 K.M ( 11.73 K.M stringing completed). | NHAI approval soughted for 33 KV I/C Line road crossing. Rest 2.5 K.M line will be completed after harvesting . | Nesco | 19.72 | 2 X 5 MVA | 4.8871
10 | TPNODL | Jajpur | Jajpur | Vyasasorabar | M/S OSIC | Handed Over | Completed | Completed | Yes | yes | 15.12.2019 | NO | 2.1 KM Line work (All Pole erection completed and 1 KM stringing completed) | 2 feeder- 5.248 KM (Pole erection completed for all feeders). 2 K.M stringing already completed | 3 nos of poles of 33 KV line under ROW by local people. The matter has been brought in notice of NESCO officials | Southco | 4.43 | 2 X 5 MVA | 4.8871
11 | TPNODL | Mayurbhanj | Mayurbhanj | Lalbazar | M/S OSIC | Handed Over | Completed | Completed | Yes | yes | 30.11.2019 | NO | 2.5 K.M Line work (Pole erection completed) | 4 feeder - 8.06 K.M (Pole erection completed) | Sufficient Shtdwon not being provided for stringing works of 33 KV line. | Wesco | 4.095 | 2 X 5 MVA | 4.8871
12 | TPSODL | Ganjam | Berhampur | Dura | M/S Sterling & Wilson Pvt Ltd. | Yet to be taken over | Completed | Completed | No | Yes | 31.12.2019 |  | Out of 5.92 K.M, 4.2 K.M work has already been completed. | 3 feeder - 2.68 K.M (2.1 K.M Work complete) | For 33 KV new line ROW raised by R&B. NHAI clearance soughted for 11 KV Line road crossing. |  | 36.645 | 2 X 5 MVA | 4.45
13 | TPWODL | Jharsuguda | Jharsuguda | Jhadeswar | M/S L&T |  | Completed | Completed | Yes | No |  |  | 6 KM line |  |  |  |  | 2 X 5 MVA | 4.775
14 | TPWODL | Sambalpur | Sambalpur | Chaunpur | M/S L&T | Handed over | Completed | Completed | Yes | Yes |  |  | 34 KM (Double circuit) | 4 feeder -9.9 Km( all works completed) |  |  |  | 2 X 5 MVA | 4.775
Total for 14 Nos of PSS | [17 empty] | 164 MVA | 65.05
Expenditure:-
Expenditure for construction of above mentioned 8 Substations is Rs 36.65 Crores

## DDUGJY
List of 33/11kV PSS Constructed and commissioned under DDUGJY Project:
| District | Block | SS with capacity | Type of work | Feeder from | Feeder to | Length of line (in Ckm) | Cost ( in lakhs) | Total cost of SS with associated feeder (Rs. in Cr)
B.New Substation | Cuttack | Baranga | Naranpur/ Trisulia (2x3.15Mva) | New SS |  |  | - | 340.6803 | 5.6507
A.33 kV New Line |  | Baranga |  | 33 kV New | JDS Feeder | Baranga new PSS | 3.309 | 55.7847
C. 11kV New Line |  | Baranga |  | 11 kV New | Naranpur(Trisulia) | Bidyadharpur tapping | 9.985 | 88.4076
C. 11kV New Line |  | Baranga |  | 11 kV New | Naranpur(Trisulia) | Belagachna | 3.664 | 32.4412
C. 11kV New Line |  | Baranga |  | 11 kV New | Naranpur(Trisulia) | Madhupur | 5.394 | 47.7587
B.New Substation | Khurda | Begunia | Hatabasta (2x5 Mva) | New SS |  |  | - | 347.3664 | 4.3974
A.33 kV New Line |  | Begunia |  | 33 kV New | Cut point Binodpada | Hatabasta pss | 3.3 | 55.6329
C. 11kV New Line |  | Begunia |  | 11 kV New | Hatabasta new PSS | Bankoi | 1.7 | 15.0519
C. 11kV New Line |  | Begunia |  | 11 kV New | Hatabasta new PSS | Sunakhala (Kumbhari) | 1.5 | 13.2811
C. 11kV New Line |  | Begunia |  | 11 kV New | Hatabasta new PSS | Srichandanpur Tapping (Kumaruni) | 0.95 | 8.4113
B.New Substation |  | Chilika | Solari (2x5 Mva) | New SS |  |  | - | 358.1491 | 4.1928
A.33 kV New Line |  | Chilika |  | 33 kV New | Cut point Paikaosadia | Solari pss | 0.065 | 1.0958
C. 11kV New Line |  | Chilika |  | 11 kV New | Solari pss | Brahman kusudiha Tapping | 3.53 | 31.2548
C. 11kV New Line |  | Chilika |  | 11 kV New | Solari pss | Paika kusudiha tapping | 3.25 | 28.7756
B.New Substation | Puri | Nimapada | Charichaka (2x3.15Mva) | New SS |  |  | - | 343.9029 | 4.3401
A.33 kV New Line |  | Nimapada |  | 33 kV New | Charichaka | kakatpur cut point | 1.59 | 26.805
C. 11kV New Line |  | Nimapada |  | 11 kV New | Charichaka | Sailo feeder | 0.75 | 6.6405
C. 11kV New Line |  | Nimapada |  | 11 kV New | Charichaka | Charichaka to BSNL office (Market feeder) | 0.8 | 7.0832
C. 11kV New Line |  | Nimapada |  | 11 kV New | Charichaka | Charichaka to Charichaka Bazar (Tampalo feeder) | 5.6 | 49.5826
B.New Substation |  | Nimapada | Dandipur (2x3.15Mva) | New SS |  |  | - | 339.3471 | 5.7944
A.33 kV New Line |  | Nimapada |  | 33 kV New | Dandipur | Dandipur new PSS | 12.7 | 214.1025
C. 11kV New Line |  | Nimapada |  | 11 kV New | Dandipur | Kaliapada feeder | 1.47 | 13.0154
C. 11kV New Line |  | Nimapada |  | 11 kV New | Dandipur | Dhanua feeder | 1.425 | 12.617
C. 11kV New Line |  | Nimapada |  | 11 kV New | Dandipur | Road cross Dp | 0.04 | 0.35416
| TPCODL |  |  |  |  | 5nos PSS | For 5nos PSS | Total Cost | 24.3754
| Balangir | Patnagarh | Larambha (2x5MVA) | New SS |  |  |  | 415.377 | 5.6586
|  |  |  | 33 kV New | Ghumer Substation | 33/11kV Larambha PSS | 8.041 | 130.72
|  |  |  | 11 kV New | 33/11kV Larambha PSS | Dangabahal | 1.58 | 13.493
|  |  |  | 11 kV New | 33/11kV Larambha PSS | Larambha village | 0.259 | 3.18
|  |  |  | 11 kV New | 33/11kV Larambha PSS | Bagmund | 0.252 | 3.09
| Balangir | Balangir | Kudasingha (2x3.15MVA) | New SS |  |  |  | 401.11 | 5.6229
|  |  |  | 33 kV New | Deogaon Substation(Kuthrula tapping) | 33/11kV Kudasingha PSS | 5.75 | 76.048
|  |  |  | 11 kV New | 33/11kV Kudasingha PSS | Kudasingha village | 1.345 | 10.127
|  |  |  | 11 kV New | 33/11kV Kudasingha PSS | Chikalbahal | 6.221 | 49.331
|  |  |  | 11 kV New | 33/11kV Kudasingha PSS | Sinkhaman | 3.356 | 25.673
| Bargarh | Bargarh | Kamagaon (2x5MVA) | New SS |  |  |  | 456.426 | 8.3094
|  |  |  | 33 kV New | 33/11kV Khedapalli Substation | 33/11kV Kamagaon substation | 14.93 | 204.989
|  |  |  | 11 kV New | 33/11kV Kamagaon substation | Kamagaon | 3.74 | 27.669
|  |  |  | 11 kV New | 33/11kV Kamagaon substation | Kharmunda | 8.7 | 59.604
|  |  |  | 11 kV New | 33/11kV Kamagaon substation | Bandasarala | 11.19 | 82.256
| Jharsuguda | Lakhanpur | Govindpur (2x5MVA) | New SS |  |  |  | 431.634 | 5.7193
|  |  |  | 33 kV New | Mega lift 33/11kV SS | 33/11kV Govindpur PSS | 1.547 | 26.769
|  |  |  | 11 kV New | 33//11kV Govindpur PSS | Kadamdihi | 2.967 | 24.69
|  |  |  | 11 kV New | 33//11kV Govindpur PSS | Jamagaon | 2.931 | 26.015
|  |  |  | 11 kV New | 33//11kV Govindpur PSS | Bhourkhol | 7.412 | 62.824
| Kalahandi | Bhawanipatna | Bandhapala (2x5MVA) | New SS |  |  |  | 469.33 | 6.1854
|  |  |  | 33 kV New | 33kV Junagarh Feeder | 33/11kV Bandhapala PSS | 0.44 | 8.57
|  |  |  | 11 kV New | 33/11kV Bandhapala PSS | Kartagiri | 9.104 | 76.76
|  |  |  | 11 kV New | 33/11kV Bandhapala PSS | Badili | 7.347 | 55.938
|  |  |  | 11 kV New | 33/11kV Bandhapala PSS | Bandhapala | 1.122 | 7.938
| Sambalpur | Rengali | Rengali (2x5MVA) | New SS |  |  |  | 413.98 | 4.9726
|  |  |  | 33 kV New | Rengali Substation | New Rengali 33/11kV PSS | 0.08 | 19.756
|  |  |  | 11 kV New | New Rengali 33/11kV PSS | Industrial | 2 | 18.653
|  |  |  | 11 kV New | New Rengali 33/11kV PSS | Nishan Vanga | 3.1 | 29.312
|  |  |  | 11 kV New | New Rengali 33/11kV PSS | Polytechnic | 1.526 | 15.557
| Sundargarh | Nuagaon | Raibahal (2x5MVA) | New SS |  |  |  | 482.69 | 7.4472
|  |  |  | 33 kV New | Hamirpur | 33/11kV Raibahal PSS | 11.496 | 206.52
|  |  |  | 11 kV New | 33/11kV Raibahal PSS | Fulijhar | 2.142 | 22.476
|  |  |  | 11 kV New | 33/11kV Raibahal PSS | Gopapur | 3.166 | 29.576
|  |  |  | 11 kV New | 33/11kV Raibahal PSS | Ankurpalli | 0.267 | 3.46
| TPWODL |  |  |  |  | 7nos PSS | For 7nos PSS | Total Cost | 43.9154
| Total 12nos PSS Project Cost | [7 empty] | 68.2908