## Completed
Sl. No. | Name of the Project with scope of work | Estimated cost (Rs. Cr.) | Actual Award Cost (Rs. Cr.) | Actual expenditure (unaudited) upto 11/2025 (Rs. Cr.) | Work order No. & Date | Scheduled date of completion | Approval of Commission(TP/BP & IP) | Revised date of completion | Actual Date of completion | Estimated cost (Rs. Cr.) | Revised Estimated cost (Rs. Cr.) | Actual expenditure (unaudited) upto 11/2025 (Rs. Cr.) | Actual Cost Capitalised upto 31.03.2025 | Cost Over Run | Time Over Run | Reason of cost escalation | Reasion for delay
PROJECTS COMPLETED DURING (April' 24 to Mar-25)
1 | 2x40MVA, 220/33kV GSS at Balichandrapur (Palei) | 47.28 | 41.77 | 45.9 | W.O No. 930 dtd. 27.02.2019. | 26.02.2021 | 1. 63/2020 (BP) 03.11.2021 2. 45/2021 (IP) 27.12.2021 | 2024-06-01 | 22.05.2024 | 47.28 | 47.28 | 45.9 | 49.79 | *** | 39 months | *** | Land handover delayed due to court case,work started from 17.09.2021
2 | 2x160MVA + 2x20MVA, 220/132/33kV GSS at Turmunga | 119.3 | 103.12 | 101.38 | W.O No. 701 Dtd. 18.02.2019 | 17.02.2021 | 1. 18/2017 (TP) 09.04.2019 2. 05/2016 (BP) 30.07.2016 3. 52/2022 (IP) 5.12.2023 | 2022-02-01 | 22.07.2024 | 119.3 | 119.3 | 101.38 |  | *** | 41 months | *** | Forest clearance issue. Resolved through relevant Govt. Administration & Local bodies.
3 | 2x20MVA, 132/33kV GSS at Brundabahal | 52.15 | 41.54 | 27.11 | W.O No.200 Dtd.06.02.2021 | 25.08.2022 | 1. 63/2020 (BP) 03.11.2021 2. 57/2021 (IP) 12.01.2022 | 2024-03-01 | 09.08.2024 | 52.15 | 52.15 | 27.11 | 28.94 | *** | 24 months | *** | ROW issue.Resolved through relevant Govt. Administration & Local bodies.
4 | 2x63MVA, 132/33kV GIS at Nayapalli | 120.48 | 87.88 | 79.97 | W.O No. 164 dtd. 07.03.2019 | 06.09.2020 | 1. 63/2020 (BP) 03.11.2021 2. 49/2021 (TP) 12.01.2022 3. 52/2022 (IP) 5.12.2023 | 30.05.23 | 23.10.2024 | 120.48 | 120.48 | 79.97 | 92.55 | *** | 49 months | *** | ROW issue.Resolved through relevant Govt. Administration & Local bodies.
5 | 220kV LILO from Balimela-Jayanagar CKT-I to Govindpalli GSS | 9.03 | 7.84 | 5.92 | W.O No.-519 Dtd.17.08.2022 | 17.08.2022 | Project cost <10 Cr. | 16.08.2023 | 09.05.2024 | 9.03 | 9.03 | 5.92 | 6.2 | *** | 9 months | *** | ROW issue.Resolved through relevant Govt. Administration & Local bodies.
6 | 132kV Chhend-Kuarmunda LILO line | 1.72 | 0.47 | 0.19 | W.O No: 1224 (8), Dtd 17.07.2023. | 17.07.2023 | Project cost <10 Cr. | 16.11.2023 | 24.07.2024 | 1.72 | 1.72 | 0.19 | 1.321 | *** | 6 months | *** | ROW issue.Resolved through relevant Govt. Administration & Local bodies.
7 | 132kV Jayanagar-Sunabeda ckt-II | 27.82 | 22.22 | 25.08 | W.O.No:5301 & 5306 dt.04.07.2013 | 04.07.2013 | 1. 05/2016 (BP) 30.07.2016 | 03.01.2016 | 15.10.2024 | 27.82 | 27.82 | 25.08 | 31.43 | *** | 106 months | Due to GST amendment price changes after LOA. | ROW issue & hilly area.Resolved through relevant Govt. Administration & Local bodies.
PROJECTS COMPLETED DURING (April' 25 to Dec-25)
8 | 220kV Cuttack- Pratapsasan DC line | 34.93 | 34.93 | 32.63 | W.O.No:5177 dt.10.10.2018 + Work performed by multiple Rate Contract Honders | 09.04.2020 | 1. 08/2013 (IP) 04.06.2014 |  | 11.04.2025 | *** | 34.93 | 32.63 |  | *** | 60 months | *** | ROW issue.Resolved through relevant Govt. Administration & Local bodies.
9 | 132/33kV Grid S/S at Agalpur-Rampur & associated 132kV LILO Line | 35.06 | 32.99 | 28.04 | M/S Empowertrans Private Limited. WO-No-405/03.06.2023 | 06/2025 | 1. 63/2022 (IP) 29.04.2023 | 2025-12-01 | 22.08.2025 | 35.06 | 35.06 | 28.04 |  | *** | 02 months | NA
10 | 3rd 500 MVA, 400/220kV ICT at New Duburi. | 53.05 | 53.05 | 46.65 | M/S A.K.Das Associates Ltd. Work Order No. 3924 & 3929 Dtd. 22.06.2017 of Sr.G.M(CPC), OPTCL. | 06/2018 | 1. 63/2020 (BP) 03.11.2021 2. 69/2023 (IP) 07.08.2023 | 08/2025 | 29.08.2025 | 53.05 | 53.05 | 46.65 |  | *** | 86 months | NA | Initially 315MVA ICT was planned to be installed however due to burning of ICT at Meramundali GSS, the respective ICT has been diverted to Meramundali GSS. Thereafter, fresh 500MVA ICT order and upon receipt the same has been commissioned at New Duburi
11 | 2X20MVA, 132/33kV Grid S/S Lamtaput with SAS and its associated 132kV LILO line. SCOPE: 132kV Bay: 6 +2 (Unequipped) 33kV Bay: 7 + 2 (Unequipped) 132kV LILO line: 1.0 km. Estimated Cost: 30.06 Cr. Award Cost: 26.32 Cr. | 30.06 | 26.32 | 29.37 | M/s SALASAR Techno Engineering Ltd. W.O. No. 5862 dt. 28.11.2018 Rs. 26.32 Cr. | 2020-12-01 | 1. 63/2020 (BP) 03.11.2021 2. 45/2021 (IP) 27.12.2021 | 2025-11-01 | 23.11.2025 | 30.06 | 30.06 | 29.37 |  | 3.05 | 59 months | Due to increase in hard soil quantity & special type satellite with deep bore well earthing cost escalation occurred
12 | 132 kV Bhadrak – Anandpur Ckt - II (in DC Towers) |  | 8.14 | 5.3 | JEPL, 28.03.22 |  |  |  | 26.12.2025 |  | 8.14 | 5.3
0