## Summary (2)
[24 empty] | 510.9856 | 512.3592 | 0.078474 | -1.452
Details of fixed assets capitalised as on 31.03.2025.
SL No | Cost Center / Unit |  |  | Description of CWIP | [6 empty] | Total Cost Of the Work | Source of Funding |  |  |  |  | Project Period |  | Actual Fund Received till 31-03-2025 |  |  |  |  | Actual Expenditure Upto 31-03-2025 | Amount Capitalized | Transfer to Other Unit R&M | CB of CWIP as on 31-03-2025
| Code | Circle | Name | Major Category | Minor Category | Account Code | Name of Scheme | Name of Capital work | Project as whole | Location of work to Identify |  | Equity/own | Debt | Grant | Other | Total | Start | Schdule Completion/Capitalized Date | Equity/Own | Debt | Grant | other | Total
2 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 5 | 14.22.5.3 | OWN | 2 nos. of 33 kV feeder bay at 220/132/33 KV GSS Balangir new for Dunguripali & Loisingha feeder |  | SADEIPALI | 1.2546 | 1.2546 | 0 | 0 | 0 | 1.2546 | 2024-01-08 | 2024-10-24 | 0.15458 | 0 | 0 | 0 | 0.15458 | 0.15458 | 0.15458 | 0 | 0
3 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 6 | 14.22.6.4 | OWN | Diversion of 132kv Bolangir-Sonepur DC line from Loc no-34 to loc-36 near Oriental public school,Malamunda under EHT(O&M)division,Bolangir (under T&D, |  | Malamunda, Balangir | 0.53022 | 0.53022 | 0 | 0 | 0 | 0.53022 | 2020-02-12 | 2024-11-14 | 0.1515 | 0 | 0 | 0 | 0.1515 | 0.1515 | 0.1515 | 0 | 0
4 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 6 | 14.22.6.4 | OWN | Stringing of 132 KV 2nd Ckt line of Bolangir (S.Pali) Sonepur Line on DC Tower with 132 KV bay extension one non at Sonepur & one at Sadeipalli grid S |  | SADEIPALI-SONEPUR LINE | 10.6453 | 10.6453 | 0 | 0 | 0 | 10.6453 | 2014-11-14 | 2024-11-14 | 8.9714 | 0 | 0 | 0 | 8.9714 | 8.9714 | 8.9714 | 0 | 0
5 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 5 | 14.47.5.3 | Deposit | 33KV lower suktel left command at 220/132/33 KV GSS Balangir new |  | SADEIPALI | 0.85488 | 0 | 0 | 0 | 0.85488 | 0.85488 | 2023-12-08 | 2024-10-24 | 0 | 0 | 0 | 0.85488 | 0.85488 | 0.099333 | 0.099333 | 0 | 0
6 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 5 | 14.47.5.3 | Deposit | 33KV lower suktel Right command at 220/132/33 KV GSS Balangir new |  | SADEIPALI | 0.92117 | 0 | 0 | 0 | 0.92117 | 0.92117 | 2023-12-08 | 2024-10-24 | 0 | 0 | 0 | 0.92117 | 0.92117 | 0.12997 | 0.12997 | 0 | 0
7 | 156 | O&M circle Bolangir | EHT (O & M) DIVISION ,BOLANGIR | 14 | 6 | 14.47.6.4 | Deposit | Diversion work of 132 KV Balangir-Sonepur line from loc. 15 to Loc 23 due to construction of proposed NH 57 in between loc. 18 to 20 |  | Madhiapali & Puintala, Balangir | 1.3803 | 0 | 0 | 0 | 1.3803 | 1.3803 | 2024-02-09 | 2024-06-20 | 0 | 0 | 0 | 1.3803 | 1.3803 | 0.47997 | 0.47997 | 0 | 0
8 | 251 | O&M circle Bolangir | EHT (O & M) DIVISION ,KESINGA | 14 | 6 | 14.47.6.3 | Deposit | Diversion work of 220 KV Kesinga-Bolangir DC Line from existing Loc.no:-223 to Loc No.232 due to Construction of Prop. NH-59 in between Loc No.228 t |  | Belgaon | 2.7739 | 0 | 0 | 0 | 2.7739 | 2.7739 | 2024-02-09 | 2025-01-07 | 0 | 0 | 0 | 2.7503 | 2.7503 | 0.2845 | 0.2845 | 0 | 0
9 | 251 | O&M circle Bolangir | EHT (O & M) DIVISION ,KESINGA | 14 | 6 | 14.47.6.4 | Deposit | Diversion works of 132 KV (Kesinga-Saintala) Line From loc.no:-65 to 73 for Construction of Prop. N.H-59 in between loc.no.68-69 under EHT(O&M) Divi |  | Belgaon | 0.8099 | 0 | 0 | 0 | 0.8099 | 0.8099 | 2024-01-25 | 2024-07-07 | 0 | 0 | 0 | 0.76813 | 0.76813 | 0.21338 | 0.21338 | 0 | 0
13 | 285 | O&M circle Bolangir | EHT (O & M) DIVISION ,NUAPADA | 14 | 6 | 14.22.6.4 | OWN | Construction of 2nd Circuit string at 132 KV Patnagarh-Padampur line |  | Patnagarh-Padampur Line | 8.0294 | 8.0294 | 0 | 0 | 0 | 8.0294 | 2022-11-17 | 2025-03-24 | 6.2428 | 0 | 0 | 0 | 6.2428 | 6.2428 | 6.2428 | 0 | 0
15 | 152 | O & M CIRCLE ,BURLA | EHT (O & M) DIVISION ,ROURKELA | 14 | 6 | 14.22.6.3 | OTSSP- II | Engineering, Supply, Erection, Testing & Commissioning of High Temperature Low Sag (HTLS) Conductor after dismantling of ACSR Zebra Conductor in exist |  | ROURKELA | 26.2234 | 8.1034 | 18.12 | 0 | 0 | 26.2234 | 2024-01-08 | 2024-04-29 | 26.22 | 0 | 0 | 0 | 26.22 | 26.2234 | 26.2234 | 0 | 0
19 | 153 | O & M CIRCLE ,BURLA | EHT (O & M) DIVISION ,BURLA | 14 | 5 | 14.22.5.4 | OWN | INSTALLATION OF NOITROGEN INJECTION TYPE FIRE PREVENTION & EXTINGUISHING SYSTEM(NIFPES) AT GSS KATAPALI |  | KATAPALI | 0.26374 | 0.26374 | 0 | 0 | 0 | 0.26374 |  | 2024-05-07 | 0.26374 | 0 | 0 | 0 | 0.26374 | 0.26046 | 0.26046 | 0 | 0
20 | 153 | O & M CIRCLE ,BURLA | EHT (O & M) DIVISION ,BURLA | 14 | 5 | 14.46.5.3 | DEPOSIT WORK | Construction of one No of 33kv feeder bay (Bay No 11) at 220/132/33 kv GSS Katapali for tapping of P.S to proposed pump house located at Rengali, Bar |  | RENGALI | 0.63863 | 0 | 0 | 0 | 0.64 | 0.64 | 21/06/2023 | 2023-12-06 | 0 | 0 | 0 | 0.013886 | 0.013886 | 0.013886 | 0.013886 | 0 | 0
24 | 278 | O & M CIRCLE ,BURLA | EHT (O&M) DIVISION, RAJGANGPUR | 14 | 5 | 14.47.5.4 | DEPOSIT WORK | Construction of 1 no. of 33 KV Bay feeder bay at 132/33KV Gss Kalunga for availing 08 MVA power to M/s Bajrangbali Sponge Iron Power Ltd |  | NA | 0.97969 | 0 | 0 | 0 | 0.9797 | 0.9797 | 2024-01-24 | 2024-07-23 | 0 | 0 | 0 | 0.98 | 0.98 | 0.70532 | 0.70532 | 0 | 0
28 | 279 | O & M CIRCLE ,BURLA | EHT (O&M)DIVISION, JHARSUGUDA | 14 | 5 | 14.22.5.3 | OWN | 132 KV RCC CABLE TRENCH AT GSS,BUDHIPADAR |  | 220/132/33KV Grid S/S, Budhipadar | 0.024341 | 0.024341 | 0 | 0 | 0 | 0.024341 | 21.08.2023 | 21.12.2023/ 18-12-2023 | 0.024341 | 0 | 0 | 0 | 0.024341 | 0.024341 | 0.024341 | 0 | 0
29 | 279 | O & M CIRCLE ,BURLA | EHT (O&M)DIVISION, JHARSUGUDA | 14 | 5 | 14.22.5.3 | OWN | CONSTRUCTION OF 220 KV RCC CABLE TRENCH AT GSS,BUDHIPADAR |  | 220/132/33KV Grid S/S, Budhipadar | 1.6304 | 1.6304 | 0 | 0 | 0 | 1.6304 | 21.08.2023 | 21.12.2023/26-12-2024 | 1.2247 | 0 | 0 | 0 | 1.2247 | 1.2247 | 1.2247 | 0 | -1e-07
47 | 286 | O&M circle Bolangir | EHT (O & M) DIVISION ,BARPALI | 14 | 5 | 14.22.5.1 | OWN | Construction of 3rd Transformer bay & commissioninf of 20 MVA, 132/33KV power Transformer at 132/33 KV Grid Sub-Station Bapali |  | BARPALI ( BARGARH ) | 5.08 | 5.08 | 0 | 0 | 0 | 5.08 | 04.02.2022 | 2024-06-19 | 5.08 | 0 | 0 | 0 | 5.08 | 5.0822 | 5.0822 | 0 | 0
48 | 286 | O&M circle Bolangir | EHT (O & M) DIVISION ,BARPALI | 14 | 5 | 14.47.5.3 | DEPOSIT WORK | Construction of 33kv 2nd feeder bay for Gangadhar Meher Lift Irrigation Project Bijepur at 220/132/33kv GSS, Bargarh New for dedicated power supply to |  | BARPALI ( BARGARH ) | 5.765 | 0 | 0 | 0 | 5.765 | 5.765 | 11.10.2022 | 2024-07-25 | 0 | 0 | 0 | 0 | 0 | 5.7037 | 5.7037 | 0 | 0
49 | 2 | DDO HQRS, BHUBANESWAR | DDO HQRS, BHUBANESWAR | 14 | 9 | 14.77.9.2 | OWN | Computers and Peripherals | Computers and Peripherals | IT Dept., OPTCL, BHUBANESWAR | 0.10815 | 0.10815 | 0 | 0 | 0 | 0.10815 | NA | 2022-07-31 | 0.10815 | 0 | 0 | 0 | 0.10815 | 0.10815 | 0.029676 | 0.078474 | 0
58 | 134 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,CHAINPAL | 14 | 5 | 14.46.5.3 | Megalift Project Division | Construction of 33KV dedicated fdr. Bay for Mega lift Irrigation project at 220/33KV Grid s/s Rengali. |  | RENGALI | 0.068665 | 0 | 0 | 0 | 0.068665 | 0.068665 | NA | 2018-10-31 | 0 | 0 | 0 | 0.068665 | 0.068665 | 0.068665 | 0.068665 | 0 | 0
62 | 134 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,CHAINPAL | 14 | 6 | 14.47.6.3 | TTPS Expansion | Diversion of 220-KV TTPS- Kaniha- Rengali DC line from Loc no. 06 to Loc no. 12 of TTPS Expansion. |  | RENGALI | 1.2393 | 0 | 0 | 0 | 1.24 | 1.24 | 0 | On going | 0 | 0 | 0 | 1.24 | 1.24 | 1.2393 | 1.2393 | 0 | 0
67 | 134 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,CHAINPAL | 14 | 6 | 14.47.6.3 | TTPS Expansion | Survey of 220KV TTPS-Joda DC line from loc. No.4 to 9 (Loc.01 to 05)-TTPS plant Exp.-Bharat Sahoo |  | MERAMUNDALI | 0.010862 | 0 | 0 | 0 | 0.010862 | 0.010862 | 0 | On going | 0 | 0 | 0 | 0.010862 | 0.010862 | 0.010862 | 0.010862 | 0 | 0
68 | 134 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,CHAINPAL | 14 | 6 | 14.47.6.3 | TTPS Expansion | Survey work of 220kv TTPS-Meramundali DC line (Loc.01 to 05) TTPS plant Exp.-Manaranjan Enterprises |  | MERAMUNDALI | 0.018678 | 0 | 0 | 0 | 0.018678 | 0.018678 |  | On going |  |  | 0 | 0.0236 | 0.0236 | 0.018678 | 0.018678 | 0 | 0
70 | 134 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,CHAINPAL | 14 | 6 | 14.47.6.3 | TTPS Expansion | Diversion of 220KV TTPS-Joda DC line from loc. No.4 to 9 (Loc.01 to 05)-TTPS plant Exp.-Bharat Sahoo |  | CHAINPAL | 1.225 | 0 | 0 | 0 | 1.22 | 1.22 | 0 | 2024-12-30 | 0 | 0 | 0 | 1.22 | 1.22 | 1.225 | 1.225 | 0 | 0
75 | 276 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,DHENKANAL | 14 | 5 | 14.22.5.3 | OWN | 20 MVA 132/33KV Power Transformer at Grid S/S Goda |  | 220/132/33KV Grid S/s, Goda | 0.01964 | 0.01964 | 0 | 0 | 0 | 0.01964 | 07.02.2023 | 13.10.2023 | 0.01964 | 0 | 0 | 0 | 0.01964 | 0.01964 | 0.01964 | 0 | 0
77 | 276 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,DHENKANAL | 14 | 5 | 14.22.5.4 | OWN | 40 MVA 132/33KV Power Transformer at Grid S/S Gondia` |  | 132/33KV Grid S/s, Gondia | 0.16874 | 0.16874 | 0 | 0 | 0 | 0.16874 | 07.02.2025 | 28.02.2025 | 0.16874 | 0 | 0 | 0 | 0.16874 | 0.16874 | 0.16874 | 0 | 0
79 | 276 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,DHENKANAL | 14 | 5 | 14.22.5.4 | OWN | Conversion of 132KV HMIL Bay to 132KV Bay of 40MVA 132/33 KV Power Transformer-II Grid S/S Kharagprasad |  | 132/33KV Grid S/s, Kharagprasad | 3.3946 | 3.3946 | 0 | 0 | 0 | 3.3946 | 27.12.2023 | 28.02.2025 | 3.3946 | 0 | 0 | 0 | 3.3946 | 3.3946 | 3.3946 | 0 | 0
83 | 276 | O&M Circle,Chainpal | EHT (O & M) DIVISION ,DHENKANAL | 14 | 5 | 14.47.5.3 | DEPOSIT | 33KV Feeder Bay for RWSS at 132/33KV Grid S/S Kharagprasad |  | 132/33KV Grid S/s, Kharagprasad | 0.67899 | 0 | 0 | 0 | 0.67899 | 0.67899 | 13.06.2023 | 24.01.2024 | 0 | 0 | 0 | 0.2191 | 0.2191 | 0.2191 | 0.2191 | 0 | 0
87 | 163 | O&M circle jajpur | EHT (O & M) DIVISION ,BALASORE | 14 | 5 | 14.22.5.3 | OWN | Construction of one of 33 KV bay at Balasore Grid S/s for power supply to City PSS, Balasore, TPNODL. |  | BALASORE,TPNODL | 0.2379 | 0.2379 | 0 | 0 | 0 | 0.2379 |  | 2024-04-19 | 0.2379 | 0 | 0 | 0 | 0.2379 | 0.2379 | 0.2379 | 0 | 0
114 | 132 | SLDC | SLDC | 14 | 9 | 14.25.9.304 | OWN | Load Forecasting Software (System) | 2 | SLDC/Jabalpur | 0.12725 | 0.12725 | 0 | 0 | 0 | 0.12725 | 2023-07-15 | 2024-02-22 | 0.12725 | 0 | 0 | 0 | 0.12725 | 0.12725 | 0.12725 | 0 | 0
119 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.22.5.3 | 50% own / 50% deposit (SE Railway) | Construction of 220 KV LILO line for 220/132/33 KV Grid Sub-Station at Bamra. | 220/132/33 KV (AIS) Grid SS With SAS at Bamra and associated220 KV LILO Line from Loc. No. 125 & 126of existing 220KV Budhipadar to Tarkera line (CKT-II) and 132 KV Lilo Line from Loc No 291 of Existing132 KV Budhipadar to Tarkera Line(CKT-II) to BAMRA | BAMRA | 81.87 | 40.935 |  | 0 | 40.935 | 81.87 | 2018-05-16 | 2022-09-04 | 40.94 |  | - | 39.9782 | 80.9182 | 0.2579 | 0.2579 | 0 | 0
120 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.22.6.3 |  | Construction of 220 KV LILO line for 220/132/33 KV Grid Sub-Station at Bamra. | [5 empty] | 0 |  | 0 | [6 empty] | 0 | 0.014996 | 0.014996 | 0 | 0
121 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.47.5.3 |  | Construction of 220/132/33 KV Grid Sub-Station at Bamra. | [5 empty] | 0 |  | 0 | [6 empty] | 0 | 0.2579 | 0.2579 | 0 | 0
122 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.47.6.3 |  | Construction of 220 KV LILO line for 220/132/33 KV Grid Sub-Station at Bamra. | [5 empty] | 0 |  | 0 | [6 empty] | 0 | 0.014996 | 0.014996 | 0 | 0
125 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.22.5.3 | JICA | Construction of 220/33 KV AIS S/S at Deogarh in Odisha State of India under Package- 8 Under Japan International Cooperation Agency (JICA)'s ODA Loan | Constrtiction of 220/33 KV GSS Sunamunda, Deogarh and its associated 220 KV LILO Line from loc no-331 of existing 220KV Rengali-Tarkera DC Line | Deogarh | 46.8 | 9.52 | 37.28 | 0 |  | 46.8 | 2017-05-05 | 2021-08-06 | 9.52 | 37.28 | - | 0 | 46.8 | 0.010107 | 0.010107 | 0 | 0
126 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.22.6.3 |  | Construction of 220 KV DC LILO Line for 220/33 KV AIS S/S at Deogarh in Odisha State of India under Package- 8 Under Japan International Cooperation | [5 empty] | 0 |  | 0 | [6 empty] | 0 | 0.083178 | 0.083178 | 0 | 0
128 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.22.5.3 | 40% eqt/60% debt | Const of 2 x 100MVA 220/132/33 KV Grid S/S at Kuanrmunda |  | Kuanrmunda | 67.59 | 23.17 | 44.42 | 0 |  | 67.59 | 2010-10-23 | 2023-01-25 | 23.17 | 44.42 | 0 | 0 | 67.59 | 0.51867 | 0.51867 | 0 | 0
130 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.22.5.4 | JICA | Construction of 132/33 KV Grid S/S at Lakhanpur alongwith associated Transmission line from Brajrajnagar. |  | laKakhanpur | 56.93 | 21.44 | 35.49 | 0 |  | 56.93 | 2017-05-05 | 2023-04-29 | 21.44 | 35.49 | 0 | 0 | 56.93 | 5.4367 | 5.4367 | 0 | 0
137 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.47.6.4 | Deposit (NSPCL) | Diversion of 132 KV D/C Line from Loc. No. 9 to Loc No. 12 of 132KV CPP-II (NSPCL, Rourkela) to MSDS-V, SAIL, RSP line along with connecting the line |  | NSPCL, Rourkela | 4.56 | 0 | 0 | 0 | 4.56 | 4.56 | 2017-10-07 | 2019-12-10 |  |  | 0 | 6.2262 | 6.2262 | 0.090446 | 0.090446 | 0 | 0
138 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.47.6.4 | Deposit(M/S East CostRailways) | Construction of 132 KV SC Line (Two Conductor) on DC tower from existing 220/132/33KV Lapanga Grid S/S to proposed RTSS at Rengali (Approximate Line l |  | Lapanga-Rengali | 15.01 | 0 | 0 | 0 | 15.01 | 15.01 |  | 2017-08-19 |  |  | 0 | 9.2128 | 9.2128 | 0.067531 | 0.067531 | 0 | 0
139 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.51.5.5 | RRCP-II | Construction of 132KV LILO Line from 132 KV Chhend-Shri Ganesh Metaliks Circuit (Between Loc. No. 50 to 53) to 220/132/33 KV GSS, Kuanrmunda. | Construction of 132KV LILO Line from 132 KV Chhend-Shri Ganesh Metaliks Circuit (Between Loc. No. 50 to 53) to 220/132/33 KV GSS, Kuanrmunda. | Chhend | 8.61 | 2.583 | 6.027 | 0 | 0 | 8.61 | 2023-07-17 | 2024-07-24 | 2.583 | 0 | 0 | 0 | 2.583 | 1.2556 | 1.2556 | 0 | 0
140 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 6 | 14.51.6.7 |  | Construction of 132KV LILO Line from 132 KV Chhend-Shri Ganesh Metaliks Circuit (Between Loc. No. 50 to 53) to 220/132/33 KV GSS, Kuanrmunda. | [7 empty] | 0 |  |  | 2.583 |  |  |  | 2.583 | 0.066021 | 0.066021 | 0 | 0
141 | 203 | Const circle,SBP | EHT (CONST) DIVISION , JHARSUGUDA | 14 | 5 | 14.51.5.5 | RRCP-I | Construction of 132 KV D/C line from 400/220/132/33 KV Grid S/s at Lapanga to 132/33 KV GSS Brajarajnagar alongwith diversion of 220 KV DC IB-Budhipad |  | Lapanga-Remja | 27.57 |  |  | 27.57 |  | 27.57 | 2017-02-23 | 2023-06-22 |  |  | 27.57 | 0 | 27.57 | -1.8226 | -1.8226 | 0 | 0
147 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.22.5.4 | JICA | 132/33 KV Grid S/S Thuapali (Deshbhatli) & Associated Line |  | Thuapali | 39.6 | 7.85 | 31.75 | 0 | 0 | 39.6 | 2017-05-05 | 2021-07-14 | 7.85 | 31.75 | 0 | 0 | 39.6 | 0.79988 | 0.79988 | 0 | 0
148 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.22.5.4 |  | 132/33 KV Grid S/S B.M.Pur & Associated 132 KV Line From Sonepur to B.M. Pur |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0.017576 | 0.017576 | 0 | 0
154 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.22.5.4 | SIP | 132/33 KV Grid S/S Bhatli & Associated Line | 132/33 KV Grid S/S Bhatli & Associated Line | Bhatli | 51.94 | 15.66 | 36.28 | 0 | 0 | 51.94 | 2018-11-30 | 2023-07-21 | 15.66 | 36.28 | 0 | 0 | 51.94 | 43.6045 | 43.6045 | 0 | 0
155 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.22.5.7 | SIP | 132/33 KV Grid S/S Bhatli & Associated Line | [7 empty] | 0 | [6 empty] | 0 | 5.5541 | 5.5541 | 0 | 0
157 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 6 | 14.22.6.3 | 40% eqt/60% debt | 220KV DC Line From Existing GSS Sadeipali, New Bolangir to GSS Kesinga | 2x100 MVA, 220/132 KV S/S at Kesinga with 220 KV D/C line from Bolangir to Kesinga & 2no. 220 KV bay extension at Bolangir. | Kesinga | 82.72 | 33.85 | 48.87 | 0 | 0 | 82.72 | 2018-01-12 | 2022-03-09 | 33.85 | 48.87 | 0 | 0 | 82.72 | 0.2126 | 0.2126 | 0 | 0
158 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 6 | 14.22.6.3 | 40% eqt/60% debt | Construction work of 220KV LILO of Bolangir-Kesinga line for connectivity to 400/220 KV GSS Madhiapali PGCIL Bolangir | [7 empty] | 0 | [6 empty] | 0 | 0.05747 | 0.05747 | 0 | 0
159 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.47.5.4 | Deposit | 01 No 33KV feeder Bay Extention at 132/33 GSS BHATLI For GANGADHAR MEHER LIFT IRRIGATION PROJECT |  | Bhatli | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-07-21 |  |  | 0 | 1.4587 | 1.4587 | 0.55649 | 0.55649 | 0 | 0
161 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 6 | 14.47.6.5 | Deposit (BPCL) | Construction of BPCL BHATLI LINE BIO ETHANOL |  | Bhatli | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-07-21 |  |  | 0 | 10.3918 | 10.3918 | 0.93918 | 0.93918 | 0 | 0
164 | 255 | Const circle,SBP | EHT (CONST) DIVISION , BOLANGIR | 14 | 5 | 14.51.5.8 | RRCP-I | 2nd 132KV Feeder Bay at 132/33 KV Grid SS Padampur & 132 /33 KV Grid Ss Nuapada |  | Padampur-Nuapada | 28.83 |  |  | 28.83 |  | 28.83 | 2018-09-15 | 2021-08-06 |  |  | 28.83 |  | 28.83 | 1.5022 | 1.5022 | 0 | 0
167 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.22.5.4 | System Improvement Project | Transformer of 2x20 MVA 132/33 KV Grid S/s at Nawarangpur | GSS Nawarangpur & Associated Line | Nawarangpur | 39.17 | 11.81 | 27.36 | 0 | 0 | 39.17 | 2019-03-01 | 2024-04-30 | 11.81 | 27.36 | 0 | 0 | 39.17 | 3.9312 | 3.9312 | 0 | 0
168 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.22.5.4 | System Improvement Project | Construction of 2x20 MVA 132/33 KV Grid S/s at Nawarangpur with associated 132 KV DC line for LILO arrangement of existing 132 KV Jayanagar - Tentulik |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2019-03-01 | 2021-12-29 | 0 | 0 | 0 | 0 | 0 | 0.28642 | 0.28642 | 0 | 0
170 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.22.5.4 | Equity 300 | GSS Pottangi | GSS Pottangi & Associated Line | Pottangi | 39.24 | 15.35 | 23.89 | 0 | 0 | 39.24 | 2013-06-26 | 2019-09-15 | 15.35 | 23.89 | 0 | 0 | 39.24 | 0.89638 | 0.89638 | 0 | 0
171 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.22.5.4 | Equity 300 | Construction of 132/33 KV Grid S/s at Boriguma with LILO of existing 132 KV SC line from 220/132KV grid substation, Jaynagar to 132/33KV grid substati | GSS Boriguma & Associated Line | Boriguma | 32.11 | 7.59 | 24.52 | 0 | 0 | 32.11 | 2014-12-31 | 2023-04-24 | 7.59 | 24.52 | 0 | 0 | 32.11 | 28.8663 | 28.8663 | 0 | 0
172 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.7 | Equity 300 | 132/33 KV Grid S/S, BORIGUMA [Conductors - Material Cost ] |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2.0198 | 2.0198 | 0 | 0
173 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.4 | Equity 300 | Boriguma LILO line |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.3021 | 0.3021 | 0 | 0
174 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.3 | RRCP-II | Const. of 220 KV LILO line from 220/132KV grid substation, Balimela to Jaynagar LILO at Govindpali SC including bays. | Balimela-Malkangir to Govindpali Line | Govindpali | 7.84 | 2.27 | 5.57 | 0 | 0 | 7.84 | 2022-08-17 | 2024-05-08 | 2.27 | 5.57 | 0 | 0 | 7.84 | 6.1987 | 6.1987 | 0 | 0
175 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.3 | OPTCL OWN FUNDING | Stringing of 2nd circuit (three conductors) from LILO point of existing 220 KV Balimela-Malkangiri Line to Newly constructed 220/33 KV Grid S/S Kalime | Balimela-Malkangir to Kalimela Line | Kalimela | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 2022-06-03 | 2022-11-10 | 0.15 | 0 | 0 | 0 | 0.15 | 0.15364 | 0.15364 | 0 | 0
176 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.3 | JICA | Const. of 220/33 KV Grid S/s at Govindapalli with LILO of 220 KV SC line from Balimela to Malkangiri. | GSS Govindpali | Govindpali | 90.06 | 29.06 | 61 | 0 | 0 | 90.06 | 2018-01-09 | 2020-11-07 | 29.06 | 61 | 0 | 0 | 90.06 | 15.614 | 15.614 | 0 | 0
178 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.4 | Equity | 132KV Bay swapping at Jayanagar End | Jayanagar-Sunabeda Line | Jayanagar-Sunabeda Line | 27.83 | 7.73 | 20.1 | 0 | 0 | 27.83 | 2013-07-04 | 2024-10-15 | 7.73 | 20.1 | 0 | 0 | 27.83 | 0.35 | 1.76 | 0 | -1.41
179 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 6 | 14.22.6.4 |  | CONSTRUCTION OF 132 KV DC LINE ON DC TOWER FROM THE EXISTING 220/132/33 KV S/S AT JAYANAGAR TO THE EXISTING 132/33 KV S/S AT SUNABEDA |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 29.31 | 29.66 | 0 | -0.35
182 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.47.5.3 | Deposit by Avantika | Const of 2no 33kv Bay at 220KV Grid sub-station Gobindapalli Avantika Work | GSS Govindpali DW | Govindpali | 1.2634 | 0 | 0 | 0 | 1.26 | 1.26 | 2022-10-01 | 2024-03-27 | 0 | 0 | 0 | 1.26 | 1.26 | 1.0071 | 1.0071 | 0 | 0
183 | 192 | Const circle,Berhempur | EHT (CONST) DIVISION , JEYPORE | 14 | 5 | 14.47.5.3 | Deposit by EE Megalift | Construction of 1No 33kv Bay at 220/33 kv Grid s/s Gobindapalli for megalift project at saradaput | GSS Govindpali DW | Govindpali | 0.25673 | 0 | 0 | 0 | 0.26 | 0.26 | 2023-11-14 | 2024-04-28 | 0 | 0 | 0 | 0.26 | 0.26 | 0.42254 | 0.42254 | 0 | 0
197 | 222 | Const circle,Berhempur | EHT(CONST) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | System Improvement Project | Construction of 132/33 KV Grid S/s GIS at Hinjilikatu, Ganjam | GIS Hinjilikatu | Hinjilikatu | 44.76 | 13.49 | 31.27 | 0 | 0 | 44.76 | 2019-02-14 | 2022-07-29 | 13.49 | 31.27 | 0 | 0 | 44.76 | 0.53118 | 0.53118 | 0 | 0
200 | 222 | Const circle,Berhempur | EHT(CONST) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.7 |  | 2*20 mva 132/33 kv SS at R UDAYGIRI with 132 kv line from MOHANA to R UDAYGIRI [Transformer] |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024-09-24 | 0 | 0 | 0 | 0 | 0 | 3.3176 | 3.3176 | 0 | 0
208 | 222 | Const circle,Berhempur | EHT(CONST) DIVISION , BERHAMPUR | 14 | 5 | 14.51.5.5 | RRCP-I | 220 KV DC LILO line from 220 KV Narendrapur-Therubali DC line to 220/132/33 KV Grid S/s.Aska | Narendrapur-Therubali to Aska | Narendrapur-Therubali to Aska | 49.75 | 0 | 0 | 49.75 | 0 | 49.75 | 2018-12-04 | 2024-03-11 | 0 | 0 | 49.75 | 0 | 49.75 | 3.794 | 3.794 | 0 | 0
212 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 5 | 14.22.5.3 | JICA | Construction of 220/132/33 KV Grid S/s at Gunupur with 220 KV LILO arrangement from existing 220 KV Theruvalli- Narendrapur Ckt-I and 132 KV Lilo arra | GSS Gunupur | Gunupur | 95.45 | 28.25 | 67.2 | 0 | 0 | 95.45 | 2019-03-08 | 2022-03-30 | 28.25 | 67.2 | 0 | 0 | 95.45 | 0.89443 | 0.89443 | 0 | 0
213 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 5 | 14.22.5.4 | Equity | Construction of 132/33 KV Grid S/S At Brundabahal & its associated 132 KV LILO Transmission Line | GSS Brundabahal | Brundabahal | 58.12 | 58.12 | 0 | 0 | 0 | 58.12 | 2021-02-26 |  | 58.12 | 0 | 0 | 0 | 58.12 | 18.2014 | 18.2014 | 0 | 0
215 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 6 | 14.22.6.4 |  | Construction of 132/33 KV Grid S/S At Brundabahal & its associated 132 KV LILO Transmission Line |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10.7383 | 10.7383 | 0 | 0
216 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 6 | 14.22.6.4 | OPTCL OWN FUNDING | Construction of 132KV SC line on DC tower from existing loc no-170 of Akhusingh-Paralakhemundi line to proposed Loc No-41 of RTSS Palasingh line, in r | Akhusingh-Paralakhemundi line to RTSS Palasingh | Akhusingh-Paralakhemundi line to RTSS Palasingh | 3.3366 | 3.3366 | 0 | 0 | 0 | 3.3366 | 2022-12-17 | 2025-02-28 | 3.3366 | 0 | 0 | 0 | 3.3366 | 3.9336 | 3.9336 | 0 | 0
217 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 5 | 14.47.5.3 | DEPOSITS by Eco Rly | 220 KV Traction line from 220 /33 Kv Grid S/S Laxmipur to 220 / 25 KV RTSS Laxmipur | RTSS Laxmipur | Laxmipur | 11.734 | 0 | 0 | 0 | 11.734 | 11.734 | 2020-09-18 | 2021-10-31 | 0 | 0 | 0 | 11.734 | 11.734 | 0.28591 | 0.28591 | 0 | 0
219 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 6 | 14.47.6.4 | DEPOSITS by Eco Rly | 132KV 2Phase line from 132/33 KV Grid S/S Bhawanipatna to RTSS,Bhawanipatna | RTSS Bhawanipatna | Bhawanipatna | 3.2981 | 0 | 0 | 0 | 3.2981 | 3.2981 | 2020-09-16 | 2023-06-22 | 0 | 0 | 0 | 3.2981 | 3.2981 | 0.20323 | 0.20323 | 0 | 0
220 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 6 | 14.47.6.4 | DEPOSITS by Eco Rly | onstruction of 132 KV SC line on DC Tower (Two Conductor) from U/C 220/132/33 KV Grid Sub-station, Gunupur to proposed RTSS, Palasingi and 132 KV feed | RTSS Palasing | Palasingh | 11.2245 | 0 | 0 | 0 | 11.2245 | 11.2245 | 2020-09-18 | 2023-06-05 | 0 | 0 | 0 | 11.2245 | 11.2245 | 0.28606 | 0.28606 | 0 | 0
221 | 227 | Const circle,Berhempur | EHT (CONST) DIVISION , RAYAGADA | 14 | 6 | 14.47.6.4 | DEPOSITS by Eco Rly | Construction of 132 KV SC ( 2 phase) Traction line from existing 132 /33 KV Grid Bhawanipatna to proposed RTSS Lanjigarh along with one no 132 KV feed | RTSS Lanjigarh | Lanjigard | 16.7842 | 0 | 0 | 0 | 16.7842 | 16.7842 | 2020-05-27 | 2020-08-31 | 0 | 0 | 0 | 16.7842 | 16.7842 | 0.55617 | 0.55617 | 0 | 0
227 | 183 | Const circle,BBSR | EHT (CONST) DIVISION , BBSR | 14 | 5 | 14.55.5.6 | SCRIPS | 220/33KV GIS S/S at Kantabada |  | Kantabada | 68.922 | 0 | 0 | 68.922 | 0 | 68.922 | 2019-02-22 | 2023-10-10 | 0 | 0 | 68.922 | 0 | 68.922 | 2.49 | 2.49 | 0 | 0
228 | 183 | Const circle,BBSR | EHT (CONST) DIVISION , BBSR | 14 | 5 | 14.55.5.6 | SCRIPS | Const. of 220/33KV GIS substation at Nayapalli |  | Nayapali | 120.4892 | 0 | 0 | 120.4892 | 0 | 120.4892 | 2019-03-07 | 2025-02-14 | 0 | 0 | 120.4892 | 0 | 120.4892 | 92.5503 | 92.5503 | 0 | 0
233 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 2.104 | 14.75.2.104 | OWN | Construction of Extension to Control Room Building for providing Carrier Room of Telecom Sub-Division and E&MR Sub-Division Office with Store in 132/33 KV Grid Sub-Station Campus at Rajgangpur | 1 | 132/33 KV Grid Sub-Station Campus at Rajgangpur In Sundargarh District | 0.59049 | 0.59 |  | 0 |  | 0.59 | 2024-03-18 | 2024-07-17 | 0.59 |  |  |  | 0.59 | 0.60561 | 0.60561 | 0 | 0
234 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 2.104 | 14.75.2.104 | OWN | Renovation Works to 400/132/33 KV Grid S/S Control room of OPTCL at Lapanga.( provision for Grading concrete to Roof) | 1 | 400/132/33 KV Grid Sub-Station Control room of OPTCL at Lapanga in Sambalpur District | 0.1739 | 0.17 | 0 | 0 | 0 | 0.17 | 2023-11-20 | 2024-02-19 | 0.17 | 0 | 0 | 0 | 0.17 | 0.17776 | 0.17776 | 0 | 0
236 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 2.104 | 14.75.2.104 | OWN | Renovation of 220/132/33 KV Grid Sub-Station Control room Building of OPTCL at Joda. | 1 | 220/132/33 KV Grid Sub-Station Control room Building of OPTCL at Joda in Keonjhar District | 0.315 | 0.31 | 0 | 0 | 0 | 0.31 | 2024-03-07 | 2024-07-07 | 0.31 | 0 | 0 | 0 | 0.31 | 0.32297 | 0.32297 | 0 | 0
237 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 2.204 | 14.75.2.204 | OWN | Renovation to E&MR Division & Sub-Divisionors office Building of OPTCL at Burla in the District of Sambalpur. (Provision for inside & outside Repairing & Painting, vitrified & PeriPheral development) | 1 | Burla in Sambalpur District | 0.29 | 0.29 | 0 | 0 | 0 | 0.29 | 2023-11-24 | 2024-02-23 | 0.29 | 0 | 0 | 0 | 0.29 | 0.28534 | 0.28534 | 0 | 0
242 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.104 | 14.75.4.104 | OWN | Provision for paving the Bern's of the approach road in 220/132 KV Bolangir (New) GSS of OPTCL at sadeipali-Bolangir (by using cement concrete paver blocks) | 1 | 220/132 KV Bolangir (New) Grid Sub-Station of OPTCL at sadeipali-Bolangir in Bolangir District | 0.18 | 0.17881 | 0 | 0 | 0 | 0.17881 | 2023-11-10 | 2024-02-09 | 0.17881 | 0 | 0 | 0 | 0.17881 | 0.17881 | 0.17881 | 0 | 0
243 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.134 | 14.75.4.134 | OWN | Improvement to Boundary wall around 132/33 KV Grid Sub-Station campus of OPTCL at Rairakhole.(Provision for repairing and heightening of Boundary wall) | 1 | 132/33 KV Grid Sub-Station campus of OPTCL at Rairakhole in Sambalpur District | 0.67 | 0.67379 | 0 | 0 | 0 | 0.67379 | 2024-02-02 | 2024-06-01 | 0.67379 | 0 | 0 | 0 | 0.67379 | 0.67379 | 0.67379 | 0 | 0
246 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.134 | 14.75.4.134 | OWN | Improvement to Boundary wall around 132/33 KV Grid Sub-Station at Uditnagar, Rourkela (Provision for Heightening, Repairing & Painting of Boundary wall) | 1 | 132/33 KV Grid Sub-Station at Uditnagar, Rourkela in Sundargarh District | 0.41895 | 0.42 | 0 | 0 | 0 | 0.42 | 2023-06-06 | 2023-09-05 | 0.39 | 0 | 0 | 0 | 0.39 | 0.3886 | 0.3886 | 0 | 0
247 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.134 | 14.75.4.134 | OWN | Re-Construction of Boundry wall around 220/132/33 KV Grid Sub-Station Campus of OPTCL at Kesinga. | 1 | 220/132/33 KV Grid Sub-Station of OPTCL at Kesinga in Kalahandi District | 0.86 | 0.85562 | 0 | 0 | 0 | 0.85562 | 2023-11-22 | 2024-04-21 | 0.85562 | 0 | 0 | 0 | 0.85562 | 0.85562 | 0.85562 | 0 | 0
248 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.134 | 14.75.4.134 | OWN | Improvement to boundary wall arround 220/32 KV Grid Sub-Station Campus of OPTCL at Tarkera-Rourkela. | 1 | 220/132 KV Grid Sub-Station of OPTCL at Tarkera-Rourkela in Sundargarh District. | 0.6 | 0.60493 | 0 | 0 | 0 | 0.60493 | 2023-12-11 | 2024-04-10 | 0.60493 | 0 | 0 | 0 | 0.60493 | 0.60493 | 0.60493 | 0 | 0
249 | 213 | Civil Circle, Bhubaneswar | CWD-II,BURLA | 14 | 4.134 | 14.75.4.134 | OWN | Improvement to Boundary wall arround 132/33 KV Grid Sub-Station of OPTCL at Kalunga.(Provision for Boundary wall at the West side of the Control Room) | 1 | 132/33 KV Grid Sub-Station of OPTCL at Kalunga in Sundargarh District | 0.7 | 0.70462 | 0 | 0 | 0 | 0.70462 | 2024-01-05 | 2024-05-04 | 0.70462 | 0 | 0 | 0 | 0.70462 | 0.70462 | 0.70462 | 0 | 0
257 | 184 | Const circle,jajpur | EHT (CONST) DIVISION , BALASORE | 14 | 5 | 14.22.5.3 | Govt Funding | Constn. of 2X160 MVA & 2X40MVA, 220/132/33 KV Grid S/S with SAS at Balimunda(Dhamara) and Associate 220 KV LILO Line from Loc. No. 277 of exisiting 22 |  | Dhamra | 81.52 | 24.58 | 56.94 | 0 | 0 | 81.52 | 29.06.2018 | 24.04.2023 | 24.58 | 56.94 |  | 0 | 81.52 | 0.11946 | 0.11946 | 0 | 0
258 | 184 | Const circle,jajpur | EHT (CONST) DIVISION , BALASORE | 14 | 5 | 14.22.5.4 | JICA | Constn. of 2 x 20 MVA, 132/33KV S/S, CHANDIPUR with 132 KV LILO Line. Jica Funded |  | Chandipur | 44.88 | 13.464 | 31.416 | 0 | 0 | 44.88 | 18.02.2019 | 31.08.2022 | 13.464 | 31.416 | 0 | 0 | 44.88 | 1.4036 | 1.4036 | 0 | 0
262 | 184 | Const circle,jajpur | EHT (CONST) DIVISION , BALASORE | 14 | 6 | 14.22.6.4 | OWN | Constn. Of one No 132/33 KV Bay at Kuchei End (PGCIL) |  | Kuchei | 4.44 | 4.44 | 0 | 0 | 0 | 4.44 | 26.06.2023 | 01.08.2024 | 4.44 | 0 | 0 | 0 | 4.44 | 4.8 | 4.8 | 0 | 0
267 | 184 | Const circle,jajpur | EHT (CONST) DIVISION , BALASORE | 14 | 5 | 14.53.5.6 | DRPS-1 | Const. Of 132KV DC Line from propose 220/132/33 kv G/S ,Dhamara at Balimunda to 132/33 kv GIS Chandbali.DRPS Scheme (Gupta Power) |  | Balimunda-Chandbali | 15.53 | 0 | 0 | 15.53 | 0 | 15.53 | 30.06.2019 | 13.02.2024 | 0 | 0 | 15.53 | 0 | 15.53 | 0.76246 | 0.76246 | 0 | 0
280 | 256 | Const circle,BBSR | EHT(CONST) DIVISION, CUTTACK | 14 | 5 | 14.22.5.3 | SIP(30% Equity) | Construction of 220/33KV grid sub-station at Balichandrapur (Palei) with associated lines. |  | Balichandrapur | 47.28 | 14.25 | 33.03 | 0 |  | 47.28 | 27.02.2019 | 2024-05-22 | 16.76 | 33.03 | 0 | 0 | 49.79 | 49.7948 | 49.7948 | 0 | 0
289 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | IMPROVEMENT TO 132/33 KV Control Room building at KHURDA. (Providing grading concrete, UPVC doors and windows, Al. false ceiling, ladies retiring room, AE(M) office room and inside, outside repairing and painting) | 1 | 132/33 KV Control Room building at KHURDA | 0.35781 | 0.36674 | 0 | 0 | 0 | 0.36674 | 08.02.2024 | 07.06.24 | 0.36674 |  | 0 | 0 | 0.36674 | 0.36674 | 0.36674 | 0 | 0
290 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | IMPROVEMENT TO 132/33 KV GRID SUB - STATION AT CHANDAKA (Providing grading concrete, control room false ceilling with led light, inside and outside repairing and painting) | 1 | 132/33 KV GRID SUB - STATION AT CHANDAKA | 0.32883 | 0.33609 | 0 | 0 | 0 | 0.33609 | 07.02.24 | 06.06.24 | 0.33609 |  | 0 | 0 | 0.33609 | 0.33609 | 0.33609 | 0 | 0
291 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Renovation of control room building and Re-construction of broken boundary wall inside 132/33 kv Grid S/s at Jajpur Road and construction of ladies and gents rest room cum toilet inside 132/33 kv grid s/s at Jajpur Road. | 1 | 132/33 kv Grid S/s at Jajpur Road | 0.38653 | 0.39734 | 0 | 0 | 0 | 0.39734 | 16.10.23 | 15.02.24 | 0.39734 |  | 0 | 0 | 0.39734 | 0.39734 | 0.39734 | 0 | 0
292 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Renovation of control room building inside 220/132 KV grid s/s OPTCL theruvalli vitrified tile flooring renovation of toilets partition walling, false ceiling repairing and painting etc | 1 | 220/132 KV grid s/s OPTCL theruvalli | 0.41618 | 0.42598 | 0 | 0 | 0 | 0.42598 | 16.10.23 | 15.03.24 | 0.42598 |  | 0 | 0 | 0.42598 | 0.42598 | 0.42598 | 0 | 0
293 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Imrovement to 220/33 kV Grid sub staion at samaghara (providing outside repairing and painting) | 1 | 220/33 kV Grid sub staion at samaghara | 0.21388 | 0.22001 | 0 | 0 | 0 | 0.22001 | 14.03.24 | 13.06.24 | 0.22001 |  | 0 | 0 | 0.22001 | 0.22001 | 0.22001 | 0 | 0
294 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Renovatin of control room building at 220/132/33 KV grid s/s at paradeep (Providing grading concrete with parapet repair, inside and outside repairing and painting) | 1 | 220/132/33 KV grid s/s at paradeep | 0.20151 | 0.20613 | 0 | 0 | 0 | 0.20613 | 01.02.24 | 30.04.24 | 0.20613 |  | 0 | 0 | 0.20613 | 0.20613 | 0.20613 | 0 | 0
295 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Renovation of 132/33 KV grid s/s at Karanjia (provision of crack repairing, plastering , painting , tile flooring, False ceilling & Light, toilets renovatino etc) | 1 | 132/33 KV grid s/s at Karanjia | 0.26006 | 0.26755 | 0 | 0 | 0 | 0.26755 | 18.11.23 | 17.02.24 | 0.26755 |  | 0 | 0 | 0.26755 | 0.26755 | 0.26755 | 0 | 0
297 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2104 | 14-75-2104 | OWN | Extension of Existing battery room at 132/33 KV Grid s/s chandpur | 1 | 132/33 KV Grid s/s chandpur | 0.10736 | 0.11087 | 0 | 0 | 0 | 0.11087 | 08.07.2024 | 07.10.24 | 0.11087 |  | 0 | 0 | 0.11087 | 0.11087 | 0.11087 | 0 | 0
308 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2204 | 14-75-2204 | OWN | Improvement to T W Building OPTCL BBSR (Providing grading concrete, outside repairing & painting) | 1 | Bhubaneswar | 0.27 | 0.27094 | 0 | 0 | 0 | 0.27094 | 18.03.24 | 17.06.24 | 0.27094 |  | 0 | 0 | 0.27094 | 0.27094 | 0.27094 | 0 | 0
309 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2204 | 14-75-2204 | OWN | Improvement to SLDC Building Mancheswar (Providing outside repairing , painting, paver block) | 1 | Bhubaneswar | 0.23542 | 0.2413 | 0 | 0 | 0 | 0.2413 | 21.02.24 | 20.05.24 | 0.2413 |  | 0 | 0 | 0.2413 | 0.2413 | 0.2413 | 0 | 0
310 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2204 | 14-75-2204 | OWN | Supply of RMU alongwith active supervision of M/S Siemens Representative at the time of erection and commissioning at Tech Tower Building, OPTCL | 1 | Bhubaneswar | 0.11 | 0.10863 | 0 | 0 | 0 | 0.10863 |  |  | 0.10863 |  | 0 | 0 | 0.10863 | 0.10863 | 0.10863 | 0 | 0
311 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2204 | 14-75-2204 | OWN | Construction of staircase Attached to New zone office building inside 220/132 KV Grid Presmises at Remuna Golei | 1 | 220/132 KV Grid Presmises at Remuna Golei | 0.10189 | 0.10489 | 0 | 0 | 0 | 0.10489 | 19.03.24 | 18.05.24 | 0.10489 |  | 0 | 0 | 0.10489 | 0.10489 | 0.10489 | 0 | 0
312 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2204 | 14-75-2204 | OWN | Peripherial development of power community center at OPTCL colony, Bhoinagar, Bhubaneswar (Providing VDF flooring to approach road, parking space and kitchen) | 1 | Bhubaneswar | 0.43 | 0.43281 | 0 | 0 | 0 | 0.43281 | 12.12.24 | 11.04.25 | 0.43281 |  | 0 | 0 | 0.43281 | 0.43281 | 0.43281 | 0 | 0
314 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2304 | 14-75-2304 | OWN | Furnishing and finishing items for water supply and sanitary washing and painting works to D-TYPE-2 NOS ,E type 2 nos. & Ftype-4 nos constructed earlier in core house shape in 132/33 kv Grid s/s at Jajpur Town. | 1 | 132/33 kv Grid s/s at Jajpur Town. | 0.12 | 0.12153 | 0 | 0 | 0 | 0.12153 |  |  | 0.12153 |  | 0 | 0 | 0.12153 | 0.12153 | 0.12153 | 0 | 0
319 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2404 | 14-75-2404 | OWN | Construction of store godown inside 132/33 KV Grid s/s Rayagada | 1 | 132/33 KV Grid s/s Rayagada | 0.28016 | 0.28 | 0 | 0 | 0 | 0.28 | 29.4.23 | 28.8.23 | 0.10317 |  | 0 | 0 | 0.10317 | 0.10317 | 0.10317 | 0 | 0
320 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2404 | 14-75-2404 | OWN | Construction of open stock yard at 400/220/132 KV Grid s/s, Mendhasal | 1 | 400/220/132 KV Grid s/s, Mendhasal | 0.27251 | 0.27 | 0 | 0 | 0 | 0.27 | 08.07.2024 | 07.10.24 | 0.054221 |  | 0 | 0 | 0.054221 | 0.054221 | 0.054221 | 0 | 0
321 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2404 | 14-75-2404 | OWN | Construction of RCC roof closed store building at 132/33 KV Grid S/s at Chandaka | 1 | 132/33 KV Grid S/s at Chandaka | 0.32632 | 0.33 | 0 | 0 | 0 | 0.33 | 18.03.24 | 17.07.24 | 0.3352 |  | 0 | 0 | 0.3352 | 0.3352 | 0.3352 | 0 | 0
322 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 2404 | 14-75-2404 | OWN | Improvement to 132/33 KV Grid s/s at Kesura (providing parking shed) | 1 | 132/33 KV Grid s/s at Kesura | 0.10416 | 0.1 | 0 | 0 | 0 | 0.1 | 02.01.25 | 01.03.25 | 0.10767 |  | 0 | 0 | 0.10767 | 0.10767 | 0.10767 | 0 | 0
324 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Improvement to road and parking area at F.W & T.W Building OPTCL, Bhubaneswar | 1 | F.W & T.W Building OPTCL, Bhubaneswar | 0.1554 | 0.16 | 0 | 0 | 0 | 0.16 | 18.03.24 | 17.6.24 | 0.1589 |  | 0 | 0 | 0.1589 | 0.1589 | 0.1589 | 0 | 0
327 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Construction of peripheral road around switchyard of 400/33 KV Grid s/s at mendhasala | 1 | 400/33 KV Grid s/s at mendhasala | 0.37002 | 0.37 | 0 | 0 | 0 | 0.37 | 08.07.2024 | 07.11.24 | 0.10029 |  | 0 | 0 | 0.10029 | 0.10029 | 0.10029 | 0 | 0
328 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Construction of peripheral road around 132/33 KV Grid s/s at Puri (Balance portion) | 1 | 132/33 KV Grid s/s at Puri | 0.26469 | 0.26 | 0 | 0 | 0 | 0.26 | 08.07.2024 | 07.10.24 | 0.047538 |  | 0 | 0 | 0.047538 | 0.047538 | 0.047538 | 0 | 0
329 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Construction of Periphery road to 132/33 kv Grid S/s switchyard Jajpur road (Balance portion southside) | 1 | 132/33 kv Grid S/s switchyard Jajpur road | 0.18165 | 0.18 | 0 | 0 | 0 | 0.18 | 15.03.24 | 14.06.24 | 0.18699 |  | 0 | 0 | 0.18699 | 0.18699 | 0.18699 | 0 | 0
331 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Construction of CC road from NH to 220/132 KV grid s/s and OPTCL Colony at 220/132 KV grid s/s at Bhadrak | 1 | 220/132 KV grid s/s at Bhadrak | 0.64792 | 0.65 | 0 | 0 | 0 | 0.65 | 9.6.23 | 8.10.23 | 0.086016 |  | 0 | 0 | 0.086016 | 0.086016 | 0.086016 | 0 | 0
332 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Improvement to approach road infront of telecom and E&mr s/d, Puri (Provision for concrete pavement) | 1 | E&mr s/d, Puri | 0.10345 | 0.1 | 0 | 0 | 0 | 0.1 | 07.01.25 | 06.03.25 | 0.10676 |  | 0 | 0 | 0.10676 | 0.10676 | 0.10676 | 0 | 0
333 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Improvement to front approach of control room from 132/33 KV grid s/s of OPTCL at Khurda | 1 | 132/33 KV grid s/s of OPTCL at Khurda | 0.10389 | 0.1 | 0 | 0 | 0 | 0.1 | 07.01.25 | 06.03.25 | 0.10764 |  | 0 | 0 | 0.10764 | 0.10764 | 0.10764 | 0 | 0
335 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Improvement to connecting approach to control room building in 132/33 KV Grid s/s campus at chandpur (provision for concrete pavement approach from main entrance gate to porch of control room) | 1 | 132/33 KV Grid s/s campus at chandpur | 0.10389 | 0.1 | 0 | 0 | 0 | 0.1 | 07.01.25 | 06.03.25 | 0.10723 |  | 0 | 0 | 0.10723 | 0.10723 | 0.10723 | 0 | 0
336 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4104 | 14-75-4104 | OWN | Improvement of approach road inside switchyard at 132/33 KV Grid S/S at chandikhol (providing cement concrete approach road) | 1 | at 132/33 KV Grid S/S at chandikhol | 0.3383 | 0.34 | 0 | 0 | 0 | 0.34 | 12.12.24 | 11.03.25 | 0.14259 |  | 0 | 0 | 0.14259 | 0.14259 | 0.14259 | 0 | 0
339 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Construction of vehicle parking shed at 220 KV GIS s/s at infocity-II | 1 | 220 KV GIS s/s at infocity-II | 0.10397 | 0.1076 | 0 | 0 | 0 | 0.1076 | 13.01.25 | 12.03.25 | 0.1076 |  | 0 | 0 | 0.1076 | 0.1076 | 0.1076 | 0 | 0
340 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Construction of two wheeler parking shed at 132/33 KV Grid s/s at Arugul | 1 | at 132/33 KV Grid s/s at Arugul | 0.10388 | 0.10745 | 0 | 0 | 0 | 0.10745 | 07.01.25 | 06.03.25 | 0.10745 |  | 0 | 0 | 0.10745 | 0.10745 | 0.10745 | 0 | 0
341 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Improvement to 132/33 KV GSS OPTCL Akhushinghi (Renovation of store room and parking shed) | 1 | 132/33 KV GSS OPTCL Akhushinghi | 0.10369 | 0.10729 | 0 | 0 | 0 | 0.10729 | 13.01.25 | 12.03.25 | 0.10729 |  | 0 | 0 | 0.10729 | 0.10729 | 0.10729 | 0 | 0
342 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Improvement to 220/132 KV GSS at Therubali (Providing open stockyard) | 1 | 220/132 KV GSS at Therubali | 0.10325 | 0.10669 | 0 | 0 | 0 | 0.10669 | 13.01.25 | 12.03.25 | 0.10669 |  | 0 | 0 | 0.10669 | 0.10669 | 0.10669 | 0 | 0
343 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Improvement to 132/33 KV Grid s/s at Konark (providing parking shed) | 1 | 132/33 KV Grid s/s at Konark | 0.10019 | 0.10291 | 0 | 0 | 0 | 0.10291 | 07.01.25 | 06.03.25 | 0.10291 |  | 0 | 0 | 0.10291 | 0.10291 | 0.10291 | 0 | 0
344 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4124 | 14-75-4124 | OWN | Renovation of storm water drain in switchyard face at the proximity of back side gate inside 220/33 KV GSS at Samangara | 1 | 220/33 KV GSS at Samangara | 0.10391 | 0.10701 | 0 | 0 | 0 | 0.10701 | 07.01.25 | 06.03.25 | 0.10701 |  | 0 | 0 | 0.10701 | 0.10701 | 0.10701 | 0 | 0
353 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Reconstruction of damaged compound wall around 220/132 KV S/S of OPTCL at remuna Golei, Balasore (Balance Portion) (Release of EoT) | 1 | 220/132 KV S/S of OPTCL at remuna Golei, Balasore | 0.41824 | 0.42 | 0 | 0 | 0 | 0.42 | 25.5.23 | 24.8.23 | 0.042736 |  | 0 | 0 | 0.042736 | 0.042736 | 0.042736 | 0 | 0
355 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Re construction of broken compound wall around EHT, Construcition Store at Jajpiur Road(Provision at west and north side of the store yard | 1 | Construcition Store at Jajpiur Road | 0.29802 | 0.3 | 0 | 0 | 0 | 0.3 | 09.10.23 | 08.01.24 | 0.086355 |  | 0 | 0 | 0.086355 | 0.086355 | 0.086355 | 0 | 0
356 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Construction of damaged compound wall and raising of compound wall with concenrtina coil cuttack chandbali road side at 132/33 kV grid S/s at kendrapara | 1 | 132/33 kV grid S/s at kendrapara | 0.40808 | 0.41 | 0 | 0 | 0 | 0.41 | 28.11.23 | 27.03.2024 | 0.22297 |  | 0 | 0 | 0.22297 | 0.22297 | 0.22297 | 0 | 0
358 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Construction of compound wall around Multi-storied office building at Tulasipur, Cuttack | 1 | at Tulasipur, Cuttack | 0.27739 | 0.28412 | 0 | 0 | 0 | 0.28412 | 18.03.24 | 17.06.24 | 0.28412 |  | 0 | 0 | 0.28412 | 0.28412 | 0.28412 | 0 | 0
359 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Construction of safty fencing zone wall with steel grill for 132/33 KV OPTCL switchyard, Chainpal | 1 | 132/33 KV OPTCL switchyard, Chainpal | 0.11 | 0.10516 | 0 | 0 | 0 | 0.10516 | 15.03.24 | 14.05.24 | 0.10516 |  | 0 | 0 | 0.10516 | 0.10516 | 0.10516 | 0 | 0
360 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | CONSTRUCTION OF COMPOUND WALL ARROUND 132/33 KV GRID SUB - STATION AT MANCHESWAR. | 1 | 132/33 KV GRID SUB - STATION AT MANCHESWAR. | 0.76867 | 0.77 | 0 | 0 | 0 | 0.77 | 06.01.24 | 05.06.24 | 0.077521 |  | 0 | 0 | 0.077521 | 0.077521 | 0.077521 | 0 | 0
361 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | CONSTRUCTION OF COMPOUND WALL ARROUND 132/33 KV GRID SUB - STATION AT KHURDA. | 1 | 132/33 KV GRID SUB - STATION AT KHURDA. | 0.58 | 0.57539 | 0 | 0 | 0 | 0.57539 | 22.03.24 | 21.07.24 | 0.57539 |  | 0 | 0 | 0.57539 | 0.57539 | 0.57539 | 0 | 0
364 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | M/R to Qtr No C-1 (Duplex) inside OPTCL at Bhoinagar Bhubaneswar (providing polymer based watef proofing treatment,UPVC window, vitrified tile flooring, WPC coowkath, repairing and painting) | 1 | Bhubaneswar | 0.10376 | 0.1 | 0 | 0 | 0 | 0.1 | 14.10.24 | 13.12.24 | 0.10753 |  | 0 | 0 | 0.10753 | 0.10753 | 0.10753 | 0 | 0
365 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Const. of Compound Wall around the OPTCL colony at Choudwar | 1 | OPTCL colony at Choudwar | 0.4215 | 0.42 | 0 | 0 | 0 | 0.42 | 06.09.24 | 05.01.25 | 0.2157 |  | 0 | 0 | 0.2157 | 0.2157 | 0.2157 | 0 | 0
366 | 212 | Civil Circle, Bhubaneswar | CWD-I,BHUBANESWAR | 14 | 4134 | 14-75-4134 | OWN | Const. of Compound Wall at west, south & east of 220/33 KV GSS at Nayagarh | 1 | 220/33 KV GSS at Nayagarh | 1.1272 | 1.13 | 0 | 0 | 0 | 1.13 | 18.03.24 | 17.09.24 | 0.87143 |  | 0 | 0 | 0.87143 | 0.87143 | 0.87143 | 0 | 0
372 | 176 | Telecom circle meramunduli | TELECOM DIVISION , MERAMUNDALI | 14 | 5 | 14.47.5.8 | Deposit Work | MCL Nandira deposit work |  | MCL Berhampur | 1.0163 |  | 0 | 0 | 1.0163 | 1.0163 |  | 45608 | 0 | 0 | 0 | 1.0163 | 1.0163 | 1.0163 | 1.0163 | 0 | 0
373 | 232 | Telecom circle meramunduli | TELECOM DIVISION, SAMBALPUR | 14 | 5 | 14.47.5.8 | Deposit Work | NTPC Dulanga Coal mine works Nil |  | Dulanga Coal mines of NTPC to SLDC BBSR | 0.11506 |  | 0 | 0 | 0.11506 | 0.11506 | 16.02.2024 | 45373 | 0 | 0 | 0 | 0.11506 | 0.11506 | 0.11506 | 0.11506 | 0 | 0
374 | 236 | Telecom circle meramunduli | TELECOM DIVISION, BOLANGIR | 14 | 6 | 14.22.6.3 | OWN | 220 kv Bolangfir -Kesinga line |  | NA | 0.048265 | 0.048265 | 0 | 0 | 0 | 0.048265 |  | 44625 | 0.048265 | 0 | 0 | 0 | 0.048265 | 0.048265 | 0.048265 | 0 | 0
378 | 233 | Telecom circle meramunduli | TELECOM DIVISION, JAJPUR | 14 | 5 | 14.22.5.8 | Deposit Work | Data integration of NINL with SLDC |  |  | 1.2381 | 0 | 0 | 0 | 1.2381 | 1.2381 |  | 22. Jun.24 | 0 | 0 | 0 | 1.2381 | 1.2381 | 1.2381 | 1.2381 | 0 | 0
410 | 268 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,CHHATRAPUR (NEW) | 14 | 5 | 14.22.5.4 | OWN | Construction of wire mess fencing around 132Kv and 33kv Switchyard of GSS, Ganjam | Construction of wire mess fencing around 132Kv and 33kv Switchyard of GSS, Ganjam | 132/33KVGrid S/s Ganjam | 0.064457 | 0.064457 | 0 | 0 | 0 | 0.064457 | 2024-04-05 | 2024-04-19 | 0.064457 | 0 | 0 | 0 | 0.064457 | 0.064457 | 0.064457 | 0 | 0
412 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.3 | PSDF | "PCC Work in 220 KV & 132 KV Switchyards and water Supply points earth pits in 33 KV , 132 KV and 220 KV Switchyards at 220/132/33 KV GSS Narendrapur. | PCC work in 220 KV and 132 KV S/Y and Hydrant systems for supply of water to earth pits in 33 KV, 132 KV and 220 KV S/Y at Grid S/S Narendrapur. | Narendrapur GSS | 1.7088 | 0 | 0 | 0 | 1.7088 | 1.7088 | 2024-02-26 | 2025-01-19 | 0 | 0 | 0 | 1.7088 | 1.7088 | 1.7088 | 1.7088 | 0 | 0
414 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | OWN | PCC,Rementaling with water points for earth pits of 132 KV and 33 KV Switchyard at 132/33 KV GSS Mohana Under EHT(O&M) Division OPTCL Berhampur. | PCC,Rementaling with water points for earth pits of 132 KV and 33 KV Switchyard at 132/33 KV GSS Mohana Under EHT(O&M) Division OPTCL Berhampur. | Mohana GSS | 0.24636 | 0.24636 | 0 | 0 | 0 | 0.24636 | 2024-06-13 | 2024-11-14 | 0.24636 | 0 | 0 | 0 | 0.24636 | 0.24636 | 0.24636 | 0 | 0
415 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | OWN | PCC Rementaling with water points for earth pits of 132 & 33 KV Switchyard at 132/33 KV Grid S/S Digapahandi under EHT(O&M) Division OPTCL Berhampur. | PCC Rementaling with water points for earth pits of 132 & 33 KV Switchyard at 132/33 KV Grid S/S Digapahandi under EHT(O&M) Division OPTCL Berhampur. | Digapahandi GSS | 0.42744 | 0.42744 | 0 | 0 | 0 | 0.42744 | 2024-02-28 | 2024-07-07 | 0.42744 | 0 | 0 | 0 | 0.42744 | 0.42744 | 0.42744 | 0 | 0
417 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | OWN | Erection and commissioning of 1 No of 20 MVA 132/33 KV Power Transformer at 132/33 KV GSS Chikiti. | Commissioning of 1 No of 20 MVA 132/33 KV Power Transformer at 132/33 KV GSS Chikiti. | Chikiti GSS | 0.077434 | 0.077434 | 0 | 0 | 0 | 0.077434 | 2024-01-25 | 2024-11-14 | 0.077434 | 0 | 0 | 0 | 0.077434 | 0.077434 | 0.077434 | 0 | 0
418 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | OWN | Nitrogen Injection Type Fire prevention and extinguishing system (NIFPES) including accessories at GSS Chikiti | Commissioning of 1 No of 20 MVA 132/33 KV Power Transformer at 132/33 KV GSS Chikiti. | Chikiti GSS | 0.177 | 0.177 | 0 | 0 | 0 | 0.177 | 2024-01-25 | 2024-11-14 | 0.177 | 0 | 0 | 0 | 0.177 | 0.177 | 0.177 | 0 | 0
419 | 142 | O&M Cercle,Berhempur | EHT (O & M) DIVISION , BERHAMPUR | 14 | 5 | 14.22.5.4 | OWN | 20MVA Power Transformer Bay of Chikiti GSS | Commissioning of 1 No of 20 MVA 132/33 KV Power Transformer at 132/33 KV GSS Chikiti. | Chikiti GSS | 3.489 | 3.489 | 0 | 0 | 0 | 3.489 | 2024-01-25 | 2024-11-14 | 3.489 | 0 | 0 | 0 | 3.489 | 3.489 | 3.489 | 0 | 0
420 | 143 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,BHANJANAGAR | 14 | 5 | 14.22.5.3 | OWN | PCC and metaling of 220 KV switchyard at Grid S/S Bhanjanaga |  | BHANJANAGAR | 0.70812 | 0.70812 | 0 | 0 | 0 | 0.70812 | 2024-04-01 | 2024-08-28 | 0.70812 | 0 | 0 | 0 | 0.70812 | 0.70812 | 0.70812 | 0 | 0
421 | 143 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,BHANJANAGAR | 14 | 5 | 14.22.5.3 | OWN | Provision of additional earthmat and earthing required at GSS, Phulbani |  | PHULBANI | 0.31255 | 0.31255 | 0 | 0 | 0 | 0.31255 | 2024-04-01 | 2024-10-07 | 0.31255 | 0 | 0 | 0 | 0.31255 | 0.31255 | 0.31255 | 0 | 0
422 | 143 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,BHANJANAGAR | 14 | 6 | 14.22.6.3 | OWN | Providing of 1 no of OC+6 type interposing tower over river Badanadi between loc no 15 & 16 of 220 KV Bhanjanagar-Nayagarh DC line |  | BHANJANAGAR | 0.21059 | 0.21059 | 0 | 0 | 0 | 0.21059 | 2024-06-01 | 2025-02-13 | 0.21059 | 0 | 0 | 0 | 0.21059 | 0.21059 | 0.21059 | 0 | 0
423 | 143 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,BHANJANAGAR | 14 | 6 | 14.47.6.3 | Deposit work | 33KV dedicated feeder bay of 132/33KV Grid S/S Phulbani at Medical college Campus (Amount received from R & B Division Phulbani |  | PHULBANI | 0.48 | 0 | 0 | 0 | 0.48 | 0.48 | 2023-10-11 | 2023-12-30 |  | 0 |  | 0.48 | 0.48 | 0.011337 | 0.011337 | 0 | 0
424 | 143 | O&M Cercle,Berhempur | EHT (O & M) DIVISION ,BHANJANAGAR | 14 | 6 | 14.47.6.4 | Deposit work | Const of 33kv feeder bay Aska to extend power supply to pH Sub station Janibilli |  | JANIBILI | 0.036688 | 0 | 0 | 0 | 0.04 | 0.04 | 2018-10-20 | 2018-11-05 |  | 0 | 0 | 0.04 | 0.04 | 0.036688 | 0.036688 | 0 | 0
425 | 136 | O&M Cercle,Bhubaneswar | EHT (O & M) DIVISION , BHUBANESWAR | 14 | 5 | 14.22.5.3 | OWN | 40 MVA,220/33 KV POWER TRANSFORMERS and Nitrogen Fire Prevention System |  | BHUBANESWAR (220/33kV Grid S/S,INFOCITY-II | 6.4255 | 6.4255 | 0 | 0 | 0 | 6.4255 | 2025-01-17 | 2025-03-28 | 6.4255 |  | 0 | 0 | 6.4255 | 6.4255 | 6.4255 | 0 | 0
431 | 263 | O&M Cercle,Bhubaneswar | EHT (O & M) DIVISION ,KHURDA (NEW) | 14 | 5 | 14.22.5.3 | OWN | Modification of 33kV Incomer Bus (Both Power Transformer I & II) |  | 220/132/33 kV Grid S/s Atri | 0.042277 | 0.042277 | 0 | 0 | 0 | 0.042277 | 2024-01-05 | 2024-06-02 | 0.042277 |  | 0 | 0 | 0.042277 | 0.042277 | 0.042277 | 0 | 0
436 | 263 | O&M Cercle,Bhubaneswar | EHT (O & M) DIVISION ,KHURDA (NEW) | 14 | 5 | 14.22.5.4 | OWN | Upgradation of One No. 12.5MVA 132/33 kV Power transformer No. II (Bharat Bijlee Make) with by one no. 40MVA 132/33 kV Power Transformer (ECE Make) at Grid s/s Chandpur . |  | 132/33 KV Grid s/s KHURDA | 5.59 | 5.5939 | 0 | 0 | 0 | 5.5939 | 2024-08-22 | 2025-01-03 | 5.5939 |  | 0 | 0 | 5.5939 | 5.5939 | 5.5939 | 0 | 0
438 | 264 | O&M Cercle,Bhubaneswar | EHT (O&M)DIVISION, PURI | 14 | 5 | 14.22.5.4 | OWN | REPLACEMENT OF DAMAGED 132/33KV 31.5 MVA TRF BY NEW 132/33KV 40 MVA TRF(WITH INSTALLATION & COMMISSIONING) AT 132/33KV GRID S/S,SHAMUKA. |  | 132/33KV GRID S/S,SHAMUKA. | 5.5332 | 5.5332 | 0 | 0 | 0 | 5.5332 | 2024-02-28 | 2024-05-19 | 5.5332 |  | 0 | 0 | 5.5332 | 5.5332 | 5.5332 | 0 | 0
439 | 264 | O&M Cercle,Bhubaneswar | EHT (O&M)DIVISION, PURI | 14 | 5 | 14.22.5.4 | OWN | UPGRADATION OF TRANSFORMER CAPACITY FROM 1 X 20 MVA TO 2 X 20 MVA AT 132/33KV GRID S/S,SATSANKHA |  | 132/33KV GRID S/S,SATSANKHA | 3.548 | 3.548 | 0 | 0 | 0 | 3.548 | 2024-05-03 | 2024-05-22 | 3.548 |  | 0 | 0 | 3.548 | 3.548 | 3.548 | 0 | 0
440 | 264 | O&M Cercle,Bhubaneswar | EHT (O&M)DIVISION, PURI | 14 | 6 | 14.46.6.8 | DEPOSIT | "ENGINEERING,SUPPLY , ERECTION , TESTING AND COMMISIONING OF SHIFTING OF 132KV NIMAPARA-SAMAGARA PURI LILO LINE ( 1.2KM APPROX) FROM SRI JAGANNATH MEDICAL COLLEGE. |  | 132KV NIMAPARA-SAMAGARA-PURI LINE | 10.4111 | 0 | 0 | 0 | 10.41 | 10.41 | 2022-06-02 | 2024-02-20 |  |  | 0 | 8.3453 | 8.3453 | 7.924 | 7.924 | 0 | 0
445 | 135 | EHT (O&M) Circle, Cuttack | EHT (O & M) DIVISION , CHOUDWAR | 14 | 5 | 14.22.5.4 | OWN | Augmentation of sub-station capacity of 132/33 KV GSS MANIA (1*12.5+1*20)MVA to (1*12.5+1*20+1*40)MVA along with construction of 3rd 132KV Transformer |  | CHOUDWAR | 5.7895 | 5.7895 | 0 | 0 | 0 | 5.7895 | 03.10.2024 | 28.03.2025 | 5.7895 | 0 | 0 | 0 | 5.7895 | 5.7895 | 5.7895 | 0 | 0
451 | 267 | O&M Circle,Cuttack | EHT (O&M)DIVISION, PARADEEP | 14 | 5 | 14.22.5.4 | NA | Augmentation of 20MVA 132/33KV power transformer of GSS Chandikhole with new 40 MVA transformer. |  | chandikhole | 5.6026 | 5.6026 | 0 | 0 | 0 | 5.6026 |  | 2024-11-06 | 0 | 0 | 0 | 0 | 0 | 5.6026 | 5.6026 | 0 | 0
452 | 267 | O&M Circle,Cuttack | EHT (O&M)DIVISION, PARADEEP | 14 | 5 | 14.22.5.4 | NA | Augmentation of S/S capacity from 2x12.5 MVA to 2x20MVA of GSS,Olavar |  | Olavar | 0.19263 | 0.19263 | 0 | 0 | 0 | 0.19263 |  | 2024-12-03 | 0 | 0 | 0 | 0 | 0 | 0.19263 | 0.19263 | 0 | 0
462 | 266 | O&M Circle,Cuttack | EHT (O&M)DIVISION, CUTTACK | 14 | 5 | 14.22.5.3 | OWN | Up-gradation of S/S capacity from (3x40) MVA to (1x63) MVA & (2x40) MVA at GSS ,Cuttack |  | 220/132/33KV Grid s/sCuttack | 7.6882 | 7.6882 | 0 | 0 | 0 | 7.6882 | 17.01.2025 | 2025-02-28 | 7.6882 | 0 | 0 | 0 | 7.6882 | 7.6882 | 7.6882 | 0 | 0
464 | 266 | O&M Circle,Cuttack | EHT (O&M)DIVISION, CUTTACK | 14 | 5 | 14.22.5.4 | OWN | Up-gradation of S/s capacity from (1x40+2x20)MVA & (2x40+1x20)MVA at GSS, Phulnakhara . |  | 132/33kv Grid S/S Jagatsinghpur | 5.9394 | 5.9394 | 0 | 0 | 0 | 5.9394 | 09.06.2024 | 2024-07-24 | 5.4072 | 0 | 0 | 0 | 5.4072 | 5.4072 | 5.4072 | 0 | 0
465 | 266 | O&M Circle,Cuttack | EHT (O&M)DIVISION, CUTTACK | 14 | 5 | 14.22.5.4 | OWN | Up-gradation of S/s capacity from (1x40+2x20)MVA & (2x40+1x20)MVA at GSS, Jagatsinghpur . |  | 132/33kv Grid S/S Phulnakhara | 5.9363 | 5.9363 | 0 | 0 | 0 | 5.9363 | 12.06.2024 | 2024-07-31 | 5.4253 | 0 | 0 | 0 | 5.4253 | 5.4253 | 5.4253 | 0 | 0
469 | 145 | O&M circle,jaypore | EHT (O & M) DIVISION , JAYANAGER | 14 | 5 | 14.22.5.3 | NA | Construction of 132 KV Bus Coupler Bay in spare bay available in 132 KV extension Switchyard at Grid S/s Jayanagar. |  | 220/132/33 KV GSS, Jayanagar | 0.56433 | 0.56433 | 0 | 0 | 0 | 0.56433 | 2023-01-09 | 2025-03-12 | 0.56433 | 0 | 0 | 0 | 0.56433 | 0.56433 | 0.56433 | 0 | 0
471 | 145 | O&M circle,jaypore | EHT (O & M) DIVISION , JAYANAGER | 14 | 5 | 14.22.5.4 | NA | 3rd Transformer bay at 132/33 KV Grid S/s Umerkote |  | 132/33 KV GSS,Umerkote | 4.5254 | 4.5254 | 0 | 0 | 0 | 4.5254 | 2024-10-15 | 2024-06-12 | 4.5254 | 0 | 0 | 0 | 4.5254 | 6.4687 | 6.4687 | 0 | 0
473 | 145 | O&M circle,jaypore | EHT (O & M) DIVISION , JAYANAGER | 14 | 5 | 14.22.5.4 | NA | Erection and commissioning of 20 MVA ECE make transformer at 132/33 KV GSS, Borigumma |  | 132/33 KV GSS,Borigumma | 3.2109 | 3.2109 | 0 | 0 | 0 | 3.2109 | 2024-12-12 | 2025-02-09 | 3.2109 | 0 | 0 | 0 | 3.2109 | 3.2109 | 3.2109 | 0 | 0
474 | 145 | O&M circle,jaypore | EHT (O & M) DIVISION , JAYANAGER | 14 | 6 | 14.22.6.4 | NA | Construction of 2 nos of interposing tower for revival of 132KV railway line from Machkund power house to Machkund Road RTSS |  | 132KV TLS,Jeypore | 0.40806 | 0.40806 | 0 | 0 | 0 | 0.40806 | 2024-05-06 | 2024-11-27 | 0.40806 | 0 | 0 | 0 | 0.40806 | 0.40806 | 0.40806 | 0 | 0
476 | 145 | O&M circle,jaypore | EHT (O & M) DIVISION , JAYANAGER | 14 | 6 | 14.47.6.4 | NA | Erection of tower for diversion of 132KV Maliguda RTSS Lilo line. |  | 132KV TLS,Jeypore | 0.96451 | 0 | 0 | 0 | 0.96451 | 0.96451 | 2023-12-28 | 2024-11-29 | 0 | 0 | 0 | 0.96451 | 0.96451 | 0.77672 | 0.77672 | 0 | 0
478 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.3 | NA | Laying of earth mat with super impose of existing earth mat in 132 KV & 33 KV switchyard of 220/132/33 KV GSS, Theruvali |  | 220/132/33 KV GSS, Theruvali | 0.35635 | 0.35635 | 0 | 0 | 0 | 0.35635 | 15.06.24 | 2024-08-08 | 0.35635 | 0 | 0 | 0 | 0.35635 | 0.40644 | 0.40644 | 0 | 0
479 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.3 | NA | Dragging of old 12.5 MVA transformer & erection of new ECE make 20 MVA 132/33 KV power transformer at 220/132/33 KV GSS, Theruvali (w.O. No.291, Dt.2 |  | 220/132/33 KV GSS, Theruvali | 2.9037 | 2.9037 | 0 | 0 | 0 | 2.9037 | 25.01.2025 | 2025-03-04 | 2.9037 | 0 | 0 | 0 | 2.9037 | 3.3826 | 3.3826 | 0 | 0
481 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.4 | NA | PCC, remetalling of 132 & 33 KV Switchyard at 132/33/11 KV GSS Rayagada |  | 132/33/11 KV GSS Rayagada | 0.52631 | 0.52631 | 0 | 0 | 0 | 0.52631 | 15.09.24 | 2024-12-05 | 0.52631 | 0 | 0 | 0 | 0.52631 | 0.54537 | 0.54537 | 0 | 0
482 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.4 | NA | PCC & Earthmat at 132/33KV Grid S/S,Akhusingh , under Major Renovation Work |  | 132/33KV Grid S/S,Akhusingh | 0.5766 | 0.5766 | 0 | 0 | 0 | 0.5766 | 05.12.2023 | 2025-03-10 | 0.5766 | 0 | 0 | 0 | 0.5766 | 0.56596 | 0.56596 | 0 | 0
483 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.4 | NA | PCC & Earthmat at 132/33KV Grid S/S,Paralakhemundi , under Major Renovation Work |  | 132/33KV Grid S/S,Paralakhemundi | 0.40264 | 0.40264 | 0 | 0 | 0 | 0.40264 | 10.01.2024 | 2025-03-10 | 0.40264 | 0 | 0 | 0 | 0.40264 | 0.41203 | 0.41203 | 0 | 0
484 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 5 | 14.22.5.4 | NA | Stringing of single circuit line from Paralakhemundi S/S to Akhusingh S/S on existing DC tower along with 2 nos. Feeder bay extention at both ends.Sub |  | Paralakhemundi S/S to Akhusingh S/S | 29.4934 | 29.4934 | 0 | 0 | 0 | 29.4934 | 08.12.2010 | 25.02.2025 | 29.4934 |  |  |  | 29.4934 | 3.0067 | 3.0067 | 0 | 0
485 | 144 | O&M circle,jaypore | EHT (O & M) DIVISION ,THERUBALI | 14 | 6 | 14.22.6.4 | NA | Stringing of single circuit line from Paralakhemundi S/S to Akhusingh S/S on existing DC tower along with 2 nos. Feeder bay extention at both ends.Lin |  | Paralakhemundi S/S to Akhusingh S/S | 0 | 0 | 0 | 0 | 0 | 0 | 08.12.2010 | 25.02.2025 |  |  |  |  | 0 | 2.2102 | 2.2102 | 0 | 0
489 | 173 | Telecom circle BBSR | TELECOMMUNICATION DIVISION,BERHAMPUR | 14 | 5 | 14.22.5.8 | OWN | OPGW work |  | Berhampur | 0.30795 | 0.30795 | 0 | 0 | 0 | 0.30795 | NA |  | 0.30795 | 0 | 0 | 0 | 0.30795 | 0.3674 | 0.059446 | 0 | 0.30795
[21 empty] | Assets Capitalised from CWIP |  |  |  | 512.3592
[21 empty] | Direct Purchase (Own Fund) |  |  |  | 16.03
[21 empty] | Intangible Assets Addition (Own Fund) |  |  |  | 1.43
[21 empty] | Total Assets Addition during the FY 2024-25 |  |  |  | 529.8192