## Source (hidden)
Licencee OPTCL | ab | [14 empty] | OERC | FORM F-2
Project wise /Scheme wise Capital Expenditure
Rs. in Crores
Sl No. | Description of the Project/Scheme | PREVIOUS YEAR(2024-25) | [5 empty] | CURRENT YEAR(2025-26) | [5 empty] | ENSUING YEAR(2026-27)
|  | OB as on 01.04.24 | Exp. during the year | Interest during construction | Transfer to fixed assets | Other Adjustment | Closing balance of WIP as on 31.03.25 | Expenditure during the year |  |  | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.26 | Exp. during the year | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.27 | Financed by | OERC
[8 empty] | Actual For First Six Months | Projection For Balance Six Months | Total
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
A | CONSTRUCTION-Own Contribution (Debt:Equity)
1 | 220/33 KV Sub-Station at Nuabetanda | [5 empty] | Actual For First Six Months 8: 0; Projection For Balance Six Months 9: 30; Total 10: 30; Total 13: 30; Total 14: 35; Total 17: 65 | OTSSP-I | AEA
2 | 220/33 KV Sub-Station at Hatabasta | [5 empty] | Actual For First Six Months 8: 6.45; Projection For Balance Six Months 9: 20; Total 10: 26.45; Total 13: 26.45; Total 14: 15; Total 17: 41.45 | OTSSP-I | AEA
3 | 220/33 KV Sub-Station at Mundamba | 0 | 0.03 |  |  |  | 0.03 | 12.15 | 17.85 | 30 |  |  | 30.03 | 20 |  |  | 50.03 | OTSSP-II | BEA
4 | 220KV UG Cabling from GSS Mendhasal to GIS Chanadaka B with Bay Extension at both ends | [5 empty] | Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5 | DRPS-II | AEA
5 | 220/33KV AIS with 22km Line at Khandapada | [5 empty] | Total 10: 0; Total 13: 0; Total 17: 0 | DRPS-II | AEC
6 | 220/33KV GIS at Sundarpada with Line | [5 empty] | Total 10: 0; Total 13: 0; Total 17: 0 | DRPS-II | AEB
7 | Constn. of 2x20 MVA 132/33KV GRID S/S, CHANDIPUR & ASSOCIATED 132 KV LILO (FROM EXISTING 132KV SORO-BALASORE S/C Line) SCHEME |  | 1.4 |  | 1.4 |  | 0 | 0.79 | 1.75 | 2.54 |  | 2.54 | 0 | 0.1 |  | 0.1 | 0 | JICA | BEA
8 | Construction of 2nd Circuit of 132 KV Bhadrak-Anadpur Line from 220/132/33 KV grid S/S,Bhadrak to 132/33 KV Grid S/S,Anadpur with One No. Feeder bay extention at both ends | 5.01 | 3.3 |  |  |  | 8.31 | 0.41 | 1.59 | 2 |  | 10.31 | 0 | 0.37 |  | 0.37 | 0 | RRCP-I | BEA
9 | Construction 2x500 MVA, 400/220 GIS at Ramakrushnapur along with Associated 400 KV (4.642 RKMs.) & 220 KV (38.194 KMs.) LILO. | 6.05 |  |  |  |  | 7: 6.05; Total 10: 0; Total 12: 6.05; Total 13: 0; Total 17: 0 | DRPS-II | BEA
10 | Const. Of 132 KV SC line for proposed Grid S/S Balimunda( Dhamara) to existing 132/33 KV s/s Olaver. | 0.16 |  |  |  |  | 7: 0.16; Total 10: 0; Total 12: 0.16; Total 13: 0; Total 17: 0 | 30% Gov/UCO Bank | BEA
11 | Const. Of 220 KV DC line for 400/220/132 KV )PGCIL) Grid S/S to proposed 220/132 KV Grid S/S, Karanjia. | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 12: 0.03; Total 13: 0; Total 17: 0 | New EFC | BEC
12 | Const. Of 400 KV LILO one tapping from new Duburi-Paradeep. | 0.02 |  |  |  |  | 7: 0.02; Total 10: 0; Total 12: 0.02; Total 13: 0; Total 17: 0 | New EFC | BEC
13 | Const. of 2X12.5MVA 132/33 KV Grid S/S Basta with associated line. | 0.05 |  |  |  |  | 7: 0.05; Total 10: 0; Total 12: 0.05; Total 13: 0; Total 17: 0 | own | BEA
14 | Const. Of 132 KV SC line from existing 400/220/132 KV (PGCIL) Grid S/S Kuchei to Grid S/S Rairangpur. | 0.1 |  |  |  |  | 7: 0.1; Total 10: 0; Total 12: 0.1; Total 13: 0; Total 17: 0 | own | BEA
15 | Constn. Of one No 132/33 KV Bay at Kuchei End (PGCIL) | 4.78 | 0.02 |  | 4.8 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | own | BEA
16 | Const of 2*500MVA 400/220 KV GSS Ramakrishnapur | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5 | DRPS-II | BEA
17 | Construction of 132kv Lamtaput LILO lne from 132 KV Podagada -Pottangi line with 2No Bay extention at Lamtaput Grid s/s |  | 0.08 |  |  |  | 0.08 | 0.01 | 5 | 5.01 |  |  | 5.09 | 10 |  |  | 15.09 | Special EFC | BEA
18 | Revival of 132 KV existing Transmission Line from Macchkund Power House to Machhkund RTSS (including Surevey work - 4 lakh) ) | 0.07 |  |  |  |  | 7: 0.07; Total 10: 0; Total 12: 0.07; Total 13: 0; Total 17: 0 | own | BEC
19 | Const. of 220/33 KV Grid S/s at Govindapalli with LILO of 220 KV SC line from Balimela to Malkangiri. |  | 15.62 |  | 15.62 |  | 7: 0; Actual For First Six Months 8: 1.32; Projection For Balance Six Months 9: 2.39; Total 10: 3.71; Total 13: 3.71; Total 17: 3.71 | JICA | BEA
20 | Construction of 132/33 KV Grid S/s at Boriguma with LILO of existing 132 KV SC line from 220/132KV grid substation, Jaynagar to 132/33KV grid substation, Tentulikhunti. | 30.92 | 0.27 |  | 31.19 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | E-300 | BEA
21 | Balance work of 132/33 KV GSS Boriguma | [5 empty] | 0 | 0.08 | 0.95 | 1.03 |  |  | 1.03 | 0.31 |  |  | 1.34 | E-300 | BEC
22 | Stringing of 2nd circuit (three conductors) from LILO point of existing 220 KV Balimela-Malkangiri Line to Newly constructed 220/33 KV Grid S/S Kalimela. | 0.14 | 0.02 |  | 0.16 |  | 7: 0; Actual For First Six Months 8: 0.21; Total 10: 0.21; Total 13: 0.21; Total 16: 0.21; Total 17: 0 | own | BEC
23 | Construction of 132KV DC line from Sunabeda to 220/132/33KV grid substation Jayanagar with bay extension at each end. Est.No. 17/2012-13 | 29.82 | 1.18 | 0.43 | 31.43 |  | 7: 0; Projection For Balance Six Months 9: 1.8; Total 10: 1.8; Total 12: 1.8; Total 13: 0; Total 17: 0 | 40%Gov/Union bank | BEA
24 | Construction of 1no. 132 KV feeder bay each at 132/33KV GSS Dabugaon & Umerkote along with hot lines stringling of 132KV conductor from Dabugaon GSS to Umerkote GSS. |  | 2.15 |  |  |  | 2.15 | 1.05 | 3.37 | 4.42 |  |  | 6.57 | 1.42 |  |  | 7.99 | own | BEC
25 | GSS Pottangi |  | 0.9 |  | 0.9 |  | 7: 0; Projection For Balance Six Months 9: 0.65; Total 10: 0.65; Total 12: 0.65; Total 13: 0; Total 17: 0 | E-300 | BEA
26 | Construction of 2x20MVA 220/33KV Grid S/s at KALIMELA with associated 220KV SC line on DC tower from Malkangiri S/s to the proposed Kalimela S/s with one no offedder bay extension at Malkangiri. | [5 empty] | 7: 0; Actual For First Six Months 8: 0.05; Total 10: 0.05; Total 12: 0.05; Total 13: 0; Total 17: 0 | E-250 | BEA
27 | Construction of 2x20 MVA, 220/33 KV Grid S/s at Malkanagiri with associated 220 KV SC line on DC tower from Balimela S/s to proposed Malkangiri S/s with one bay extension. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.5; Total 10: 1.5; Total 13: 1.5; Total 17: 1.5 | E-300 | BEA
28 | const of 220/33KV GSS Mukhiguda | [5 empty] | 7: 0; Projection For Balance Six Months 9: 50; Total 10: 50; Total 13: 50; Total 14: 100; Total 17: 150 | NEW EFC | AEB
29 | 400KV DC line from Indravati Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 50; Total 10: 50; Total 13: 50; Total 14: 100; Total 17: 150 | GEETC | AEB
30 | Construction of 220/132/33 KV grid S/s at kiakata(Executed by M/s TPL) | 153.44 | 1.37 | 4.19 |  |  | 159 | 1.72 | 8 | 9.72 |  |  | 168.72 | 1 |  | 169.72 | 0 | JICA | BEA
31 | 132/33 KV GSS at Athamallik and Associated lines(Executed by M/s MBH Power) | 13.95 | 11.63 |  |  |  | 25.58 | 1.4 | 9.1 | 10.5 |  | 36.08 | 0 | 2 |  | 2 | 0 | LVMS | BEA
32 | Construction of 400 KV line from TTPS Stage-II to 400/220/33 KV GIS at Meramundali-B (Executed by M/s Groma) | [5 empty] | 0 | 1.08 | 38.92 | 40 |  |  | 40 | 20 |  |  | 60 | Special- EFC | AEA
33 | Diversion of one no. of 400KV and 4 nos. of 220Kv line with 220KV lilo arrangement for connectivity with 400/220KV GIS Meramunduli-B(executed by AK Das) | 29.51 | 0.5 |  |  |  | 30.01 | 0.14 | 1.86 | 2 |  |  | 32.01 | 10 |  |  | 42.01 | SACI | BEA
34 | 2*40 MVA, 220/33 KV GSS with SAS at Janhapada, Parjang(Executed by M/s Empower Trans) |  | 19.13 |  |  |  | 19.13 | 1.39 | 12.69 | 14.08 |  |  | 33.21 | 1.32 |  | 34.53 | 0 | OTSSP-I | BEA
35 | Aluminium Park(Executed by M/s SEL) | [5 empty] | 0 | 0.94 | 14.06 | 15 |  |  | 15 | 30 |  |  | 45 | OTSSP-II | BEA
36 | 220/132/33 KV GSS at Chhendipada and Associated lines(Executed by M/s APS) | 6.36 | 5.61 |  |  |  | 11.97 | 11.15 | 13.85 | 25 |  |  | 36.97 | 20 |  |  | 56.97 | OTSSP-II | BEA
37 | 2X200 MVA, 220/132 KV AIS S/S WITH SAS AT Chainpal | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 | New EFC | AEB
38 | 440/220/33 KV GSS at Neulapoi, Dhenkanal |  | 0.26 |  |  |  | 7: 0.26; Total 10: 0; Total 13: 0.26; Total 17: 0.26 | OTSSP-II | BEA
39 | 2x20 MVA, 220/33 Grid S/s near Deogarh along with associated LILO arrangement from 220 KV Rengali-Tarkera Transmission Line. |  | 0.093 |  | 0.093 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | JICA | BEA
40 | Construction of 132/33 KV Grid S/S at Lakhanpur alongwith associated Transmission line from Brajrajnagar. |  | 5.437 |  | 5.437 |  | 0 |  | 0.1 | 0.1 |  | 0.1 | 0 | 0.1 |  | 0.1 | 0 | JICA | BEA
41 | Construction of 2x20 MVA, 132/33 KV Grid S/s at Hirakud with GIS along with associated 132 KV LILO lind from existing 132 KV Burla-Lapanga line & existing 132 KV ALCO line. Est. Cost-11/2017-18 |  | 0.003 |  | 0.003 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | E-140 | BEA
42 | Const. of 400/220 KV Grid S/S at Lapanga | 0.467 |  |  |  |  | 7: 0.467; Total 10: 0; Total 12: 0.467; Total 13: 0; Total 17: 0 | E-250 | BEA
43 | Const of 2 x 100MVA 220/132/33 KV Grid S/S at Kuanrmunda with LILO arrangement from existing 220KV Budhipadar Tarkera DC Line |  | 0.519 |  | 0.519 |  | 0 | 1.6 | 6.69 | 8.29 |  | 8.29 | 0 |  |  |  | 0 | E-300 | BEA
44 | Construction of 132 KV LILO Line from one ckt of 132 KV Budhipadar-Sundargarh DC line with construction of 132 KV feeder bay at 220/132/33 KV Grid S/s Bamra. (Approx. line length-45 KM) | 6.191 | 6.828 |  |  |  | 13.019 | 3.14 | 11.08 | 14.22 |  |  | 27.239 | 6 |  | 33.239 | 0 | RRCP-II | BEA
45 | Construction of 132KV LILO Line from 132 KV Chhend-Shri Ganesh Metaliks Circuit (Between Loc. No. 50 to 53) to 220/132/33 KV GSS, Kuanrmunda. | 1.109 | 0.212 |  | 1.321 |  | 7: 0; Actual For First Six Months 8: 0.05; Total 10: 0.05; Total 12: 0.05; Total 13: 0; Total 17: 0 | RRCP-II | BEA
46 | Construction of 220 KV LILO line from Loc. No. 125 & Loc. No. 126 of existing 220 KV Budhipadar to Tarkera line (CKT-II) and 132 KV LILO line from Loc. No. 291 of existing 132 KV Budhipadar to Tarkera line (CKT-II) and 220/132/33 KV Grid Sub-Station at Bamra. (50% Own Work) |  | 0.273 |  | 0.273 |  | 0 | 0.54 | 1.11 | 1.65 |  | 1.65 | 0 |  |  |  | 0 | OTSSP-II | BEA
47 | Construction of 220/132 KV S/S at IB(PMU) | 0.679 |  |  |  |  | 7: 0.679; Total 10: 0; Total 13: 0.679; Total 17: 0.679 |  | BEC
48 | Construction of 220/132 KV S/S at IB(PMU) (PROVISION FOR ABANDONED PPROJECT) | -0.679 |  |  |  |  | 7: -0.679; Total 10: 0; Total 13: -0.679; Total 17: -0.679 |  | BEC
49 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Koida. 220 KV D/C Barbil-Koida line. 220 KV Taldih-Koida line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.12; Total 10: 0.12; Total 13: 0.12; Total 14: 5; Total 17: 5.12 | NEW EFC | AEB
50 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Kansbahal. 220 KV D/C Kuarmunda-Kansbahal line. 132 KV D/C Kansbahal-Kalunga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.13; Total 10: 0.13; Total 13: 0.13; Total 14: 5; Total 17: 5.13 | NEW EFC | AEB
51 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Basantpur. 220 KV D/C A. Katapali-Basantpur line. 132 KV D/C Basantpur-Thuapali line. 132 KV D/C Basantpur-Maneswar line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.2; Total 10: 0.2; Total 13: 0.2; Total 14: 5; Total 17: 5.2 | NEW EFC | AEB
52 | Construction of 2 X 50MVA, 132/33 KV GSS at Kolabira. 132 KV D/C Kolabira-Kuchinda line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3 | NEW EFC | AEB
53 | Construction of 2 X 50MVA, 132/33 KV GSS at Subdega. 132 KV D/C Sundargarh-Subdega line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3 | NEW EFC | AEB
54 | Construction of 2 X 50MVA, 132/33 KV GSS at Sason. 132 KV D/C Basantpur-Sason line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3 | NEW EFC | AEB
55 | Construction of 2 X 160MVA + 2 X 50 MVA, 220/132/33 KV GSS at Badimal. 220 KV D/C Budhipadar-Badimal line. 132 KV D/C Badimal-Lakhanpur line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5 | NEW EFC | AEB
56 | Construction of 765/400 KV GSS at Kolabira. 765 KV D/C Kenapali (PG)-Kolabira line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.15; Total 10: 0.15; Total 13: 0.15; Total 14: 10; Total 17: 10.15 | NEW EFC | AEB
57 | 765 KV D/C Kolabira-Duburi line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 | NEW EFC | AEB
58 | 400 KV D/C OPGC - Kolabira line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5 | NEW EFC | AEB
59 | 400 KV DC Line From Floating Solar Power Plant, Hirakud to proposed 765/400 KV GSS, Kulihamal, Pokharasale, Kolabira | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.13; Total 10: 0.13; Total 13: 0.13; Total 14: 5; Total 17: 5.13 | NEW EFC | AEB
60 | 220/132 kv SS DASPALLA with 220 kv LILO from Bhanjanagar to Meramundali line under JICA project | 53.19 | 1.43 | 1.55 |  |  | 7: 56.17; Projection For Balance Six Months 9: 22; Total 10: 22; Total 13: 78.17; Total 14: 15; Total 17: 93.17 | JICA | BEA
61 | 2*40 mva 220/33 KV grid SS at Baliguda and 220 kv line from Kesinga to Baliguda | 128.29 | 1.03 | 3.85 |  |  | 133.17 | 4.15 | 37 | 41.15 |  |  | 174.32 | 32.5 |  |  | 206.82 | E-300 | BEA
62 | 2*20 mva 132/33 kv SS at R UDAYGIRI with 132 kv line from MOHANA to R UDAYGIRI | 54.75 | 8.67 |  | 3.32 |  | 60.1 | 0.2 | 1 | 1.2 |  |  | 61.3 | 0.25 |  |  | 61.55 | E-300 | BEA
63 | 400KV DC line from Pandiabil to Sindhaba | 0.57 |  |  |  |  | 7: 0.57; Total 10: 0; Total 13: 0.57; Total 17: 0.57 |  | BEC
64 | 132 kv Line from Bhanjanagar to Phulbani | 0.13 |  |  |  |  | 7: 0.13; Projection For Balance Six Months 9: 0.4; Total 10: 0.4; Total 13: 0.53; Total 17: 0.53 | OWN | BEC
65 | Provision for incompleted / abondoned work | -0.7 |  |  |  |  | 7: -0.7; Total 10: 0; Total 13: -0.7; Total 17: -0.7 |  | BEC
66 | 220 KV DC line N.Pur-Atri to TSSEZ at Gopalpur | [5 empty] | 0 | 0.08 | 10 | 10.08 |  |  | 10.08 | 30 |  |  | 40.08 | GEETC | BEA
67 | GSS Badakushastali | [5 empty] | 7: 0; Actual For First Six Months 8: 0.29; Total 10: 0.29; Total 13: 0.29; Total 14: 14; Total 17: 14.29 | GEETC | BEA
68 | 400 KV Theruvelli-Gopalpur DC Line | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 30; Total 17: 30 | GEETC | AEB
69 | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga with associated 220kV & 132kV line. (JICA) | 93.33 | 12.98 | 0.8 |  |  | 107.11 | 3.29 | 4 | 7.29 |  | 114.4 | 0 |  |  |  | 0 | JICA | BEA
70 | 220kV LILO line from one circuit of existing 220kV TTPS-JODA D/C Line (Circuit-II) to 220/33kV GIS Substation, Keonjhar | 9.26 |  |  |  |  | 9.26 | 0.1 | 3 | 3.1 |  |  | 12.36 | 9 |  | 21.36 | 0 | OWN | BEA
71 | 2 nos. 220KV Bay extension at 220/33KV GIS Substation at Keonjhar on Turnkey Basis | 7.49 | 0.77 |  |  |  | 8.26 |  | 0.5 | 0.5 |  | 8.76 | 0 | 0.2 |  | 0.2 | 0 | E-250 | BEA
72 | 132 KV Joda-Polasponga and Polasponga-Keonjhar line | 1.37 |  |  |  |  | 7: 1.37; Total 10: 0; Total 12: 1.37; Total 13: 0; Total 17: 0 | OWN | BEC
73 | Const of 765/400 Kv GSS at Duburi | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 0.5; Total 17: 0.5 | NEW EFC | AEB
74 | 2*500MVA GSS at Basudevpur & Associated lines | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 0.5; Total 14: 5; Total 17: 5.5 | SDMF-100% grant | AEA
75 | Construction of 132 KV DC Line on DC Tower from 220/132/33 KV Grid S/S at Jayapatna(Baner) to 132/33 KV Grid S/S at Junagarh, Construction of 2 Nos of 132 KV Feeder Bay extention at 132/33KV Grid S/S Junagarh and 2 Nos of 132 KV feeder bay Extension at Jayapatna. | 7.94 | 0.87 | 2.03 |  |  | 7: 10.84; Actual For First Six Months 8: 0.01; Total 10: 0.01; Total 13: 10.85; Total 14: 5; Total 17: 15.85 | E-140 | BEA
76 | Construction of 132/33 KV Grid S/S At Brundabahal & its associated 132 KV LILO Transmission Line | 27.45 | 1.49 |  | 28.94 |  | 7: -3.5527e-15; Projection For Balance Six Months 9: 5; Total 10: 5; Total 13: 5; Total 14: 3; Total 17: 8 | Equity-Brundabahal(100%Equity) | BEA
77 | Construction of 220/33KV, 2x20MVA grid sub station near Kashipur with associated 220KVLILO line from existing 220KV Indravati-Theruvalli DC line to proposed grid sub-station. | [5 empty] | 7: 0; Actual For First Six Months 8: 0.65; Total 10: 0.65; Total 13: 0.65; Total 17: 0.65 | E-300 | BEA
78 | Construction of 220/132/33 KV Grid S/s at Gunupur with 220 KV LILO arrangement from existing 220 KV Theruvalli- Narendrapur Ckt-I and 132 KV Lilo arrangement from existing 132 KV Akhusingh-Paralakhemundi line. |  | 0.89 |  | 0.89 |  | 0 | 0.23 | 1.5 | 1.73 |  |  | 1.73 | 5 |  |  | 6.73 | JICA | BEA
79 | Construction of 132KV SC line on DC tower from existing loc no-170 of Akhusingh-Paralakhemundi line to proposed Loc No-41 of RTSS Palasingh line, in rayagada district of Odisha. | 2.37 | 1.56 |  | 3.93 |  | 7: 0; Projection For Balance Six Months 9: 0.52; Total 10: 0.52; Total 13: 0.52; Total 17: 0.52 | OWN | BEA
80 | Survey & Forest clearance work of 400kv DC line connectivity between Indravati to Therubali for development of Green Energy Evacuation Transmission Corridor for evacuation of RE power .( Approx. line length = 100km) | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.2; Total 10: 1.2; Total 13: 1.2; Total 14: 0.47; Total 17: 1.67 | GEETC | AEC
81 | Survey for Construction of Transmission Infrastucture meant for proposed 3x75 MW FSPV Project, UIHEP Indravati from UIHEP, Grid sub-station mukhiguda to proposed pooling sub-station (Padepadar) approx length-12 KMs and contour survey of sub-station land to an extent of acres-28.00 | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.07; Total 10: 0.07; Total 13: 0.07; Total 17: 0.07 | NEW EFC | AEC
82 | Providing Consultancy Service for obtaining the forest clearance of 400kv Quad Moose D/C line connectivity between Jeypore to Therubali to TATA SEZ | [5 empty] | 7: 0; Actual For First Six Months 8: 1; Total 10: 1; Total 13: 1; Total 14: 5.46; Total 17: 6.46 | GEETC | AEC
83 | Construction of 400 kV DC Line from Jeypore (PGCIL) to Therubali to TATA SEZ | [5 empty] | 7: 0; Projection For Balance Six Months 9: 20; Total 10: 20; Total 13: 20; Total 14: 50; Total 17: 70 | GEETC | AEB
84 | Construction of 33/220kv Pooling Sub station at Padepadar for evacuating Power from FSPV, Indravati | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 50; Total 17: 60 | NEW EFC | AEB
85 | Construction of 220kv Line Connectivity from the proposed 33/220KV Pooling s/s, Padepadar to 400/220KV , Mukhiguda Switchyard | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 30; Total 17: 40 | NEW EFC | AEB
86 | Construction of 02 nos. of 220KV Bays at Mukhiguda s/y for evacuating Power from FSPV Project | [5 empty] | 7: 0; Projection For Balance Six Months 9: 8; Total 10: 8; Total 13: 8; Total 14: 6.2; Total 17: 14.2 | NEW EFC | AEB
87 | Consultancy Service for forest clearance work of an area of approx. 100 Acres of land proposed for Construction of 400/220KV AIS at Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.68; Total 10: 0.68; Total 13: 0.68; Total 14: 0.17; Total 17: 0.85 | GEETC | AEC
88 | Construction of 2 x 500MVA, 400/220KV AIS GSS with SAS at Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 20; Total 10: 20; Total 13: 20; Total 14: 50; Total 17: 70 | GEETC | AEB
89 | 220/132/33 KV S/S Nuapada | 0.36 |  |  |  |  | 7: 0.36; Total 10: 0; Total 13: 0.36; Total 14: 10; Total 17: 10.36 | NEW EFC | BEB
90 | 132/33 KV Grid S/S Bhatli & Associated Line | 50.654 | -1.496 |  | 49.158 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | E-140 | BEA
91 | 132/33 KV Grid S/S B.M.Pur & Associated 132 KV Line from Sonepur to B.M.Pur |  | 0.018 |  | 0.018 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | E-250 | BEC
92 | 132/33 KV Grid S/S Thuapali (Deshbhatli) & Associated Line |  | 0.8 |  | 0.8 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | JICA | BEA
93 | 220KV DC Line From Existing GSS Sadeipali, New Bolangir to GSS Kesinga |  | 0.213 |  | 0.213 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | OWN | BEC
94 | Construction work of 220KV LILO of Bolangir-Kesinga line for connectivity to 400/220 KV GSS Madhiapali PGCIL Bolangir |  | 0.058 |  | 0.058 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | OWN | BEC
95 | 2X40 MVA,220/33 KV AIS Grid S/S, Madanpur Rampur Along with its associated 220KV LILO line of 220KV Kesinga-Baliguda DC Line | 0.089 | -0.153 |  |  |  | -0.064 | 2.67 | 21 | 23.67 |  |  | 23.606 | 17.27 |  | 40.876 | 0 | LVMS | BEA
96 | Construction of 220/33 KV Srid SS at Sarasmal Rampur |  | 0.084 |  |  |  | 0.084 | 0.22 | 0.5 | 0.72 |  |  | 0.804 | 15 |  |  | 15.804 | OTSSP-I | BEA
97 | 132/33 KV Grid S/S TARBHA | 8.527 | 2.83 |  |  |  | 11.357 | 3.75 | 6.15 | 9.9 |  |  | 21.257 | 10 |  | 25.257 | 6 | E-Tarbha | BEA
98 | 2X20 MVA, 132/33 KV GSS with SAS, Rampur at Agalpur with associated 132 KV LILO Line | 2.839 | 20.08 |  |  |  | 22.919 | 4.71 | 3.3 | 8.01 |  | 30.929 | 0 | 2 |  |  | 2 | LVMS | BEA
99 | 2X20 MVA, 132/33 KV GSS with SAS, JHARBANDH with associated 132 KV LILO Line | 1.259 | 3.557 |  |  |  | 4.816 | 3.24 | 27.25 | 30.49 |  |  | 35.306 | 10 |  | 39.306 | 6 | OTSSP-I | BEA
100 | 2X40 MVA, 132/33 KV GSS with SAS, Bijepur with associated 132 KV LILO Line | 0.436 | 5.923 |  |  |  | 6.359 | 1.81 | 8.5 | 10.31 |  | 16.669 | 0 | 10 |  | 10 | 0 | OTSSP-I | BEA
101 | Construction of 132 KV SC Line on DC Tower from 132/33 KV GSS Patnagarh to 132/33KV GSS Kantabanji with 132 KV Bay Extention at both GSS patnagarh and GSS kantabanji | 4.85 | 6.62 |  |  |  | 11.47 | 1.67 | 6.1 | 7.77 |  |  | 19.24 | 5 |  | 24.24 | 0 | RRCP-II | BEA
102 | Construction of 132 KV SC Line on DC Tower from 132/33 KV GSS Padampur to 132/33KV GSS Ghens | 9.195 | 6.438 |  |  |  | 15.633 | 0.65 | 2.6 | 3.25 |  |  | 18.883 | 5 |  | 23.883 | 0 | RRCP-II | BEA
104 | 400/220/33 KV GSS Titlagarh with associated line and it's 220 KV connecting system | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1; Total 10: 1; Total 13: 1; Total 14: 10; Total 17: 11 | NEW EFC | AEB
105 | Construction of GSS Manamunda with 2nd Circuit Stringing of Boudh -Sonepur line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 8; Total 10: 8; Total 13: 8; Total 14: 20; Total 17: 28 | GEETC | AEA
106 | 2nd Circuit Stringing of 132 KV Padampur-Ghens line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 10; Total 17: 13 | RRCP-II | AEA
107 | 2nd Circuit Stringing of Patnagarh-Kantabanji line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 10; Total 17: 13 | RRCP-II | AEA
108 | Construction of 220 KV DC line from 400/220/33 KV GSS Titlagarh to 220/132/33 KV GSS Kesinga | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 0.5; Total 14: 10; Total 17: 10.5 | NEW EFC | AEB
109 | Construction of 220/33KV grid sub-station at Balichandrapur (Palei) with associated lines. | 30.89 | 18.54 | 0.36 | 49.79 |  | 7: 0; Actual For First Six Months 8: 6.66; Total 10: 6.66; Total 12: 6.66; Total 13: 0; Total 17: 0 | E-140 | BEA
110 | Construction of 132/33 KV Grid S/s at Bahugram with associated 132 KV line. Est. No. 07/2016-17 | [5 empty] | 0 | 0 | 0.1 | 0.1 |  | 0.1 | 0 |  |  |  | 0 | JICA | BEA
111 | 400/220/33KV GIS at Neulapoi with line | [5 empty] | 0 | 1.44 | 18.56 | 20 |  |  | 20 | 80 |  |  | 100 | OTSSP-II | AEA
112 | Constn of 132/33 KV Grid S/S, Kuakhia | 2.81 |  |  |  |  | 7: 2.81; Total 10: 0; Total 13: 2.81; Total 17: 2.81 | NEW EFC | BEC
113 | Constn of boundary wall at proposed land for 132/33 KV Grid S/s Pihura near Grid Steel Alloys | 0.19 |  |  |  |  | 7: 0.19; Total 10: 0; Total 13: 0.19; Total 17: 0.19 |  | BEC
114 | Const of 132 KV line from Kendrapara to Paradeep | 0.25 |  |  |  |  | 7: 0.25; Total 10: 0; Total 13: 0.25; Total 17: 0.25 |  | BEC
115 | PROVISION FOR abandoned/incomplete CWIPS | -1.66 |  |  |  |  | 7: -1.66; Total 10: 0; Total 13: -1.66; Total 17: -1.66 |  | BEC
116 | 132 KV S/s at Kendrapara (PMU) | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 |  | BEC
117 | 400 KV DC Line from Meramundali to Duburi | -0.2 |  |  |  |  | 7: -0.2; Total 10: 0; Total 13: -0.2; Total 17: -0.2 |  | BEC
118 | Up-gradation of existing132/33KVGIS Khuntuni to up-coming Neulapoi GIS with line. | [5 empty] | 0 | 0 | 10 | 10 |  |  | 10 | 10 |  |  | 20 | OTSSP-II | AEA
119 | Construction Of 220 Kv D/C Transmission Line From 400/220/33 Kv Ais Grid S/S, Neulapoi To Proposed Manufacturing Complex Of M/S : Kalyani Steels At Gajamara, Dhenkanal | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 | OTSSP-II | AEA
120 | Const of 400 KV S/S at Ersama | 12.41 | 86.61 |  |  |  | 99.02 | 17.31 | 39.69 | 57 |  |  | 156.02 | 30 |  |  | 186.02 | E-Paradeep | BEA
121 | 400 KV DC Line at Ersama | 25.73 | 31.37 |  |  |  | 57.1 | 27.01 | 55.99 | 83 |  |  | 140.1 | 70 |  |  | 210.1 | E-Paradeep | BEA
122 | Const of 220 KV DC Line at Ersma | 99.14 | 55.72 |  |  |  | 154.86 | 24.33 | 24.67 | 49 |  |  | 203.86 | 50 |  |  | 253.86 | E-Paradeep | BEA
123 | Construction of 220*40 MVA, 220/33 KV GIS at Paradeep (Plastic park) | - |  |  |  |  | Actual For First Six Months 8: 1.3; Projection For Balance Six Months 9: 3; Total 10: 4.3; Total 13: 4.3; Total 14: 20; Total 17: 24.3 | OTSSP-II | AEA
124 | STAMS-I | [6 empty] | 101 | 93 | 194 |  |  | 194 | 54 |  | 248 | 0 |  | BEA
125 | Dismantling of ACSR conductor and stringing of HTLS conductor of 132KV Bhadrak-Soro SC line including 132KV Soro LILO Line under EHT(O&M) Division, Balasore(Est. Cost- 101.70Cr) | 0 | 0 |  |  |  | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 50; Total 17: 50 |  | AEB
126 | Dismantling of ACSR Panther conductor and augmentation of ACSR Panther conductor by HTLS conductor in 132 KV Duburi-Jajpur Road DC Line under EHT (O&M) Division, Jajpur Road (24.70Cr) | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 15; Total 17: 15 |  | AEB
127 | Engineering, supply, Erection and commissioning of 2 x 160 MVA (220/132 KV),2 X 40 MVA (132/33 KV), 220/132/33 KV GRID S/S, With SAS at BALIMUNDA,Dhamra and 220 KV LILO Line from From Loc.No.277 of existing 220KV Duburi- Balasore Ckt-I line to proposed sub-station at Balimunda (Approx. line length-34.890 Kms) on “EPC/Turnkey CONTRACT BASIS”. |  | 0.12 |  | 0.12 |  | 0 | 4.46 | 0.89 | 5.35 |  | 5.35 | 0 |  |  |  | 0 | Equity-140 | BEA
128 | 400/220/33 KV GIS at Bhandaripokhari (Bhadrakh textile Park) | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5 | OTSSP-II | AEA
129 | Const of 2X20MVA 132/33KV Grid SS Raighar with LILO line dabugaon-umerkote to Raighar [Boundary Wall] | 0.62 | 1.48 |  |  |  | 2.1 | 5.64 | 40.35 | 45.99 |  |  | 48.09 | 16 |  |  | 64.09 | OTSSP-I | BEA
130 | Construction of 2x20 MVA 132/33 KV Grid S/s at Lamtaput with associated 132 KV LILO line from 132 KV Machkund PH Machkund RTSS line | 24.31 | 3.38 | 1.94 |  |  | 29.63 | 4.42 | 1.5 | 5.92 |  |  | 35.55 | 6 |  | 41.55 | 0 | E-140 | BEA
131 | Const. of 132KV SC line from proposed 132/33 grid S/s Pottangi to porposed 132/33KVgrid s/s Podagada with bay extension at both end. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.2; Total 10: 0.2; Total 13: 0.2; Total 17: 0.2 | Special EFC | BEA
132 | Boundary wall for 220/33 KV GSS at Jahnapada,Parjang | 0.34 |  |  |  |  | 7: 0.34; Total 10: 0; Total 13: 0.34; Total 17: 0.34 | OTSSP-I | BEA
133 | const.of 220/132 s/s at chendipada NISA | 0.14 |  |  |  |  | 7: 0.14; Total 10: 0; Total 13: 0.14; Total 17: 0.14 | OTSSP-II | BEA
134 | 2X 50MVA 132/33 KV GIS S/S at Autonagar | 0.01 |  |  |  |  | 0.01 | 0.36 | 0.05 | 0.41 |  |  | 0.42 | 75 |  |  | 75.42 | DRPS-II | BEA
135 | 132 KV UG cable from Narendrapur to Berhampur |  | 64.25 |  |  |  | 64.25 | 1.67 | 11.71 | 13.38 |  |  | 77.63 | 8 |  |  | 85.63 | DRPS-II | BEA
136 | GSS Gopalpur with line from narendrapur Atri | [5 empty] | 7: 0; Projection For Balance Six Months 9: 11; Total 10: 11; Total 13: 11; Total 14: 30; Total 17: 41 | GEETC | BEA
137 | 132kV DC line between existing 220/132/33Kv Grid Substion Turumunga and 132/33kV Dhenkikote Substation (Approx. Line Length-42.52 Km) with 2 nos. 132kV feeder bay extension at both end. (LVMS Scheme) | 0.55 | 1.41 |  |  |  | 1.96 | 0.59 | 2.41 | 3 |  |  | 4.96 | 8 |  |  | 12.96 |  | BEA
| Total Construction By debt and equity | 947.366 | 414.377 | 15.15 | 230.383 | 0 | 1146.51 | 270.58 | 864.43 | 1135.01 | 0 | 252.705 | 2028.815 | 1474.64 | 0 | 714.941 | 2788.514
138 | Telecom debt and equity | 74.5848 | 10.2972 | 0 | 2.4772 | 2.9985 | 79.4064 | 3.83 | 7.76 | 11.59 | 0 | 63.26 | 27.7364 | 66.44 | 0 | 85.8 | 8.3764
139 | Civil debt and equity | 11.0257 | 25.4337 | 0 | 13.2838 | 5.0692 | 18.1065 | 12.9429 | 59.2324 | 72.1753 | 0 | 28.3497 | 61.9321 | 63.4845 | 0 | 108.7647 | 16.6519
140 | IT and others debt and equity | 10.67 | 1.1 | 0 | 0.029676 | 0.078474 | 11.6619 | 0 | 12.7149 | 12.7149 | 0 | 24.3768 | 0 | 78.09 | 0 | 16.09 | 62
141 | Other Capex by O&M Wings Debt and equity | 97.4156 | 157.1259 | 0 | 128.7918 | 0 | 125.7538 | 53.2002 | 120.7419 | 173.9421 | 0 | 234.6711 | 65.0249 | 215.5374 | 0 | 204.9897 | 75.5726
| Total Capex By Debt and equity | 1141.0622 | 608.3338 | 15.15 | 374.9655 | 8.1461 | 1381.4385 | 340.5531 | 1064.8792 | 1405.4323 | 0 | 603.3625 | 2183.5083 | 1898.1919 | 0 | 1130.5854 | 2951.1148
B | WORK EXECUTED BY GoO FUNDING | [5 empty] | 7: 1381.4345; Total 13: 2183.5083; Total 17: 2951.1148
142 | 220 kV Dc line from Nuapada to Pratapsasan | 33.58 | 3.1 |  |  |  | 36.68 | 4 | 0 | 4 |  | 40.67 | 0.01 |  |  |  | 0.01 |  | BGA
143 | 132/33 KV GIS S/S at Satyanagar & Badagada with associated UG cabling | 98.34 | 27.79 |  |  |  | 126.13 | 15.09 | 19.91 | 35 |  | 95 | 66.13 | 30 |  | 96.13 | 0 |  | BGA
144 | 220/33KV GIS S/S at Godisahi & Kantabada | 0 | 2.49 |  | 2.49 |  | 0 | 0.4 | 5 | 5.4 |  | 5.4 | 0 | 0.2 |  | 0.2 | 0 |  | BGA
145 | 220/132/33 KV GIS at Balianta with assoc. lines. | 62.4 | 36.07 |  |  |  | 98.47 | 29.1 | 22.43 | 51.53 |  | 60 | 90 | 5 |  | 94.99 | 0.01 |  | BGA
146 | Const. of 220/33KV GIS substation at Nayapalli | 65.51 | 27.04 |  | 92.55 |  | 1.4211e-14 | 6.88 | 4.5 | 11.38 |  | 11.38 | 1.4211e-14 | 0.2 |  | 0.2 | 1.4211e-14 |  | BGA
147 | Bay Extn at Kesura | 0.38 | 0.19 |  |  |  | 0.57 | 0.22 | 1.18 | 1.4 |  | 1.97 | 0 | 0.2 |  | 0.2 | 0 |  | BGA
148 | 132KV Balianta DC Line | 0 | 0.15 |  |  |  | 0.15 | 0 | 8 | 8 |  |  | 8.15 | 4 |  | 12.15 | 0 |  | BGA
149 | 132 KV UG Cable from Grid S/s Samagara to Grid S/s Puri. | 0.29 | 11.27 |  |  |  | 11.56 | 1.08 | 4.92 | 6 |  |  | 17.56 | 5 |  | 22.56 | 0 |  | BGA
150 | Construction of 132 KV DC Line from 132/33 KV GIS, Chandbali to Proposed 220/132/33 KV GSS, Dhamra at Balimunda |  | 0.77 |  | 0.77 |  | 7: 0; Projection For Balance Six Months 9: 2.53; Total 10: 2.53; Total 12: 2.53; Total 13: 0; Total 17: 0 |  | BGA
151 | Construction of 2x20 MVA 132/33 KV Grid S/s at Nawarangpur with associated 132 KV DC line for LILO arrangement of existing 132 KV Jayanagar - Tentulikhunti line | 4.01 | 0.21 |  | 4.22 |  | 7: 0; Projection For Balance Six Months 9: 1.48; Total 10: 1.48; Total 12: 1.48; Total 13: 0; Total 17: 0 |  | BGA
152 | Const. of 220 KV LILO line from 220/132KV grid substation, Balimela to Jaynagar LILO at Govindpali SC including bays. | 5.71 | 0.49 |  | 6.2 |  | 7: 0; Actual For First Six Months 8: 0.06; Projection For Balance Six Months 9: 0.8; Total 10: 0.86; Total 13: 0.86; Total 17: 0.86 |  | BGA
153 | Boudha - Phulbani RRCP Project(Executed by M/s SEL) | 44.79 | 0.73 |  |  |  | 45.52 | 18.51 | 2.49 | 21 |  | 66.52 | 0 | 1 |  | 1 | 0 |  | BGA
154 | Construction of boundry wall for jiridamali store at kamakhyanagar | 0.07 |  |  |  |  | 7: 0.07; Total 10: 0; Total 13: 0.07; Total 17: 0.07 |  | BGC
155 | 132 kv line from boudha S/s to phulbani | 0.1 |  |  |  |  | 7: 0.1; Total 10: 0; Total 13: 0.1; Total 17: 0.1 |  | BGA
156 | Dalabagha survey | 0.25 |  |  |  |  | 7: 0.25; Total 10: 0; Total 13: 0.25; Total 17: 0.25 |  | BGC
157 | survey work for 220 kv lilo line from duburi - MRDL DC line to 220/132 Kv grid S/s Dhenkanal-B | 0.43 |  |  |  |  | 7: 0.43; Total 10: 0; Total 13: 0.43; Total 17: 0.43 |  | BGC
158 | Const. of 220/33KV s/s and its associate line at Gopinathpur keonjhar(Short closed) | 2.41 |  |  |  |  | 7: 2.41; Total 10: 0; Total 13: 2.41; Total 17: 2.41 |  | BGC
159 | Const.of 220 KV line from TTPS Rengali to Chendipada | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 13: 0.03; Total 17: 0.03 |  | BGC
160 | 132 kv line from champua S/s | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 13: 0.03; Total 17: 0.03 |  | BGA
161 | 132 kv line from boinda s/s to atthamallik | 0.05 | 0 |  |  |  | 7: 0.05; Total 10: 0; Total 13: 0.05; Total 17: 0.05 |  | BGA
162 | 132 kv line from boudha s/s to atthamallik(Kiakata) | 0.06 |  |  |  |  | 7: 0.06; Total 10: 0; Total 13: 0.06; Total 17: 0.06 |  | BGA
163 | provision for abandoned/incomplete CWIPS | -2.77 |  |  |  |  | 7: -2.77; Total 10: 0; Total 13: -2.77; Total 17: -2.77 |  | BGC
164 | Diversion of existing 220 kv & 132 Kv line from the premises of TTPS /NTPC colony area talcher | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 |  | BGC
165 | Power supply to M/s BRG Steel | 0 |  |  |  |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 |  | BGC
166 | Power supply to M/s MCL at Kaniha | 0 |  |  |  |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 |  | BGC
167 | provision for abandooned/incomplete CWIPS | -0.77 |  |  |  |  | 7: -0.77; Total 10: 0; Total 13: -0.77; Total 17: -0.77 |  | BGC
168 | Construction of 132 KV D/C line from 400/220/132/33 KV Grid S/s at Lapanga to 132/33 KV GSS Brajarajnagar alongwith diversion of 220 KV DC IB-Budhipadar (1st line & 2nd line) |  | -1.823 |  | -1.823 |  | 0 | 0.506 | 0.3 | 0.806 |  | 0.806 | 0 |  |  |  | 0 |  | BGA
169 | 132KV DC line from 132/33KV Grid S/S R Udayagiri to 132/33KV Grid S/S at Paralakhemundi with 2Nos of feeder bay extention at both s/s (RRCP) | 40.82 | 0.96 |  |  |  | 41.78 | 0.01 | 3 | 3.01 |  |  | 44.79 | 15.5 |  |  | 60.29 |  | BGA
170 | 220 KV DC LILO line from 220 KV Narendrapur-Therubali DC line to 220/132/33 KV Grid S/s.Aska |  | 3.8 |  | 3.8 |  | 7: 0; Projection For Balance Six Months 9: 1.2; Total 10: 1.2; Total 13: 1.2; Total 17: 1.2 |  | BGA
171 | Construction of 132/33 KV Grid S/s GIS at Hinjilikatu, Ganjam |  | 0.53 |  | 0.53 |  | 7: 0; Actual For First Six Months 8: 0.75; Projection For Balance Six Months 9: 0.6; Total 10: 1.35; Total 13: 1.35; Total 17: 1.35 |  | BGA
172 | 2nd 132KV Feeder Bay at 132/33 KV Grid SS Padampur & 132 /33 KV Grid Ss Nuapada | 1.384 | 0.118 |  | 1.502 |  | 7: -2.2204e-16; Total 10: 0; Total 13: -2.2204e-16; Total 17: -2.2204e-16 |  | BGA
173 | 2*63 MVA, 132/33kv GIS at SCB Medical, Cuttack | [5 empty] | 0 | 90.37 | 66 | 156.37 |  |  | 156.37 | 10 |  | 166.37 | 0 |  | AGA
174 | Installation & Commissioning of 3rd 315MVA, 400/220 KV ICT along with construction of 1 no. 400KV DIA & 1 No. 220KV Transformer Bay with associated system at existing 400/220KV Grid Sub-station, New Duburi. (DRC Scheme) | 20.87 | 0.09 |  |  |  | 20.96 | 28.39 | 3.3 | 31.69 |  | 52.65 | 0 | 0.5 |  | 0.5 | 0 | DRC | BGA
175 | Replacement of old conductor with new HTLS conductor in 220KV Budhipadar-Lapanga DC line from Loc. No. 1 to Loc. No. 63 (old Loc. No. 50/8) under TL SD, Jharsuguda. (334697658/-) | [5 empty] | 0 |  | 0.1 | 0.1 |  |  | 0.1 | 32 |  | 32.1 | 0 | HCTUS | AGA
176 | Estimate for replacement of old ACSR/AAAC zebra conductor of 220KV Katapali -Lapanga D/C line to HTLS conductor with all accessories | [5 empty] | Projection For Balance Six Months 9: 30; Total 10: 30; Total 13: 30; Total 14: 50; Total 16: 80; Total 17: 0 | HCTUS | AGA
177 | Replacement of old twin AAAC moose conductor with twin HTLS conductor(Zebra equivalent) in existing 400KV IB-Lapanga D/C line along with upgradation in main and tie bayof IB circuit at Lapanga GSS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.83 | 0 | 97.83 | 0 | HCTUS | AGA
| Total of Const GoO Funding | 377.984 | 113.975 | 0 | 110.239 | 0 | 381.72 | 195.366 | 177.74 | 373.106 | 0 | 338.406 | 416.42 | 251.43 | 0 | 604.23 | 63.62
178 | Total O&M by GoO | 69.1319 | 30.137 | 0 | 5.71 | 0 | 93.5389 | 7.5531 | 31.9 | 39.4531 | 0 | 88.7192 | 44.2729 | 29.7336 | 0 | 43.9847 | 30.0218
179 | Total capex by GoO funding | 447.1159 | 144.112 | 0 | 115.949 | 0 | 475.2589 | 202.9191 | 209.64 | 412.5591 | 0 | 427.1252 | 460.6929 | 281.1636 | 0 | 648.2147 | 93.6418
C | Deposit Works | [5 empty] | 7: 475.2789; Total 13: 460.6929; Total 17: 93.6418
180 | Construction of 132 KV SC line(37KM) from existing 132 Grid S/S,Bangiriposi to Proposed RTSS at Bhanjpur & 2Nos. 132 KV feeder bay at 132/33 KV GSS Bangiriposi & Associated 132 KV 2 phase DC line(40KM) from GSS Bangiripsi to proposed 132 KV RTSS Bhanjapur. | 13.57 | 4.68 |  |  |  | 18.25 | 0.85 | 2.6 | 3.45 |  | 21.7 | 0 |  |  |  | 0 |  | BD
181 | RTSS Nayagarh | 7.51 | 2.78 |  | 0 |  | 10.29 | 0.74 | 1.76 | 2.5 |  | 12.77 | 0.02 | 2 |  | 2 | 0.02 |  | BD
182 | RTSS Mancheswar | [5 empty] | Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 |  | AD
183 | RTSS Jaleswar | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 5; Total 17: 5.03 |  | AD
184 | RTSS Balasore | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 5; Total 17: 5.03 |  | AD
185 | RTSS at Boinda(Only for forest clearance) | [5 empty] | 0 |  | 0.2 | 0.2 |  | 0.2 | 0 | 0.1 |  | 0.1 | 0 |  | AD
186 | RTSS at Champapur | [5 empty] | 7: 0; Projection For Balance Six Months 9: 2.5; Total 10: 2.5; Total 13: 2.5; Total 14: 10; Total 17: 12.5 |  | AD
187 | RTSS at Khamar |  | 0.07 |  |  |  | 0.07 | 0.05 | 4.95 | 5 |  |  | 5.07 | 20 |  |  | 25.07 |  | BD
188 | RTSS Dhanmandal | 7.7 |  |  |  |  | 7: 7.7; Projection For Balance Six Months 9: 2.5; Total 10: 2.5; Total 13: 10.2; Total 14: 0.3; Total 17: 10.5 |  | BD
189 | RTSS Charbatia | 11.31 | 5.63 |  |  |  | 16.94 | 5.08 | 0.4 | 5.48 |  | 22.42 | 0 | 0.2 |  | 0.2 | 0 |  | BD
190 | other deposit work | 0.78 |  |  |  |  | 7: 0.78; Total 10: 0; Total 13: 0.78; Total 17: 0.78 |  | BD
191 | 132 KV line from Jabamayeeto RTSS-Sukinda | 11.44 | 0.04 |  |  |  | 7: 11.48; Total 10: 0; Total 12: 11.48; Total 13: 0; Total 17: 0 |  | BD
192 | RTSS Barjamda and associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 14: 5; Total 17: 5.02 |  | AD
193 | RTSS Banspani & associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 14: 5; Total 17: 5.02 |  | AD
194 | RTSS Harichandanpur & associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 17: 0.02 |  | AD
195 | 220 KV Traction line from 220 /33 Kv Grid S/S Laxmipur to 220 / 25 KV RTSS Laxmipur. (Modification of 220 kV SC Line on DC Tower from location 05 to 07 of existing 220 kV RTSS Laxmipur Line. | 0 | 0.29 |  | 0.29 |  | 0 |  | 0.2 | 0.2 |  | 0.2 | 0 | 0.2 | 0 | 0.2 | 0 |  | BD
196 | 132KV 2Phase line from 132/33 KV Grid S/S Bhawanipatna to RTSS,Bhawanipatna |  | 0.2 |  | 0.2 |  | 0 | 0.67 | 0.1 | 0.77 |  | 0.1 | 0.67 | 0 | 0 | 0 | 0.67 |  | BD
197 | Construction of 2 nos. of 132 kV Towers and dismantling of one 132 kV Tower, third phase conductor stringing on existing RTSS Rayagada Line. | [5 empty] | 0 |  | 0.1 | 0.1 |  | 0 | 0.1 | 0.02 | 0 | 0.02 | 0.1 |  | AD
198 | Construction of 01 no. of 132KV Feeder bay extension at existing 132/33KV Grid S/S, Tirtol with associated 132 KV Transmission line on DC Towers from 132/33 KV Grid S/s , TIRTOL to RTSS, Gorekhnath | [5 empty] | Projection For Balance Six Months 9: 2; Total 10: 2; Total 13: 2; Total 14: 10; Total 17: 12 |  | AD
199 | Construction of 132 KV SC ( 2 phase) Traction line from existing 132 /33 KV Grid Bhawanipatna to proposed RTSS Lanjigarh along with one no 132 KV feeder bay exxtensison at 132/33 KV Grid Ssubss-station. Estt. No 11/2014-15 |  | 0.56 |  | 0.56 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | BD
200 | Construction of 132 KV SC line on DC Tower (Two Conductor) from U/C 220/132/33 KV Grid Sub-station, Gunupur to proposed RTSS, Palasingi and 132 KV feeder bay extension at 220/132/33KV Grid Sub-Station, Gunupur. |  | 0.29 |  | 0.29 |  | 0 |  | 0.55 | 0.55 |  | 0.55 | 0 | 0 | 0 | 0 | 0 |  | BD
201 | Const of 2no 33kv Bay at 220KV Grid sub-station Gobindapalli Avantika Work | 0.85 | 0.15 |  | 1 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 |  | BD
202 | Construction of 1No 33kv Bay at 220/33 kv Grid s/s Gobindapalli for megalift project at saradaput | 0.37 | 0.03 |  | 0.4 |  | 7: 0; Actual For First Six Months 8: 0.03; Total 10: 0.03; Total 12: 0.03; Total 13: 0; Total 17: 0 |  | BD
203 | Const of 2 nos of 33KV bay at GSS Boriguma for Shrabani Power Generation pvt ltd | 0.42 | 0 |  |  |  | 0.42 | 0.06 | 0.3 | 0.36 |  | 0.78 | 0 | 0.03 |  | 0.03 | 0 |  | BD
204 | Const of 2 nos of 33KV Bay at GSS Boriguma for Sidheswari Power Generation Pvt Ltd | [5 empty] | 0 | 0.01 | 0.3 | 0.31 |  | 0.31 | 0 | 0.03 |  | 0.03 | 0 |  | AD
205 | Abondoned CWIPS | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 |  | BD
206 | Abondoned CWIPS | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 |  | BD
207 | Provision for Abondoned CWIPS | -0.02 |  |  |  |  | 7: -0.02; Total 10: 0; Total 13: -0.02; Total 17: -0.02 |  | BD
208 | Const of 4 nos of 132KV AIS Bays at 132/25KV Manabar RTSS and 2 nos 132KV AIS Bays at 132/33KV Grid SS Sunabeda withassociated 132KV DC line from existing 132/33KV Grid SS Sunabeda to RTSS Manbar(line length=25.419Km) | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 17; Total 17: 27 |  | AD
209 | Construction of 220 KV LILO line from Loc. No. 125 & Loc. No. 126 of existing 220 KV Budhipadar to Tarkera line (CKT-II) and 132 KV LILO line from Loc. No. 291 of existing 132 KV Budhipadar to Tarkera line (CKT-II) and 220/132/33 KV Grid Sub-Station at Bamra. (50% Deposit Work) |  | 0.273 |  | 0.273 |  | 0 | 0.54 | 1.11 | 1.65 |  | 1.65 | 0 |  |  |  | 0 |  | BD
210 | Construction of 220 KV 2 phase line on DC tower from 220/33 KV Bonai Grid S/s to RTSS Bimalagarh & Associted one no. 220 KV Feeder bay at 220/33 KV Grid S/s for Power | [5 empty] | 7: 0; Actual For First Six Months 8: 0.13; Total 10: 0.13; Total 12: 0.13; Total 13: 0; Total 17: 0 |  | AD
211 | Construction of 220 KV SC line on DC tower from 220/33 KV GSS Bonai to Taldih Iron Ore Mines, SAIL on deposit work basis. | 4.024 | 8.479 |  |  |  | 12.503 | 10.35 | 15 | 25.35 |  |  | 37.853 | 22 |  | 59.853 | 0 |  | BD
212 | 132KV Transmission line from proposed 220/132/33 KV Grid Sub-Station at Bamra to Proposed RTSS Dhutura | 15.832 | -0.024 |  |  |  | 7: 15.808; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 16.308; Total 14: 5; Total 17: 21.308 |  | BD
213 | 132KV Transmission line from proposed 220/132/33 KV Grid Sub-Station at Bamra to Proposed RTSS Garposh | 6.755 |  |  |  |  | 7: 6.755; Projection For Balance Six Months 9: 2; Total 10: 2; Total 13: 8.755; Total 14: 5; Total 17: 13.755 |  | BD
214 | 132 KV S/c (2 Conductor) line from 220/132/33 Grid S/s Lapanga to RTSS Rengali & associated 1 nos 132 KV Feeder bay extension at Lapange Grid S/s. Est. No. 06/2014-15 |  | 0.068 |  | 0.068 |  | 7: 0; Projection For Balance Six Months 9: 0.1; Total 10: 0.1; Total 12: 0.1; Total 13: 0; Total 17: 0 |  | BD
215 | Diversion of 132 KV D/C Line from Loc. No. 9 to Loc No. 12 of 132KV CPP-II (NSPCL, Rourkela) to MSDS-V, SAIL, RSP line along with connecting the line to the new bay |  | 0.09 |  | 0.09 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 |  | BD
216 | Diversion of (1) 132KV D/C Lapanga Brajrajnagar Line and (2) 220KV D/C Aditya Aluminium-Budhipadar Line from the proposed power plant & Ash pond area of M/s. NLC at Thelkoloi, Sambalpur | 2.2 | 10.041 |  |  |  | 12.241 | 10.69 | 18 | 28.69 |  |  | 40.931 | 12 |  | 52.931 | 0 |  | BD
217 | Diversion-cum-heightening of 400 KV D/C IB-Lapanga line from Loc. No. 22 to Loc. No. 23 and from Loc. No. 28 to Loc. No. 30 for under passing of proposed diversion of 132 KV D/C Lapanga-Brajrajnagar line and 220 KV Budhipadar-Aditya Aluminium line. | 0.303 | 0.008 |  |  |  | 7: 0.311; Total 10: 0; Total 13: 0.311; Total 16: 0.311; Total 17: 0 |  | BD
218 | Two nos of 400 KV feeder bay extension at Lapanga for connectivity of 400 KV D/C NLC - Lapanga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 |  | AD
219 | 400 KV D/C NLC - Lapanga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 10; Total 17: 10.03 |  | AD
220 | Construction of 220 KV Barkote-RTSS, Barkote line along with associated one no. of 220 KV Feeder bay at 220/33 KV GSS at Barkote. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.06; Total 10: 0.06; Total 13: 0.06; Total 14: 2; Total 17: 2.06 |  | AD
221 | Construction of 132 KV D/C Kuarmunda-RTSS, Bondamunda line along with associated two nos of 132 KV Feeder bay extension at 220/132/33 KV GSS at Kuarmunda. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.08; Total 10: 0.08; Total 13: 0.08; Total 14: 2; Total 17: 2.08 |  | AD
222 | Diversion of 220KV Narendrapur TATA MRSS Line from 220/132/33KV Grid SS Narendrapur to MS TATA Steel Ltd atnew NH 59 | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.5; Total 10: 1.5; Total 13: 1.5; Total 16: 1.5; Total 17: 0 |  | AD
223 | 220KV DC Line from GSS Dasapalla to RTSS BUGUDA | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 3; Total 17: 6 |  | AD
224 | 132kV Transmission Line from 132/33 kV Grid S/S at Rairangpur to proposed RTSS,Rairangpur with 1no. 132 KV Feeder Bay extension at 132/33 KV Grid S/S,Rairangpur (Approx. Line Length-10.523 K.M.) (RVNL Deposit Work) | 7.13 | 0.24 |  |  |  | 7.37 | 0.01 | 1.44 | 1.45 |  | 8.82 | 0 | 0.5 |  | 0.5 | 0 |  | BD
225 | 01 No 33KV feeder Bay Extention at 132/33 GSS BHATLI For GANGADHAR MEHER LIFT IRRIGATION PROJECT |  | 0.56 |  | 0.56 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 |  | BD
226 | 132 KV two phase SC line from existing 132/33 KV GSS, Sonepur to proposed RTSS Sonepur and 1. Nos 132kv feeder bay extension at 132/33 KV GSS sonepur | 1.601 | 2.83 |  |  |  | 4.431 | 1.97 | 2.5 | 4.47 |  | 8.902 | -0.001 | 1 |  |  | 0.999 |  | BD
227 | Construction of BPCL BHATLI LINE BIO ETHANOL | 5.345 | -4.41 |  | 0.93 |  | 7: 0.005; Total 10: 0; Total 13: 0.005; Total 17: 0.005 |  | BD
| Total of Const Deposit Works | 97.14 | 32.875 | 0 | 4.661 | 0 | 125.354 | 31.18 | 73.9 | 105.08 | 0 | 90.142 | 140.292 | 162.38 | 0 | 117.675 | 184.997
| Total O&M Deposit work | 27.0681 | 37.6167 | 0 | 16.6722 | 0 | 48.0326 | 26.4289 | 77.6555 | 104.0844 | 0 | 43.0929 | 109.0241 | 219.56 | 0 | 195.01 | 133.5741
| Total Capex by deposit Work | 124.2081 | 70.4917 | 0 | 21.3332 | 0 | 173.3866 | 57.6089 | 151.5555 | 209.1644 | 0 | 133.2349 | 249.3161 | 381.94 | 0 | 312.685 | 318.5711
| GRAND TOTAL | 1712.3862 | 822.9375 | 15.15 | 512.2477 | 8.1461 | 2030.084 | 601.0811 | 1426.0747 | 2027.1559 | 0 | 1163.7225 | 2893.5173 | 2561.2955 | 0 | 2091.4851 | 3363.3278
| OWN | 1141.0622 | 608.3338 | 15.15 | 374.9655 | 8.1461 | 1381.4385 | 340.5531 | 1064.8792 | 1405.4323 | 0 | 603.3625 | 2183.5083 | 1898.1919 | 0 | 1130.5854 | 2951.1148
| GRANT | 447.1159 | 144.112 | 0 | 115.949 | 0 | 475.2589 | 202.9191 | 209.64 | 412.5591 | 0 | 427.1252 | 460.6929 | 281.1636 | 0 | 648.2147 | 93.6418
| DEPOSIT | 124.2081 | 70.4917 | 0 | 21.3332 | 0 | 173.3866 | 57.6089 | 151.5555 | 209.1644 | 0 | 133.2349 | 249.3161 | 381.94 | 0 | 312.685 | 318.5711
|  | 1712.3862 | 822.9375 | 15.15 | 512.2477 | 8.1461 | 2030.084 | 601.0811 | 1426.0747 | 2027.1559 | 0 | 1163.7225 | 2893.5173 | 2561.2955 | 0 | 2091.4851 | 3363.3278
| Debt | [5 empty] | Total 10: 983.8026; Total 14: 1328.7343
| Equity | [5 empty] | Total 10: 421.6297; Total 14: 569.4576
| Construction | [5 empty] | Actual For First Six Months 8: 497.126; Projection For Balance Six Months 9: 1116.07; Total 10: 1613.196; Total 14: 1888.45; Total 15: 0; Total 16: 1436.846
| O&M | [5 empty] | Total 14: 464.831; Total 15: 0; Total 16: 443.9844
| Civil | [5 empty] | Total 14: 63.4845; Total 15: 0; Total 16: 108.7647
| Telecom | [5 empty] | Total 14: 66.44; Total 15: 0; Total 16: 85.8
| IT | [5 empty] | Total 14: 78.09; Total 15: 0; Total 16: 16.09
| TOTAL | [5 empty] | Total 14: 2561.2955; Total 15: 0; Total 16: 2091.4851

## As on 31.03.2025
CWIP position as on 31.03.2025
[16 empty] | OERC | FORM F-2
Rs. in Crores
Sl No. | Description of the Project/Scheme | PREVIOUS YEAR(2024-25) | [5 empty] | CURRENT YEAR(2025-26) | [5 empty] | ENSUING YEAR(2026-27)
|  | OB as on 01.04.24 | Exp. during the year | Interest during construction | Transfer to fixed assets | Other Adjustment | Closing balance of WIP as on 31.03.25 | Expenditure during the year |  |  | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.26 | Exp. during the year | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.27 | Remark | Loan Amount/Sanctioned | Remarks
[8 empty] | Actual For First Six Months | Projection For Balance Six Months | Total
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A. With Investment approval from the Commission (Rs. 10 Cr. or more)
CONSTRUCTION-Own Contribution (Debt:Equity)
3 | 220/33 KV Sub-Station at Mundamba | 0 | 0.03 |  |  |  | 0.03 | 12.15 | 17.85 | 30 |  |  | 30.03 | 20 |  |  | 50.03 | OTSSP-II | BEA
7 | Constn. of 2x20 MVA 132/33KV GRID S/S, CHANDIPUR & ASSOCIATED 132 KV LILO (FROM EXISTING 132KV SORO-BALASORE S/C Line) SCHEME |  | 1.4 |  | 1.4 |  | 0 | 0.79 | 1.75 | 2.54 |  | 2.54 | 0 | 0.1 |  | 0.1 | 0 | JICA | BEA
8 | Construction of 2nd Circuit of 132 KV Bhadrak-Anadpur Line from 220/132/33 KV grid S/S,Bhadrak to 132/33 KV Grid S/S,Anadpur with One No. Feeder bay extention at both ends | 5.01 | 3.3 |  |  |  | 8.31 | 0.41 | 1.59 | 2 |  | 10.31 | 0 | 0.37 |  | 0.37 | 0 | RRCP-I | BEA
9 | Construction 2x500 MVA, 400/220 GIS at Ramakrushnapur along with Associated 400 KV (4.642 RKMs.) & 220 KV (38.194 KMs.) LILO. | 6.05 |  |  |  |  | 7: 6.05; Total 10: 0; Total 12: 6.05; Total 13: 0; Total 17: 0; Total 18: DRPS-II | BEA
10 | Const. Of 132 KV SC line for proposed Grid S/S Balimunda( Dhamara) to existing 132/33 KV s/s Olaver. | 0.16 |  |  |  |  | 7: 0.16; Total 10: 0; Total 12: 0.16; Total 13: 0; Total 17: 0; Total 18: 30% Gov/UCO Bank | BEA
13 | Const. of 2X12.5MVA 132/33 KV Grid S/S Basta with associated line. | 0.05 |  |  |  |  | 7: 0.05; Total 10: 0; Total 12: 0.05; Total 13: 0; Total 17: 0; Total 18: own | BEA
14 | Const. Of 132 KV SC line from existing 400/220/132 KV (PGCIL) Grid S/S Kuchei to Grid S/S Rairangpur. | 0.1 |  |  |  |  | 7: 0.1; Total 10: 0; Total 12: 0.1; Total 13: 0; Total 17: 0; Total 18: own | BEA
15 | Constn. Of one No 132/33 KV Bay at Kuchei End (PGCIL) | 4.78 | 0.02 |  | 4.8 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: own | BEA
16 | Const of 2*500MVA 400/220 KV GSS Ramakrishnapur | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5; Total 18: DRPS-II | BEA
17 | Construction of 132kv Lamtaput LILO lne from 132 KV Podagada -Pottangi line with 2No Bay extention at Lamtaput Grid s/s |  | 0.08 |  |  |  | 0.08 | 0.01 | 5 | 5.01 |  |  | 5.09 | 10 |  |  | 15.09 | Special EFC | BEA
19 | Const. of 220/33 KV Grid S/s at Govindapalli with LILO of 220 KV SC line from Balimela to Malkangiri. |  | 15.62 |  | 15.62 |  | 7: 0; Actual For First Six Months 8: 1.32; Projection For Balance Six Months 9: 2.39; Total 10: 3.71; Total 13: 3.71; Total 17: 3.71; Total 18: JICA | BEA
20 | Construction of 132/33 KV Grid S/s at Boriguma with LILO of existing 132 KV SC line from 220/132KV grid substation, Jaynagar to 132/33KV grid substation, Tentulikhunti. | 30.92 | 0.27 |  | 31.19 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: E-300 | BEA
23 | Construction of 132KV DC line from Sunabeda to 220/132/33KV grid substation Jayanagar with bay extension at each end. Est.No. 17/2012-13 | 29.82 | 1.18 | 0.43 | 31.43 |  | 7: 0; Projection For Balance Six Months 9: 1.8; Total 10: 1.8; Total 12: 1.8; Total 13: 0; Total 17: 0; Total 18: 40%Gov/Union bank | BEA
25 | GSS Pottangi |  | 0.9 |  | 0.9 |  | 7: 0; Projection For Balance Six Months 9: 0.65; Total 10: 0.65; Total 12: 0.65; Total 13: 0; Total 17: 0; Total 18: E-300 | BEA
26 | Construction of 2x20MVA 220/33KV Grid S/s at KALIMELA with associated 220KV SC line on DC tower from Malkangiri S/s to the proposed Kalimela S/s with one no offedder bay extension at Malkangiri. | [5 empty] | 7: 0; Actual For First Six Months 8: 0.05; Total 10: 0.05; Total 12: 0.05; Total 13: 0; Total 17: 0; Total 18: E-250 | BEA
27 | Construction of 2x20 MVA, 220/33 KV Grid S/s at Malkanagiri with associated 220 KV SC line on DC tower from Balimela S/s to proposed Malkangiri S/s with one bay extension. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.5; Total 10: 1.5; Total 13: 1.5; Total 17: 1.5; Total 18: E-300 | BEA
30 | Construction of 220/132/33 KV grid S/s at kiakata(Executed by M/s TPL) | 153.44 | 1.37 | 4.19 |  |  | 159 | 1.72 | 8 | 9.72 |  |  | 168.72 | 1 |  | 169.72 | 0 | JICA | BEA
31 | 132/33 KV GSS at Athamallik and Associated lines(Executed by M/s MBH Power) | 13.95 | 11.63 |  |  |  | 25.58 | 1.4 | 9.1 | 10.5 |  | 36.08 | 0 | 2 |  | 2 | 0 | LVMS | BEA
33 | Diversion of one no. of 400KV and 4 nos. of 220Kv line with 220KV lilo arrangement for connectivity with 400/220KV GIS Meramunduli-B(executed by AK Das) | 29.51 | 0.5 |  |  |  | 30.01 | 0.14 | 1.86 | 2 |  |  | 32.01 | 10 |  |  | 42.01 | SACI | BEA
34 | 2*40 MVA, 220/33 KV GSS with SAS at Janhapada, Parjang(Executed by M/s Empower Trans) |  | 19.13 |  |  |  | 19.13 | 1.39 | 12.69 | 14.08 |  |  | 33.21 | 1.32 |  | 34.53 | 0 | OTSSP-I | BEA
35 | Aluminium Park(Executed by M/s SEL) | [5 empty] | 0 | 0.94 | 14.06 | 15 |  |  | 15 | 30 |  |  | 45 | OTSSP-II | BEA
36 | 220/132/33 KV GSS at Chhendipada and Associated lines(Executed by M/s APS) | 6.36 | 5.61 |  |  |  | 11.97 | 11.15 | 13.85 | 25 |  |  | 36.97 | 20 |  |  | 56.97 | OTSSP-II | BEA
38 | 440/220/33 KV GSS at Neulapoi, Dhenkanal |  | 0.26 |  |  |  | 7: 0.26; Total 10: 0; Total 13: 0.26; Total 17: 0.26; Total 18: OTSSP-II | BEA
39 | 2x20 MVA, 220/33 Grid S/s near Deogarh along with associated LILO arrangement from 220 KV Rengali-Tarkera Transmission Line. |  | 0.093 |  | 0.093 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: JICA | BEA
40 | Construction of 132/33 KV Grid S/S at Lakhanpur alongwith associated Transmission line from Brajrajnagar. |  | 5.437 |  | 5.437 |  | 0 |  | 0.1 | 0.1 |  | 0.1 | 0 | 0.1 |  | 0.1 | 0 | JICA | BEA
41 | Construction of 2x20 MVA, 132/33 KV Grid S/s at Hirakud with GIS along with associated 132 KV LILO lind from existing 132 KV Burla-Lapanga line & existing 132 KV ALCO line. Est. Cost-11/2017-18 |  | 0.003 |  | 0.003 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: E-140 | BEA
42 | Const. of 400/220 KV Grid S/S at Lapanga | 0.467 |  |  |  |  | 7: 0.467; Total 10: 0; Total 12: 0.467; Total 13: 0; Total 17: 0; Total 18: E-250 | BEA
43 | Const of 2 x 100MVA 220/132/33 KV Grid S/S at Kuanrmunda with LILO arrangement from existing 220KV Budhipadar Tarkera DC Line |  | 0.519 |  | 0.519 |  | 0 | 1.6 | 6.69 | 8.29 |  | 8.29 | 0 |  |  |  | 0 | E-300 | BEA
44 | Construction of 132 KV LILO Line from one ckt of 132 KV Budhipadar-Sundargarh DC line with construction of 132 KV feeder bay at 220/132/33 KV Grid S/s Bamra. (Approx. line length-45 KM) | 6.191 | 6.828 |  |  |  | 13.019 | 3.14 | 11.08 | 14.22 |  |  | 27.239 | 6 |  | 33.239 | 0 | RRCP-II | BEA
45 | Construction of 132KV LILO Line from 132 KV Chhend-Shri Ganesh Metaliks Circuit (Between Loc. No. 50 to 53) to 220/132/33 KV GSS, Kuanrmunda. | 1.109 | 0.212 |  | 1.321 |  | 7: 0; Actual For First Six Months 8: 0.05; Total 10: 0.05; Total 12: 0.05; Total 13: 0; Total 17: 0; Total 18: RRCP-II | BEA
46 | Construction of 220 KV LILO line from Loc. No. 125 & Loc. No. 126 of existing 220 KV Budhipadar to Tarkera line (CKT-II) and 132 KV LILO line from Loc. No. 291 of existing 132 KV Budhipadar to Tarkera line (CKT-II) and 220/132/33 KV Grid Sub-Station at Bamra. (50% Own Work) |  | 0.273 |  | 0.273 |  | 0 | 0.54 | 1.11 | 1.65 |  | 1.65 | 0 |  |  |  | 0 | OTSSP-II | BEA
60 | 220/132 kv SS DASPALLA with 220 kv LILO from Bhanjanagar to Meramundali line under JICA project | 53.19 | 1.43 | 1.55 |  |  | 7: 56.17; Projection For Balance Six Months 9: 22; Total 10: 22; Total 13: 78.17; Total 14: 15; Total 17: 93.17; Total 18: JICA | BEA
61 | 2*40 mva 220/33 KV grid SS at Baliguda and 220 kv line from Kesinga to Baliguda | 128.29 | 1.03 | 3.85 |  |  | 133.17 | 4.15 | 37 | 41.15 |  |  | 174.32 | 32.5 |  |  | 206.82 | E-300 | BEA
62 | 2*20 mva 132/33 kv SS at R UDAYGIRI with 132 kv line from MOHANA to R UDAYGIRI | 54.75 | 8.67 |  | 3.32 |  | 60.1 | 0.2 | 1 | 1.2 |  |  | 61.3 | 0.25 |  |  | 61.55 | E-300 | BEA
66 | 220 KV DC line N.Pur-Atri to TSSEZ at Gopalpur | [5 empty] | 0 | 0.08 | 10 | 10.08 |  |  | 10.08 | 30 |  |  | 40.08 | GEETC | BEA
67 | GSS Badakushastali | [5 empty] | 7: 0; Actual For First Six Months 8: 0.29; Total 10: 0.29; Total 13: 0.29; Total 14: 14; Total 17: 14.29; Total 18: GEETC | BEA
69 | 2X160MVA, 220/132kV and 2X20MVA, 220/33kV Grid S/S, Turumunga with associated 220kV & 132kV line. (JICA) | 93.33 | 12.98 | 0.8 |  |  | 107.11 | 3.29 | 4 | 7.29 |  | 114.4 | 0 |  |  |  | 0 | JICA | BEA
70 | 220kV LILO line from one circuit of existing 220kV TTPS-JODA D/C Line (Circuit-II) to 220/33kV GIS Substation, Keonjhar | 9.26 |  |  |  |  | 9.26 | 0.1 | 3 | 3.1 |  |  | 12.36 | 9 |  | 21.36 | 0 | OWN | BEA
71 | 2 nos. 220KV Bay extension at 220/33KV GIS Substation at Keonjhar on Turnkey Basis | 7.49 | 0.77 |  |  |  | 8.26 |  | 0.5 | 0.5 |  | 8.76 | 0 | 0.2 |  | 0.2 | 0 | E-250 | BEA
75 | Construction of 132 KV DC Line on DC Tower from 220/132/33 KV Grid S/S at Jayapatna(Baner) to 132/33 KV Grid S/S at Junagarh, Construction of 2 Nos of 132 KV Feeder Bay extention at 132/33KV Grid S/S Junagarh and 2 Nos of 132 KV feeder bay Extension at Jayapatna. | 7.94 | 0.87 | 2.03 |  |  | 7: 10.84; Actual For First Six Months 8: 0.01; Total 10: 0.01; Total 13: 10.85; Total 14: 5; Total 17: 15.85; Total 18: E-140 | BEA
76 | Construction of 132/33 KV Grid S/S At Brundabahal & its associated 132 KV LILO Transmission Line | 27.45 | 1.49 |  | 28.94 |  | 7: -3.5527e-15; Projection For Balance Six Months 9: 5; Total 10: 5; Total 13: 5; Total 14: 3; Total 17: 8; Total 18: Equity-Brundabahal(100%Equity) | BEA
77 | Construction of 220/33KV, 2x20MVA grid sub station near Kashipur with associated 220KVLILO line from existing 220KV Indravati-Theruvalli DC line to proposed grid sub-station. | [5 empty] | 7: 0; Actual For First Six Months 8: 0.65; Total 10: 0.65; Total 13: 0.65; Total 17: 0.65; Total 18: E-300 | BEA
78 | Construction of 220/132/33 KV Grid S/s at Gunupur with 220 KV LILO arrangement from existing 220 KV Theruvalli- Narendrapur Ckt-I and 132 KV Lilo arrangement from existing 132 KV Akhusingh-Paralakhemundi line. |  | 0.89 |  | 0.89 |  | 0 | 0.23 | 1.5 | 1.73 |  |  | 1.73 | 5 |  |  | 6.73 | JICA | BEA
79 | Construction of 132KV SC line on DC tower from existing loc no-170 of Akhusingh-Paralakhemundi line to proposed Loc No-41 of RTSS Palasingh line, in rayagada district of Odisha. | 2.37 | 1.56 |  | 3.93 |  | 7: 0; Projection For Balance Six Months 9: 0.52; Total 10: 0.52; Total 13: 0.52; Total 17: 0.52; Total 18: OWN | BEA
90 | 132/33 KV Grid S/S Bhatli & Associated Line | 50.654 | -1.496 |  | 49.158 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: E-140 | BEA
92 | 132/33 KV Grid S/S Thuapali (Deshbhatli) & Associated Line |  | 0.8 |  | 0.8 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: JICA | BEA
95 | 2X40 MVA,220/33 KV AIS Grid S/S, Madanpur Rampur Along with its associated 220KV LILO line of 220KV Kesinga-Baliguda DC Line | 0.089 | -0.153 |  |  |  | -0.064 | 2.67 | 21 | 23.67 |  |  | 23.606 | 17.27 |  | 40.876 | 0 | LVMS | BEA
96 | Construction of 220/33 KV Srid SS at Sarasmal Rampur |  | 0.084 |  |  |  | 0.084 | 0.22 | 0.5 | 0.72 |  |  | 0.804 | 15 |  |  | 15.804 | OTSSP-I | BEA
97 | 132/33 KV Grid S/S TARBHA | 8.527 | 2.83 |  |  |  | 11.357 | 3.75 | 6.15 | 9.9 |  |  | 21.257 | 10 |  | 25.257 | 6 | E-Tarbha | BEA
98 | 2X20 MVA, 132/33 KV GSS with SAS, Rampur at Agalpur with associated 132 KV LILO Line | 2.839 | 20.08 |  |  |  | 22.919 | 4.71 | 3.3 | 8.01 |  | 30.929 | 0 | 2 |  |  | 2 | LVMS | BEA
99 | 2X20 MVA, 132/33 KV GSS with SAS, JHARBANDH with associated 132 KV LILO Line | 1.259 | 3.557 |  |  |  | 4.816 | 3.24 | 27.25 | 30.49 |  |  | 35.306 | 10 |  | 39.306 | 6 | OTSSP-I | BEA
100 | 2X40 MVA, 132/33 KV GSS with SAS, Bijepur with associated 132 KV LILO Line | 0.436 | 5.923 |  |  |  | 6.359 | 1.81 | 8.5 | 10.31 |  | 16.669 | 0 | 10 |  | 10 | 0 | OTSSP-I | BEA
101 | Construction of 132 KV SC Line on DC Tower from 132/33 KV GSS Patnagarh to 132/33KV GSS Kantabanji with 132 KV Bay Extention at both GSS patnagarh and GSS kantabanji | 4.85 | 6.62 |  |  |  | 11.47 | 1.67 | 6.1 | 7.77 |  |  | 19.24 | 5 |  | 24.24 | 0 | RRCP-II | BEA
102 | Construction of 132 KV SC Line on DC Tower from 132/33 KV GSS Padampur to 132/33KV GSS Ghens | 9.195 | 6.438 |  |  |  | 15.633 | 0.65 | 2.6 | 3.25 |  |  | 18.883 | 5 |  | 23.883 | 0 | RRCP-II | BEA
109 | Construction of 220/33KV grid sub-station at Balichandrapur (Palei) with associated lines. | 30.89 | 18.54 | 0.36 | 49.79 |  | 7: 0; Actual For First Six Months 8: 6.66; Total 10: 6.66; Total 12: 6.66; Total 13: 0; Total 17: 0; Total 18: E-140 | BEA
110 | Construction of 132/33 KV Grid S/s at Bahugram with associated 132 KV line. Est. No. 07/2016-17 | [5 empty] | 0 | 0 | 0.1 | 0.1 |  | 0.1 | 0 |  |  |  | 0 | JICA | BEA
120 | Const of 400 KV S/S at Ersama | 12.41 | 86.61 |  |  |  | 99.02 | 17.31 | 39.69 | 57 |  |  | 156.02 | 30 |  |  | 186.02 | E-Paradeep | BEA
121 | 400 KV DC Line at Ersama | 25.73 | 31.37 |  |  |  | 57.1 | 27.01 | 55.99 | 83 |  |  | 140.1 | 70 |  |  | 210.1 | E-Paradeep | BEA
122 | Const of 220 KV DC Line at Ersma | 99.14 | 55.72 |  |  |  | 154.86 | 24.33 | 24.67 | 49 |  |  | 203.86 | 50 |  |  | 253.86 | E-Paradeep | BEA
124 | STAMS-I | [5 empty] | Actual For First Six Months 8: 101; Projection For Balance Six Months 9: 93; Total 10: 194; Total 13: 194; Total 14: 54; Total 16: 248; Total 17: 0 | BEA
127 | Engineering, supply, Erection and commissioning of 2 x 160 MVA (220/132 KV),2 X 40 MVA (132/33 KV), 220/132/33 KV GRID S/S, With SAS at BALIMUNDA,Dhamra and 220 KV LILO Line from From Loc.No.277 of existing 220KV Duburi- Balasore Ckt-I line to proposed sub-station at Balimunda (Approx. line length-34.890 Kms) on “EPC/Turnkey CONTRACT BASIS”. |  | 0.12 |  | 0.12 |  | 0 | 4.46 | 0.89 | 5.35 |  | 5.35 | 0 |  |  |  | 0 | Equity-140 | BEA
129 | Const of 2X20MVA 132/33KV Grid SS Raighar with LILO line dabugaon-umerkote to Raighar [Boundary Wall] | 0.62 | 1.48 |  |  |  | 2.1 | 5.64 | 40.35 | 45.99 |  |  | 48.09 | 16 |  |  | 64.09 | OTSSP-I | BEA
130 | Construction of 2x20 MVA 132/33 KV Grid S/s at Lamtaput with associated 132 KV LILO line from 132 KV Machkund PH Machkund RTSS line | 24.31 | 3.38 | 1.94 |  |  | 29.63 | 4.42 | 1.5 | 5.92 |  |  | 35.55 | 6 |  | 41.55 | 0 | E-140 | BEA
131 | Const. of 132KV SC line from proposed 132/33 grid S/s Pottangi to porposed 132/33KVgrid s/s Podagada with bay extension at both end. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.2; Total 10: 0.2; Total 13: 0.2; Total 17: 0.2; Total 18: Special EFC | BEA
132 | Boundary wall for 220/33 KV GSS at Jahnapada,Parjang | 0.34 |  |  |  |  | 7: 0.34; Total 10: 0; Total 13: 0.34; Total 17: 0.34; Total 18: OTSSP-I | BEA
133 | const.of 220/132 s/s at chendipada NISA | 0.14 |  |  |  |  | 7: 0.14; Total 10: 0; Total 13: 0.14; Total 17: 0.14; Total 18: OTSSP-II | BEA
134 | 2X 50MVA 132/33 KV GIS S/S at Autonagar | 0.01 |  |  |  |  | 0.01 | 0.36 | 0.05 | 0.41 |  |  | 0.42 | 75 |  |  | 75.42 | DRPS-II | BEA
135 | 132 KV UG cable from Narendrapur to Berhampur |  | 64.25 |  |  |  | 64.25 | 1.67 | 11.71 | 13.38 |  |  | 77.63 | 8 |  |  | 85.63 | DRPS-II | BEA
136 | GSS Gopalpur with line from narendrapur Atri | [5 empty] | 7: 0; Projection For Balance Six Months 9: 11; Total 10: 11; Total 13: 11; Total 14: 30; Total 17: 41; Total 18: GEETC | BEA
137 | 132kV DC line between existing 220/132/33Kv Grid Substion Turumunga and 132/33kV Dhenkikote Substation (Approx. Line Length-42.52 Km) with 2 nos. 132kV feeder bay extension at both end. (LVMS Scheme) | 0.55 | 1.41 |  |  |  | 7: 1.96; Actual For First Six Months 8: 0.59; Projection For Balance Six Months 9: 2.41; Total 10: 3; Total 13: 4.96; Total 14: 8; Total 17: 12.96 | BEA
WORK EXECUTED BY GoO FUNDING
142 | 220 kV Dc line from Nuapada to Pratapsasan | 33.58 | 3.1 |  |  |  | 7: 36.68; Actual For First Six Months 8: 4; Projection For Balance Six Months 9: 0; Total 10: 4; Total 12: 40.67; Total 13: 0.01; Total 17: 0.01 | BGA
143 | 132/33 KV GIS S/S at Satyanagar & Badagada with associated UG cabling | 98.34 | 27.79 |  |  |  | 126.13 | 15.09 | 19.91 | 35 |  | 95 | 66.13 | 30 |  | 96.13 | 0 |  | BGA
144 | 220/33KV GIS S/S at Godisahi & Kantabada | 0 | 2.49 |  | 2.49 |  | 0 | 0.4 | 5 | 5.4 |  | 5.4 | 0 | 0.2 |  | 0.2 | 0 |  | BGA
145 | 220/132/33 KV GIS at Balianta with assoc. lines. | 62.4 | 36.07 |  |  |  | 98.47 | 29.1 | 22.43 | 51.53 |  | 60 | 90 | 5 |  | 94.99 | 0.01 |  | BGA
146 | Const. of 220/33KV GIS substation at Nayapalli | 65.51 | 27.04 |  | 92.55 |  | 1.4211e-14 | 6.88 | 4.5 | 11.38 |  | 11.38 | 1.4211e-14 | 0.2 |  | 0.2 | 1.4211e-14 |  | BGA
147 | Bay Extn at Kesura | 0.38 | 0.19 |  |  |  | 0.57 | 0.22 | 1.18 | 1.4 |  | 1.97 | 0 | 0.2 |  | 0.2 | 0 |  | BGA
148 | 132KV Balianta DC Line | 0 | 0.15 |  |  |  | 0.15 | 0 | 8 | 8 |  |  | 8.15 | 4 |  | 12.15 | 0 |  | BGA
149 | 132 KV UG Cable from Grid S/s Samagara to Grid S/s Puri. | 0.29 | 11.27 |  |  |  | 11.56 | 1.08 | 4.92 | 6 |  |  | 17.56 | 5 |  | 22.56 | 0 |  | BGA
150 | Construction of 132 KV DC Line from 132/33 KV GIS, Chandbali to Proposed 220/132/33 KV GSS, Dhamra at Balimunda |  | 0.77 |  | 0.77 |  | 7: 0; Projection For Balance Six Months 9: 2.53; Total 10: 2.53; Total 12: 2.53; Total 13: 0; Total 17: 0 | BGA
151 | Construction of 2x20 MVA 132/33 KV Grid S/s at Nawarangpur with associated 132 KV DC line for LILO arrangement of existing 132 KV Jayanagar - Tentulikhunti line | 4.01 | 0.21 |  | 4.22 |  | 7: 0; Projection For Balance Six Months 9: 1.48; Total 10: 1.48; Total 12: 1.48; Total 13: 0; Total 17: 0 | BGA
152 | Const. of 220 KV LILO line from 220/132KV grid substation, Balimela to Jaynagar LILO at Govindpali SC including bays. | 5.71 | 0.49 |  | 6.2 |  | 7: 0; Actual For First Six Months 8: 0.06; Projection For Balance Six Months 9: 0.8; Total 10: 0.86; Total 13: 0.86; Total 17: 0.86 | BGA
153 | Boudha - Phulbani RRCP Project(Executed by M/s SEL) | 44.79 | 0.73 |  |  |  | 45.52 | 18.51 | 2.49 | 21 |  | 66.52 | 0 | 1 |  | 1 | 0 |  | BGA
155 | 132 kv line from boudha S/s to phulbani | 0.1 |  |  |  |  | 7: 0.1; Total 10: 0; Total 13: 0.1; Total 17: 0.1 | BGA
160 | 132 kv line from champua S/s | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 13: 0.03; Total 17: 0.03 | BGA
161 | 132 kv line from boinda s/s to atthamallik | 0.05 | 0 |  |  |  | 7: 0.05; Total 10: 0; Total 13: 0.05; Total 17: 0.05 | BGA
162 | 132 kv line from boudha s/s to atthamallik(Kiakata) | 0.06 |  |  |  |  | 7: 0.06; Total 10: 0; Total 13: 0.06; Total 17: 0.06 | BGA
168 | Construction of 132 KV D/C line from 400/220/132/33 KV Grid S/s at Lapanga to 132/33 KV GSS Brajarajnagar alongwith diversion of 220 KV DC IB-Budhipadar (1st line & 2nd line) |  | -1.823 |  | -1.823 |  | 7: 0; Actual For First Six Months 8: 0.506; Projection For Balance Six Months 9: 0.3; Total 10: 0.806; Total 12: 0.806; Total 13: 0; Total 17: 0 | BGA
169 | 132KV DC line from 132/33KV Grid S/S R Udayagiri to 132/33KV Grid S/S at Paralakhemundi with 2Nos of feeder bay extention at both s/s (RRCP) | 40.82 | 0.96 |  |  |  | 7: 41.78; Actual For First Six Months 8: 0.01; Projection For Balance Six Months 9: 3; Total 10: 3.01; Total 13: 44.79; Total 14: 15.5; Total 17: 60.29 | BGA
170 | 220 KV DC LILO line from 220 KV Narendrapur-Therubali DC line to 220/132/33 KV Grid S/s.Aska |  | 3.8 |  | 3.8 |  | 7: 0; Projection For Balance Six Months 9: 1.2; Total 10: 1.2; Total 13: 1.2; Total 17: 1.2 | BGA
171 | Construction of 132/33 KV Grid S/s GIS at Hinjilikatu, Ganjam |  | 0.53 |  | 0.53 |  | 7: 0; Actual For First Six Months 8: 0.75; Projection For Balance Six Months 9: 0.6; Total 10: 1.35; Total 13: 1.35; Total 17: 1.35 | BGA
172 | 2nd 132KV Feeder Bay at 132/33 KV Grid SS Padampur & 132 /33 KV Grid Ss Nuapada | 1.384 | 0.118 |  | 1.502 |  | 7: -2.2204e-16; Total 10: 0; Total 13: -2.2204e-16; Total 17: -2.2204e-16 | BGA
174 | Installation & Commissioning of 3rd 315MVA, 400/220 KV ICT along with construction of 1 no. 400KV DIA & 1 No. 220KV Transformer Bay with associated system at existing 400/220KV Grid Sub-station, New Duburi. (DRC Scheme) | 20.87 | 0.09 |  |  |  | 20.96 | 28.39 | 3.3 | 31.69 |  | 52.65 | 0 | 0.5 |  | 0.5 | 0 | DRC | BGA
Deposit Works
180 | Construction of 132 KV SC line(37KM) from existing 132 Grid S/S,Bangiriposi to Proposed RTSS at Bhanjpur & 2Nos. 132 KV feeder bay at 132/33 KV GSS Bangiriposi & Associated 132 KV 2 phase DC line(40KM) from GSS Bangiripsi to proposed 132 KV RTSS Bhanjapur. | 13.57 | 4.68 |  |  |  | 7: 18.25; Actual For First Six Months 8: 0.85; Projection For Balance Six Months 9: 2.6; Total 10: 3.45; Total 12: 21.7; Total 13: 0; Total 17: 0 | BD
181 | RTSS Nayagarh | 7.51 | 2.78 |  | 0 |  | 10.29 | 0.74 | 1.76 | 2.5 |  | 12.77 | 0.02 | 2 |  | 2 | 0.02 |  | BD
187 | RTSS at Khamar |  | 0.07 |  |  |  | 7: 0.07; Actual For First Six Months 8: 0.05; Projection For Balance Six Months 9: 4.95; Total 10: 5; Total 13: 5.07; Total 14: 20; Total 17: 25.07 | BD
188 | RTSS Dhanmandal | 7.7 |  |  |  |  | 7: 7.7; Projection For Balance Six Months 9: 2.5; Total 10: 2.5; Total 13: 10.2; Total 14: 0.3; Total 17: 10.5 | BD
189 | RTSS Charbatia | 11.31 | 5.63 |  |  |  | 16.94 | 5.08 | 0.4 | 5.48 |  | 22.42 | 0 | 0.2 |  | 0.2 | 0 |  | BD
190 | other deposit work | 0.78 |  |  |  |  | 7: 0.78; Total 10: 0; Total 13: 0.78; Total 17: 0.78 | BD
191 | 132 KV line from Jabamayeeto RTSS-Sukinda | 11.44 | 0.04 |  |  |  | 7: 11.48; Total 10: 0; Total 12: 11.48; Total 13: 0; Total 17: 0 | BD
195 | 220 KV Traction line from 220 /33 Kv Grid S/S Laxmipur to 220 / 25 KV RTSS Laxmipur. (Modification of 220 kV SC Line on DC Tower from location 05 to 07 of existing 220 kV RTSS Laxmipur Line. | 0 | 0.29 |  | 0.29 |  | 0 |  | 0.2 | 0.2 |  | 0.2 | 0 | 0.2 | 0 | 0.2 | 0 |  | BD
196 | 132KV 2Phase line from 132/33 KV Grid S/S Bhawanipatna to RTSS,Bhawanipatna |  | 0.2 |  | 0.2 |  | 0 | 0.67 | 0.1 | 0.77 |  | 0.1 | 0.67 | 0 | 0 | 0 | 0.67 |  | BD
199 | Construction of 132 KV SC ( 2 phase) Traction line from existing 132 /33 KV Grid Bhawanipatna to proposed RTSS Lanjigarh along with one no 132 KV feeder bay exxtensison at 132/33 KV Grid Ssubss-station. Estt. No 11/2014-15 |  | 0.56 |  | 0.56 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | BD
200 | Construction of 132 KV SC line on DC Tower (Two Conductor) from U/C 220/132/33 KV Grid Sub-station, Gunupur to proposed RTSS, Palasingi and 132 KV feeder bay extension at 220/132/33KV Grid Sub-Station, Gunupur. |  | 0.29 |  | 0.29 |  | 0 |  | 0.55 | 0.55 |  | 0.55 | 0 | 0 | 0 | 0 | 0 |  | BD
201 | Const of 2no 33kv Bay at 220KV Grid sub-station Gobindapalli Avantika Work | 0.85 | 0.15 |  | 1 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | BD
202 | Construction of 1No 33kv Bay at 220/33 kv Grid s/s Gobindapalli for megalift project at saradaput | 0.37 | 0.03 |  | 0.4 |  | 7: 0; Actual For First Six Months 8: 0.03; Total 10: 0.03; Total 12: 0.03; Total 13: 0; Total 17: 0 | BD
203 | Const of 2 nos of 33KV bay at GSS Boriguma for Shrabani Power Generation pvt ltd | 0.42 | 0 |  |  |  | 0.42 | 0.06 | 0.3 | 0.36 |  | 0.78 | 0 | 0.03 |  | 0.03 | 0 |  | BD
205 | Abondoned CWIPS | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 | BD
206 | Abondoned CWIPS | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 | BD
207 | Provision for Abondoned CWIPS | -0.02 |  |  |  |  | 7: -0.02; Total 10: 0; Total 13: -0.02; Total 17: -0.02 | BD
209 | Construction of 220 KV LILO line from Loc. No. 125 & Loc. No. 126 of existing 220 KV Budhipadar to Tarkera line (CKT-II) and 132 KV LILO line from Loc. No. 291 of existing 132 KV Budhipadar to Tarkera line (CKT-II) and 220/132/33 KV Grid Sub-Station at Bamra. (50% Deposit Work) |  | 0.273 |  | 0.273 |  | 7: 0; Actual For First Six Months 8: 0.54; Projection For Balance Six Months 9: 1.11; Total 10: 1.65; Total 12: 1.65; Total 13: 0; Total 17: 0 | BD
211 | Construction of 220 KV SC line on DC tower from 220/33 KV GSS Bonai to Taldih Iron Ore Mines, SAIL on deposit work basis. | 4.024 | 8.479 |  |  |  | 12.503 | 10.35 | 15 | 25.35 |  |  | 37.853 | 22 |  | 59.853 | 0 |  | BD
212 | 132KV Transmission line from proposed 220/132/33 KV Grid Sub-Station at Bamra to Proposed RTSS Dhutura | 15.832 | -0.024 |  |  |  | 7: 15.808; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 16.308; Total 14: 5; Total 17: 21.308 | BD
213 | 132KV Transmission line from proposed 220/132/33 KV Grid Sub-Station at Bamra to Proposed RTSS Garposh | 6.755 |  |  |  |  | 7: 6.755; Projection For Balance Six Months 9: 2; Total 10: 2; Total 13: 8.755; Total 14: 5; Total 17: 13.755 | BD
214 | 132 KV S/c (2 Conductor) line from 220/132/33 Grid S/s Lapanga to RTSS Rengali & associated 1 nos 132 KV Feeder bay extension at Lapange Grid S/s. Est. No. 06/2014-15 |  | 0.068 |  | 0.068 |  | 7: 0; Projection For Balance Six Months 9: 0.1; Total 10: 0.1; Total 12: 0.1; Total 13: 0; Total 17: 0 | BD
215 | Diversion of 132 KV D/C Line from Loc. No. 9 to Loc No. 12 of 132KV CPP-II (NSPCL, Rourkela) to MSDS-V, SAIL, RSP line along with connecting the line to the new bay |  | 0.09 |  | 0.09 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | BD
216 | Diversion of (1) 132KV D/C Lapanga Brajrajnagar Line and (2) 220KV D/C Aditya Aluminium-Budhipadar Line from the proposed power plant & Ash pond area of M/s. NLC at Thelkoloi, Sambalpur | 2.2 | 10.041 |  |  |  | 12.241 | 10.69 | 18 | 28.69 |  |  | 40.931 | 12 |  | 52.931 | 0 |  | BD
217 | Diversion-cum-heightening of 400 KV D/C IB-Lapanga line from Loc. No. 22 to Loc. No. 23 and from Loc. No. 28 to Loc. No. 30 for under passing of proposed diversion of 132 KV D/C Lapanga-Brajrajnagar line and 220 KV Budhipadar-Aditya Aluminium line. | 0.303 | 0.008 |  |  |  | 7: 0.311; Total 10: 0; Total 13: 0.311; Total 16: 0.311; Total 17: 0 | BD
224 | 132kV Transmission Line from 132/33 kV Grid S/S at Rairangpur to proposed RTSS,Rairangpur with 1no. 132 KV Feeder Bay extension at 132/33 KV Grid S/S,Rairangpur (Approx. Line Length-10.523 K.M.) (RVNL Deposit Work) | 7.13 | 0.24 |  |  |  | 7.37 | 0.01 | 1.44 | 1.45 |  | 8.82 | 0 | 0.5 |  | 0.5 | 0 |  | BD
225 | 01 No 33KV feeder Bay Extention at 132/33 GSS BHATLI For GANGADHAR MEHER LIFT IRRIGATION PROJECT |  | 0.56 |  | 0.56 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | BD
226 | 132 KV two phase SC line from existing 132/33 KV GSS, Sonepur to proposed RTSS Sonepur and 1. Nos 132kv feeder bay extension at 132/33 KV GSS sonepur | 1.601 | 2.83 |  |  |  | 4.431 | 1.97 | 2.5 | 4.47 |  | 8.902 | -0.001 | 1 |  |  | 0.999 |  | BD
227 | Construction of BPCL BHATLI LINE BIO ETHANOL | 5.345 | -4.41 |  | 0.93 |  | 7: 0.005; Total 10: 0; Total 13: 0.005; Total 17: 0.005 | BD
B. Without Investment approval from the Commission (Rs. 10 Cr. or more)
CONSTRUCTION-Own Contribution (Debt:Equity)
89 | 220/132/33 KV S/S Nuapada | 0.36 |  |  |  |  | 7: 0.36; Total 10: 0; Total 13: 0.36; Total 14: 10; Total 17: 10.36; Total 18: NEW EFC | BEB | Initial exp. was for survey. However, Commission's approval will be obtained before NIT
WORK EXECUTED BY GoO FUNDING
No projects
C. Project cost less than Rs. 10 Cr.
CONSTRUCTION-Own Contribution (Debt:Equity)
11 | Const. Of 220 KV DC line for 400/220/132 KV )PGCIL) Grid S/S to proposed 220/132 KV Grid S/S, Karanjia. | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 12: 0.03; Total 13: 0; Total 17: 0; Total 18: New EFC | BEC
12 | Const. Of 400 KV LILO one tapping from new Duburi-Paradeep. | 0.02 |  |  |  |  | 7: 0.02; Total 10: 0; Total 12: 0.02; Total 13: 0; Total 17: 0; Total 18: New EFC | BEC
18 | Revival of 132 KV existing Transmission Line from Macchkund Power House to Machhkund RTSS (including Surevey work - 4 lakh) ) | 0.07 |  |  |  |  | 7: 0.07; Total 10: 0; Total 12: 0.07; Total 13: 0; Total 17: 0; Total 18: own | BEC
21 | Balance work of 132/33 KV GSS Boriguma | [5 empty] | 0 | 0.08 | 0.95 | 1.03 |  |  | 1.03 | 0.31 |  |  | 1.34 | E-300 | BEC
22 | Stringing of 2nd circuit (three conductors) from LILO point of existing 220 KV Balimela-Malkangiri Line to Newly constructed 220/33 KV Grid S/S Kalimela. | 0.14 | 0.02 |  | 0.16 |  | 7: 0; Actual For First Six Months 8: 0.21; Total 10: 0.21; Total 13: 0.21; Total 16: 0.21; Total 17: 0; Total 18: own | BEC
24 | Construction of 1no. 132 KV feeder bay each at 132/33KV GSS Dabugaon & Umerkote along with hot lines stringling of 132KV conductor from Dabugaon GSS to Umerkote GSS. |  | 2.15 |  |  |  | 2.15 | 1.05 | 3.37 | 4.42 |  |  | 6.57 | 1.42 |  |  | 7.99 | own | BEC
47 | Construction of 220/132 KV S/S at IB(PMU) | 0.679 |  |  |  |  | 7: 0.679; Total 10: 0; Total 13: 0.679; Total 17: 0.679 | BEC
48 | Construction of 220/132 KV S/S at IB(PMU) (PROVISION FOR ABANDONED PPROJECT) | -0.679 |  |  |  |  | 7: -0.679; Total 10: 0; Total 13: -0.679; Total 17: -0.679 | BEC
63 | 400KV DC line from Pandiabil to Sindhaba | 0.57 |  |  |  |  | 7: 0.57; Total 10: 0; Total 13: 0.57; Total 17: 0.57 | BEC
64 | 132 kv Line from Bhanjanagar to Phulbani | 0.13 |  |  |  |  | 7: 0.13; Projection For Balance Six Months 9: 0.4; Total 10: 0.4; Total 13: 0.53; Total 17: 0.53; Total 18: OWN | BEC
65 | Provision for incompleted / abondoned work | -0.7 |  |  |  |  | 7: -0.7; Total 10: 0; Total 13: -0.7; Total 17: -0.7 | BEC
72 | 132 KV Joda-Polasponga and Polasponga-Keonjhar line | 1.37 |  |  |  |  | 7: 1.37; Total 10: 0; Total 12: 1.37; Total 13: 0; Total 17: 0; Total 18: OWN | BEC
91 | 132/33 KV Grid S/S B.M.Pur & Associated 132 KV Line from Sonepur to B.M.Pur |  | 0.018 |  | 0.018 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: E-250 | BEC
93 | 220KV DC Line From Existing GSS Sadeipali, New Bolangir to GSS Kesinga |  | 0.213 |  | 0.213 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: OWN | BEC
94 | Construction work of 220KV LILO of Bolangir-Kesinga line for connectivity to 400/220 KV GSS Madhiapali PGCIL Bolangir |  | 0.058 |  | 0.058 |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0; Total 18: OWN | BEC
112 | Constn of 132/33 KV Grid S/S, Kuakhia | 2.81 |  |  |  |  | 7: 2.81; Total 10: 0; Total 13: 2.81; Total 17: 2.81; Total 18: NEW EFC | BEC
113 | Constn of boundary wall at proposed land for 132/33 KV Grid S/s Pihura near Grid Steel Alloys | 0.19 |  |  |  |  | 7: 0.19; Total 10: 0; Total 13: 0.19; Total 17: 0.19 | BEC
114 | Const of 132 KV line from Kendrapara to Paradeep | 0.25 |  |  |  |  | 7: 0.25; Total 10: 0; Total 13: 0.25; Total 17: 0.25 | BEC
115 | PROVISION FOR abandoned/incomplete CWIPS | -1.66 |  |  |  |  | 7: -1.66; Total 10: 0; Total 13: -1.66; Total 17: -1.66 | BEC
116 | 132 KV S/s at Kendrapara (PMU) | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 | BEC
117 | 400 KV DC Line from Meramundali to Duburi | -0.2 |  |  |  |  | 7: -0.2; Total 10: 0; Total 13: -0.2; Total 17: -0.2 | BEC
138 | Telecom debt and equity | 74.5848 | 10.2972 | 0 | 2.4772 | 2.9985 | 79.4064 | 3.83 | 7.76 | 11.59 | 0 | 63.26 | 27.7364 | 66.44 | 0 | 85.8 | 8.3764
139 | Civil debt and equity | 11.0257 | 25.4337 | 0 | 13.2838 | 5.0692 | 18.1065 | 12.9429 | 59.2324 | 72.1753 | 0 | 28.3497 | 61.9321 | 63.4845 | 0 | 108.7647 | 16.6519
140 | IT and others debt and equity | 10.67 | 1.1 | 0 | 0.029676 | 0.078474 | 11.6619 | 0 | 12.7149 | 12.7149 | 0 | 24.3768 | 0 | 78.09 | 0 | 16.09 | 62
141 | Other Capex by O&M Wings Debt and equity | 97.4156 | 157.1259 | 0 | 128.7918 | 0 | 125.7538 | 53.2002 | 120.7419 | 173.9421 | 0 | 234.6711 | 65.0249 | 215.5374 | 0 | 204.9897 | 75.5726
WORK EXECUTED BY GoO FUNDING
154 | Construction of boundry wall for jiridamali store at kamakhyanagar | 0.07 |  |  |  |  | 7: 0.07; Total 10: 0; Total 13: 0.07; Total 17: 0.07 | BGC
156 | Dalabagha survey | 0.25 |  |  |  |  | 7: 0.25; Total 10: 0; Total 13: 0.25; Total 17: 0.25 | BGC
157 | survey work for 220 kv lilo line from duburi - MRDL DC line to 220/132 Kv grid S/s Dhenkanal-B | 0.43 |  |  |  |  | 7: 0.43; Total 10: 0; Total 13: 0.43; Total 17: 0.43 | BGC
158 | Const. of 220/33KV s/s and its associate line at Gopinathpur keonjhar(Short closed) | 2.41 |  |  |  |  | 7: 2.41; Total 10: 0; Total 13: 2.41; Total 17: 2.41 | BGC
159 | Const.of 220 KV line from TTPS Rengali to Chendipada | 0.03 |  |  |  |  | 7: 0.03; Total 10: 0; Total 13: 0.03; Total 17: 0.03 | BGC
163 | provision for abandoned/incomplete CWIPS | -2.77 |  |  |  |  | 7: -2.77; Total 10: 0; Total 13: -2.77; Total 17: -2.77 | BGC
164 | Diversion of existing 220 kv & 132 Kv line from the premises of TTPS /NTPC colony area talcher | 0.01 |  |  |  |  | 7: 0.01; Total 10: 0; Total 13: 0.01; Total 17: 0.01 | BGC
165 | Power supply to M/s BRG Steel | 0 |  |  |  |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | BGC
166 | Power supply to M/s MCL at Kaniha | 0 |  |  |  |  | 7: 0; Total 10: 0; Total 13: 0; Total 17: 0 | BGC
167 | provision for abandooned/incomplete CWIPS | -0.77 |  |  |  |  | 7: -0.77; Total 10: 0; Total 13: -0.77; Total 17: -0.77 | BGC
178 | Total O&M by GoO | 69.1319 | 30.137 | 0 | 5.71 | 0 | 93.5389 | 7.5531 | 31.9 | 39.4531 | 0 | 88.7192 | 44.2729 | 29.7336 | 0 | 43.9847 | 30.0218
| OWN | 1.37 | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0 | 0
| GRANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEPOSIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.37 | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0 | 0
| Debt | [5 empty] | Total 10: 0; Total 14: 0
| Equity | [5 empty] | Total 10: 0; Total 14: 0
| Construction | [5 empty] | Actual For First Six Months 8: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 14: 0; Total 15: 0; Total 16: 0
| O&M | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| Civil | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| Telecom | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| IT | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| TOTAL | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0

## On or after 01.04.2025
CWIP position of project started/to be started on or after 01.04.2025 (including all upcoming projects)
[16 empty] | OERC | FORM F-2
Rs. in Crores
Sl No. | Description of the Project/Scheme | PREVIOUS YEAR(2024-25) | [5 empty] | CURRENT YEAR(2025-26) | [5 empty] | ENSUING YEAR(2026-27)
|  | OB as on 01.04.24 | Exp. during the year | Interest during construction | Transfer to fixed assets | Other Adjustment | Closing balance of WIP as on 31.03.25 | Expenditure during the year |  |  | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.26 | Exp. during the year | Interest during construction | Transfer to fixed assets | Closing balance of WIP as on 31.03.27 | Remark | Loan Amount/Sanctioned | Remark
[8 empty] | Actual For First Six Months | Projection For Balance Six Months | Total
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A. With Investment approval from the Commission (Rs. 10 Cr. or more)
CONSTRUCTION-Own Contribution (Debt:Equity)
1 | 220/33 KV Sub-Station at Nuabetanda | [5 empty] | Actual For First Six Months 8: 0; Projection For Balance Six Months 9: 30; Total 10: 30; Total 13: 30; Total 14: 35; Total 17: 65; Total 18: OTSSP-I | AEA
2 | 220/33 KV Sub-Station at Hatabasta | [5 empty] | Actual For First Six Months 8: 6.45; Projection For Balance Six Months 9: 20; Total 10: 26.45; Total 13: 26.45; Total 14: 15; Total 17: 41.45; Total 18: OTSSP-I | AEA
4 | 220KV UG Cabling from GSS Mendhasal to GIS Chanadaka B with Bay Extension at both ends | [5 empty] | Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5; Total 18: DRPS-II | AEA
32 | Construction of 400 KV line from TTPS Stage-II to 400/220/33 KV GIS at Meramundali-B (Executed by M/s Groma) | [5 empty] | 0 | 1.08 | 38.92 | 40 |  |  | 40 | 20 |  |  | 60 | Special- EFC | AEA
74 | 2*500MVA GSS at Basudevpur & Associated lines | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 0.5; Total 14: 5; Total 17: 5.5; Total 18: SDMF-100% grant | AEA
105 | Construction of GSS Manamunda with 2nd Circuit Stringing of Boudh -Sonepur line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 8; Total 10: 8; Total 13: 8; Total 14: 20; Total 17: 28; Total 18: GEETC | AEA
106 | 2nd Circuit Stringing of 132 KV Padampur-Ghens line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 10; Total 17: 13; Total 18: RRCP-II | AEA
107 | 2nd Circuit Stringing of Patnagarh-Kantabanji line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 10; Total 17: 13; Total 18: RRCP-II | AEA
111 | 400/220/33KV GIS at Neulapoi with line | [5 empty] | 0 | 1.44 | 18.56 | 20 |  |  | 20 | 80 |  |  | 100 | OTSSP-II | AEA
118 | Up-gradation of existing132/33KVGIS Khuntuni to up-coming Neulapoi GIS with line. | [5 empty] | 0 | 0 | 10 | 10 |  |  | 10 | 10 |  |  | 20 | OTSSP-II | AEA
119 | Construction Of 220 Kv D/C Transmission Line From 400/220/33 Kv Ais Grid S/S, Neulapoi To Proposed Manufacturing Complex Of M/S : Kalyani Steels At Gajamara, Dhenkanal | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10; Total 18: OTSSP-II | AEA
123 | Construction of 220*40 MVA, 220/33 KV GIS at Paradeep (Plastic park) | - |  |  |  |  | Actual For First Six Months 8: 1.3; Projection For Balance Six Months 9: 3; Total 10: 4.3; Total 13: 4.3; Total 14: 20; Total 17: 24.3; Total 18: OTSSP-II | AEA
128 | 400/220/33 KV GIS at Bhandaripokhari (Bhadrakh textile Park) | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5; Total 18: OTSSP-II | AEA
WORK EXECUTED BY GoO FUNDING
173 | 2*63 MVA, 132/33kv GIS at SCB Medical, Cuttack | [5 empty] | 0 | 90.37 | 66 | 156.37 |  |  | 156.37 | 10 |  | 166.37 | 0 |  | AGA
175 | Replacement of old conductor with new HTLS conductor in 220KV Budhipadar-Lapanga DC line from Loc. No. 1 to Loc. No. 63 (old Loc. No. 50/8) under TL SD, Jharsuguda. (334697658/-) | [5 empty] | 0 |  | 0.1 | 0.1 |  |  | 0.1 | 32 |  | 32.1 | 0 | HCTUS | AGA
176 | Estimate for replacement of old ACSR/AAAC zebra conductor of 220KV Katapali -Lapanga D/C line to HTLS conductor with all accessories | [5 empty] | Projection For Balance Six Months 9: 30; Total 10: 30; Total 13: 30; Total 14: 50; Total 16: 80; Total 17: 0; Total 18: HCTUS | AGA
177 | Replacement of old twin AAAC moose conductor with twin HTLS conductor(Zebra equivalent) in existing 400KV IB-Lapanga D/C line along with upgradation in main and tie bayof IB circuit at Lapanga GSS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.83 | 0 | 97.83 | 0 | HCTUS | AGA
Deposit Works
182 | RTSS Mancheswar | [5 empty] | Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 | AD
183 | RTSS Jaleswar | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 5; Total 17: 5.03 | AD
184 | RTSS Balasore | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 5; Total 17: 5.03 | AD
185 | RTSS at Boinda(Only for forest clearance) | [5 empty] | 0 |  | 0.2 | 0.2 |  | 0.2 | 0 | 0.1 |  | 0.1 | 0 |  | AD
186 | RTSS at Champapur | [5 empty] | 7: 0; Projection For Balance Six Months 9: 2.5; Total 10: 2.5; Total 13: 2.5; Total 14: 10; Total 17: 12.5 | AD
192 | RTSS Barjamda and associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 14: 5; Total 17: 5.02 | AD
193 | RTSS Banspani & associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 14: 5; Total 17: 5.02 | AD
194 | RTSS Harichandanpur & associated 132 Kv line | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.02; Total 10: 0.02; Total 13: 0.02; Total 17: 0.02 | AD
197 | Construction of 2 nos. of 132 kV Towers and dismantling of one 132 kV Tower, third phase conductor stringing on existing RTSS Rayagada Line. | [5 empty] | 0 |  | 0.1 | 0.1 |  | 0 | 0.1 | 0.02 | 0 | 0.02 | 0.1 |  | AD
198 | Construction of 01 no. of 132KV Feeder bay extension at existing 132/33KV Grid S/S, Tirtol with associated 132 KV Transmission line on DC Towers from 132/33 KV Grid S/s , TIRTOL to RTSS, Gorekhnath | [5 empty] | Projection For Balance Six Months 9: 2; Total 10: 2; Total 13: 2; Total 14: 10; Total 17: 12 | AD
204 | Const of 2 nos of 33KV Bay at GSS Boriguma for Sidheswari Power Generation Pvt Ltd | [5 empty] | 0 | 0.01 | 0.3 | 0.31 |  | 0.31 | 0 | 0.03 |  | 0.03 | 0 |  | AD
208 | Const of 4 nos of 132KV AIS Bays at 132/25KV Manabar RTSS and 2 nos 132KV AIS Bays at 132/33KV Grid SS Sunabeda withassociated 132KV DC line from existing 132/33KV Grid SS Sunabeda to RTSS Manbar(line length=25.419Km) | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 17; Total 17: 27 | AD
210 | Construction of 220 KV 2 phase line on DC tower from 220/33 KV Bonai Grid S/s to RTSS Bimalagarh & Associted one no. 220 KV Feeder bay at 220/33 KV Grid S/s for Power | [5 empty] | 7: 0; Actual For First Six Months 8: 0.13; Total 10: 0.13; Total 12: 0.13; Total 13: 0; Total 17: 0 | AD
218 | Two nos of 400 KV feeder bay extension at Lapanga for connectivity of 400 KV D/C NLC - Lapanga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10 | AD
219 | 400 KV D/C NLC - Lapanga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.03; Total 10: 0.03; Total 13: 0.03; Total 14: 10; Total 17: 10.03 | AD
220 | Construction of 220 KV Barkote-RTSS, Barkote line along with associated one no. of 220 KV Feeder bay at 220/33 KV GSS at Barkote. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.06; Total 10: 0.06; Total 13: 0.06; Total 14: 2; Total 17: 2.06 | AD
221 | Construction of 132 KV D/C Kuarmunda-RTSS, Bondamunda line along with associated two nos of 132 KV Feeder bay extension at 220/132/33 KV GSS at Kuarmunda. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.08; Total 10: 0.08; Total 13: 0.08; Total 14: 2; Total 17: 2.08 | AD
222 | Diversion of 220KV Narendrapur TATA MRSS Line from 220/132/33KV Grid SS Narendrapur to MS TATA Steel Ltd atnew NH 59 | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.5; Total 10: 1.5; Total 13: 1.5; Total 16: 1.5; Total 17: 0 | AD
223 | 220KV DC Line from GSS Dasapalla to RTSS BUGUDA | [5 empty] | 7: 0; Projection For Balance Six Months 9: 3; Total 10: 3; Total 13: 3; Total 14: 3; Total 17: 6 | AD
B. Without Investment approval from the Commission (Rs. 10 Cr. or more)
CONSTRUCTION-Own Contribution (Debt:Equity)
6 | 220/33KV GIS at Sundarpada with Line | [5 empty] | Total 10: 0; Total 13: 0; Total 17: 0; Total 18: DRPS-II | AEB
28 | const of 220/33KV GSS Mukhiguda | [5 empty] | 7: 0; Projection For Balance Six Months 9: 50; Total 10: 50; Total 13: 50; Total 14: 100; Total 17: 150; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
29 | 400KV DC line from Indravati Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 50; Total 10: 50; Total 13: 50; Total 14: 100; Total 17: 150; Total 18: GEETC | AEB | Commission's approval will be obtained before NIT
37 | 2X200 MVA, 220/132 KV AIS S/S WITH SAS AT Chainpal | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10; Total 18: New EFC | AEB | Commission's approval will be obtained before NIT
49 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Koida. 220 KV D/C Barbil-Koida line. 220 KV Taldih-Koida line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.12; Total 10: 0.12; Total 13: 0.12; Total 14: 5; Total 17: 5.12; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
50 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Kansbahal. 220 KV D/C Kuarmunda-Kansbahal line. 132 KV D/C Kansbahal-Kalunga line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.13; Total 10: 0.13; Total 13: 0.13; Total 14: 5; Total 17: 5.13; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
51 | Construction of 2 X 160MVA + 2 X 80 MVA, 220/132/33 KV GSS at Basantpur. 220 KV D/C A. Katapali-Basantpur line. 132 KV D/C Basantpur-Thuapali line. 132 KV D/C Basantpur-Maneswar line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.2; Total 10: 0.2; Total 13: 0.2; Total 14: 5; Total 17: 5.2; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
52 | Construction of 2 X 50MVA, 132/33 KV GSS at Kolabira. 132 KV D/C Kolabira-Kuchinda line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
53 | Construction of 2 X 50MVA, 132/33 KV GSS at Subdega. 132 KV D/C Sundargarh-Subdega line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
54 | Construction of 2 X 50MVA, 132/33 KV GSS at Sason. 132 KV D/C Basantpur-Sason line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 3; Total 17: 3; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
55 | Construction of 2 X 160MVA + 2 X 50 MVA, 220/132/33 KV GSS at Badimal. 220 KV D/C Budhipadar-Badimal line. 132 KV D/C Badimal-Lakhanpur line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
56 | Construction of 765/400 KV GSS at Kolabira. 765 KV D/C Kenapali (PG)-Kolabira line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.15; Total 10: 0.15; Total 13: 0.15; Total 14: 10; Total 17: 10.15; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
57 | 765 KV D/C Kolabira-Duburi line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 10; Total 17: 10; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
58 | 400 KV D/C OPGC - Kolabira line. | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 5; Total 17: 5; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
59 | 400 KV DC Line From Floating Solar Power Plant, Hirakud to proposed 765/400 KV GSS, Kulihamal, Pokharasale, Kolabira | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.13; Total 10: 0.13; Total 13: 0.13; Total 14: 5; Total 17: 5.13; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
68 | 400 KV Theruvelli-Gopalpur DC Line | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 30; Total 17: 30; Total 18: GEETC | AEB | Commission's approval will be obtained before NIT
73 | Const of 765/400 Kv GSS at Duburi | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 0.5; Total 17: 0.5; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
83 | Construction of 400 kV DC Line from Jeypore (PGCIL) to Therubali to TATA SEZ | [5 empty] | 7: 0; Projection For Balance Six Months 9: 20; Total 10: 20; Total 13: 20; Total 14: 50; Total 17: 70; Total 18: GEETC | AEB | Commission's approval will be obtained before NIT
84 | Construction of 33/220kv Pooling Sub station at Padepadar for evacuating Power from FSPV, Indravati | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 50; Total 17: 60; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
85 | Construction of 220kv Line Connectivity from the proposed 33/220KV Pooling s/s, Padepadar to 400/220KV , Mukhiguda Switchyard | [5 empty] | 7: 0; Projection For Balance Six Months 9: 10; Total 10: 10; Total 13: 10; Total 14: 30; Total 17: 40; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
86 | Construction of 02 nos. of 220KV Bays at Mukhiguda s/y for evacuating Power from FSPV Project | [5 empty] | 7: 0; Projection For Balance Six Months 9: 8; Total 10: 8; Total 13: 8; Total 14: 6.2; Total 17: 14.2; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
88 | Construction of 2 x 500MVA, 400/220KV AIS GSS with SAS at Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 20; Total 10: 20; Total 13: 20; Total 14: 50; Total 17: 70; Total 18: GEETC | AEB | Commission's approval will be obtained before NIT
104 | 400/220/33 KV GSS Titlagarh with associated line and it's 220 KV connecting system | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1; Total 10: 1; Total 13: 1; Total 14: 10; Total 17: 11; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
108 | Construction of 220 KV DC line from 400/220/33 KV GSS Titlagarh to 220/132/33 KV GSS Kesinga | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.5; Total 10: 0.5; Total 13: 0.5; Total 14: 10; Total 17: 10.5; Total 18: NEW EFC | AEB | Commission's approval will be obtained before NIT
125 | Dismantling of ACSR conductor and stringing of HTLS conductor of 132KV Bhadrak-Soro SC line including 132KV Soro LILO Line under EHT(O&M) Division, Balasore(Est. Cost- 101.70Cr) | 0 | 0 |  |  |  | 7: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 13: 0; Total 14: 50; Total 17: 50 | AEB | Commission's approval will be obtained before NIT
126 | Dismantling of ACSR Panther conductor and augmentation of ACSR Panther conductor by HTLS conductor in 132 KV Duburi-Jajpur Road DC Line under EHT (O&M) Division, Jajpur Road (24.70Cr) | [5 empty] | 7: 0; Total 10: 0; Total 13: 0; Total 14: 15; Total 17: 15 | AEB | Commission's approval will be obtained before NIT
WORK EXECUTED BY GoO FUNDING
No projects
C. Project cost less than Rs. 10 Cr.
CONSTRUCTION-Own Contribution (Debt:Equity)
5 | 220/33KV AIS with 22km Line at Khandapada | [5 empty] | Total 10: 0; Total 13: 0; Total 17: 0; Total 18: DRPS-II | AEC
80 | Survey & Forest clearance work of 400kv DC line connectivity between Indravati to Therubali for development of Green Energy Evacuation Transmission Corridor for evacuation of RE power .( Approx. line length = 100km) | [5 empty] | 7: 0; Projection For Balance Six Months 9: 1.2; Total 10: 1.2; Total 13: 1.2; Total 14: 0.47; Total 17: 1.67; Total 18: GEETC | AEC
81 | Survey for Construction of Transmission Infrastucture meant for proposed 3x75 MW FSPV Project, UIHEP Indravati from UIHEP, Grid sub-station mukhiguda to proposed pooling sub-station (Padepadar) approx length-12 KMs and contour survey of sub-station land to an extent of acres-28.00 | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.07; Total 10: 0.07; Total 13: 0.07; Total 17: 0.07; Total 18: NEW EFC | AEC
82 | Providing Consultancy Service for obtaining the forest clearance of 400kv Quad Moose D/C line connectivity between Jeypore to Therubali to TATA SEZ | [5 empty] | 7: 0; Actual For First Six Months 8: 1; Total 10: 1; Total 13: 1; Total 14: 5.46; Total 17: 6.46; Total 18: GEETC | AEC
87 | Consultancy Service for forest clearance work of an area of approx. 100 Acres of land proposed for Construction of 400/220KV AIS at Therubali | [5 empty] | 7: 0; Projection For Balance Six Months 9: 0.68; Total 10: 0.68; Total 13: 0.68; Total 14: 0.17; Total 17: 0.85; Total 18: GEETC | AEC
WORK EXECUTED BY GoO FUNDING
No projects
| OWN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GRANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEPOSIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Debt | [5 empty] | Total 10: 0; Total 14: 0
| Equity | [5 empty] | Total 10: 0; Total 14: 0
| Construction | [5 empty] | Actual For First Six Months 8: 0; Projection For Balance Six Months 9: 0; Total 10: 0; Total 14: 0; Total 15: 0; Total 16: 0
| O&M | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| Civil | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| Telecom | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| IT | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0
| TOTAL | [5 empty] | Total 14: 0; Total 15: 0; Total 16: 0