## CBA
COST BENEFIT ANALYSIS
A. BENEFITS DUE TO ADDITIONAL SALE OF ENERGY ON ACCOUNT OF CONSTRUCTION OF 400/220KV GSS BASUDEVPUR
1 | Transformation Capacity considered for revenue calculation MVA considered = 2x500MVA +600MVA (through 400kV). Besides that there is a plan to install additional 500MVA for future loads. | 1600
2 | Power factor (PF) | 0.9
3 | Diversity factor (DF=1.2 due to industrial GSS) | 1.2
4 | Load factor (LF=0.7 due to industrial GSS) | 0.7
5 | Additional Avg. power available for sale on account of construction of 400/220kV GSS Basudevpur (Joda) | 840 | 0.9: power factor 1.2: Diversity factor
6 | Additional energy available for sale in LU | 73584 | Due to industrial GSS 0.7 LF is considered
7 | With 3% transmission losses in the Grid, the energy available for sale per annum in LU | 71376.48 | TL of 3% is approved for FY 25-26
8 | Anticipated revenue at a cost of Rs.0.24/ Unit in Lakhs | 17130.3552
B. BENEFITS OF THE SCHEME DUE TO REDUCTION IN LOSSES
1 | Total losses before implementation of the scheme in MW | 1202.2222
2 | Total losses after implementation of the scheme in MW | 1184.8235 | Loss reduction from Load flow study
3 | Total reduction in losses in MW | 17.3987
4 | Load factor | 0.7
5 | Loss load factor (0.8 LF2 + 0.2 LF) | 0.532
6 | The energy available for sale per year in LU | 810.8351
7 | With 3% transmission losses in the Grid, the energy available for sale per annum in LU | 786.5101
8 | Anticipated revenue due to reduction in losses in lakhs @ Rs. 0.24/Unit | 188.7624
C. CALCULATION OF REVENUE RETURN
1 | Anticipated revenue due to reduction in losses [Rs. Lakhs] | 188.7624
2 | Anticipated revenue due to sale of additional energy [Rs. Lakhs] | 17130.3552
3 | Total anticipated annual revenue [Rs. Cr.] | 173.1912
4 | Estimated Cost [Rs. Cr.] | 1642.08
| Average Annual Rate of Return in % | 10.5471

## IRR Basudevpur
Calculation of NPV and IRR : For 2X500 MVA, 400/220KV Sub-Station at Basudevpur
CoC (%) = | 70% | x | 8.03 | + | 30% | x | 15.5 | Average | 6.58 |  |  | RoI on Loan P.a |  |  | = | 7.75 |  | IRR = | 9.439% | [16 empty] | (Rs. in Lakh)
Particulars | Constuction Period |  |  | Benefits Period | [34 empty] | Total
Financial Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Cash Inflow (CI)
Equity | 98.52 | 246.31 | 147.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492.62
Loan(Principal) | 229.89 | 574.73 | 344.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149.46
Loan (Interest) | 18.46 | 64.61 | 92.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.37
Revenue | 0 | 0 | 0 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 6061.6912
Salvage Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181.745 | 181.745
Total (CI) - (A) | 346.87 | 885.65 | 584.93 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 173.1912 | 354.9362 | 8060.8862
Cash Outflow (CO)
CWIP | 328.41 | 821.04 | 492.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642.08
IDC | 18.46 | 64.61 | 92.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.37
Loan Repayment | 0 | 0 | 0 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324.83
Interest on Loan | 0 | 0 | 0 | 101.95 | 93.09 | 84.22 | 75.36 | 66.49 | 57.62 | 48.76 | 39.89 | 31.03 | 22.16 | 13.3 | 4.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638.3
R&M exp. @ 3 % PC | 0 | 0 | 0 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 1908.2
Total (CO) - (B) | 346.87 | 885.65 | 584.93 | 266.8725 | 258.0125 | 249.1425 | 240.2825 | 231.4125 | 222.5425 | 213.6825 | 204.8125 | 195.9525 | 187.0825 | 178.2225 | 169.3525 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 54.52 | 5688.78 | IRR
Net Cash Inflow (A-B) | 0 | 0 | 0 | -93.6813 | -84.8213 | -75.9513 | -67.0913 | -58.2213 | -49.3513 | -40.4913 | -31.6213 | -22.7613 | -13.8913 | -5.0313 | 3.8387 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 118.6712 | 300.4162 | 2372.1062 | 9.439%
DF @ CoC | 1 | 0.938 | 0.88 | 0.826 | 0.775 | 0.727 | 0.682 | 0.64 | 0.601 | 0.564 | 0.529 | 0.496 | 0.465 | 0.437 | 0.41 | 0.384 | 0.361 | 0.338 | 0.318 | 0.298 | 0.28 | 0.262 | 0.246 | 0.231 | 0.217 | 0.203 | 0.191 | 0.179 | 0.168 | 0.158 | 0.148 | 0.139 | 0.13 | 0.122 | 0.115 | 0.107 | 0.101 | 0.095
Net Present value(NPV) | 0 | 0 | 0 | -77.38 | -65.74 | -55.22 | -45.76 | -37.26 | -29.66 | -22.84 | -16.73 | -11.29 | -6.46 | -2.2 | 1.57 | 45.57 | 42.84 | 40.11 | 37.74 | 35.36 | 33.23 | 31.09 | 29.19 | 27.41 | 25.75 | 24.09 | 22.67 | 21.24 | 19.94 | 18.75 | 17.56 | 16.5 | 15.43 | 14.48 | 13.65 | 12.7 | 11.99 | 28.54 | 216.86
NPV at IRR | 0 | 0 | 0 | -71.48 | -59.12 | -48.38 | -39.05 | -30.97 | -23.98 | -17.98 | -12.84 | -8.44 | -4.71 | -1.56 | 1.09 | 30.62 | 28.01 | 25.63 | 23.38 | 21.36 | 19.58 | 17.8 | 16.26 | 14.95 | 13.65 | 12.46 | 11.39 | 10.44 | 9.49 | 8.66 | 7.95 | 7.24 | 6.65 | 6.05 | 5.58 | 5.1 | 4.63 | 10.81 | 0.27
**
CoC - Cost of Capital
IDC- Interest During Construction
CWIP- Capital Work in Progress
DF- Discounting Factor
IRR- Internal Rate of Return
ARR- Average Annual Rate of Return
Opening Balance |  |  | 1324.83 | 1214.4275 | 1104.025 | 993.6225 | 883.22 | 772.8175 | 662.415 | 552.0125 | 441.61 | 331.2075
Repayment |  |  | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025 | 110.4025
Closing Balance |  |  | 1214.4275 | 1104.025 | 993.6225 | 883.22 | 772.8175 | 662.415 | 552.0125 | 441.61 | 331.2075 | 220.805
Agerage Loan |  |  | 1269.6287 | 1159.2263 | 1048.8238 | 938.4213 | 828.0187 | 717.6163 | 607.2137 | 496.8112 | 386.4087 | 276.0063
Interest |  |  | 101.9512 | 93.0859 | 84.2205 | 75.3552 | 66.4899 | 57.6246 | 48.7593 | 39.8939 | 31.0286 | 22.1633
|  |  | 0.0011886 | -0.0041321 | 0.00054712 | -0.0047736 | -9.4375e-05 | 0.0045849 | -0.00073588 | 0.0039434 | -0.0013774 | 0.0033019

## Data sheet
| Expenditure in Crores: | 1642.08
| Year: | 2026-27 | 2027-28 | 2028-29
| % of Expenditure: | 20% | 50% | 30%
| Year wise expenditure: | 328.416 | 821.04 | 492.624
Loan | 70% | 229.89 | 574.73 | 344.84
Equity | 30% | 98.52 | 246.31 | 147.79
Total | 100% | 328.41 | 821.04 | 492.63