## Summarry
BOQ Amendment Proposal - 1
NAME OF THE WORK: Design, Engineering, Supply, Erection and Commissioning of: (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS).
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Name of the agency: JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
New Amendment Price Schedule | Sr. No. | Description | Original Order Value |  |  | Total Order Value After Amendment |  |  | Differential Value Inclusive of GST(Between Original BOQ And Ammended BOQ) | Deviation Percentage
|  |  | Ex-Works Price with Freight in INR | Total GST in INR (18%) | Total in INR | Total Revised Price | Total GST in INR (18%) | Total in INR
| 1 | Schedule - VIIA - Part-I Supply Component of the Works Contract for SS & Line | 1162651101.1405 | 209277198.2053 | 1371928299.3458 | 1312689940.6894 | 236284189.3241 | 1548974130.0135 | 177045830.6677 | 12.9% | bay | 79651332.4255
| i | 220KV BAY EXTENSION AT PARADEEP | 41271733.1086 | 7428911.9596 | 48700645.0682 | 43937231.5967 | 7908701.6874 | 51845933.2841 | 3145288.2159 | 6.458% | 220 | 896397073.5047
| ii | 220KV TR. LINE FROM PARADEEP - ERASAMA | 287302237.3364 | 51714402.7205 | 339016640.0569 | 425326788.3531 | 76558821.9036 | 501885610.2566 | 162868970.1997 | 48.04% | 400 | 1991147773.9056
| iii | 400KV TR. LINE (LOC-182 TO ERASAMA) | 834077130.6955 | 150133883.5252 | 984211014.2207 | 843425920.7396 | 151816665.7331 | 995242586.4728 | 11031572.2521 | 1.121%
| 2 | Schedule - VIIB - Part-II Erection Component of the Works Contract for SS & Line | 81019459.5837 | 14583502.7251 | 95602962.3088 | 90420454.0769 | 16275681.7338 | 106696135.8107 | 11093173.5019 | 11.6%
| i | 220KV BAY EXTENSION AT PARADEEP | 2768625.7432 | 498352.6338 | 3266978.377 | 3006267.0419 | 541128.0675 | 3547395.1094 | 280416.7325 | 8.583%
| ii | 220KV TR. LINE FROM PARADEEP - ERASAMA | 16505202.031 | 2970936.3656 | 19476138.3966 | 23620508.1594 | 4251691.4687 | 27872199.628 | 8396061.2315 | 43.11%
| iii | 400KV TR. LINE (LOC-182 TO ERASAMA) | 61745631.8096 | 11114213.7257 | 72859845.5353 | 63793678.8757 | 11482862.1976 | 75276541.0733 | 2416695.538 | 3.317%
| 3 | Schedule - VIIC - Part-III Civil Work Component of the Works Contract for SS & Line | 733932529.1018 | 132107855.2383 | 866040384.3401 | 1111462638.9929 | 200063275.0187 | 1311525914.0116 | 445485529.6715 | 51.44%
| i | 220KV BAY EXTENSION AT PARADEEP | 27711429.3427 | 4988057.2817 | 32699486.6244 | 20557630.5356 | 3700373.4964 | 24258004.032 | -8441482.5924 | -25.82%
| ii | 220KV TR. LINE FROM PARADEEP - ERASAMA | 122276432.8626 | 22009757.9153 | 144286190.7778 | 310711240.356 | 55928023.2641 | 366639263.6201 | 222353072.8423 | 154.1%
| iii | 400KV TR. LINE (LOC-182 TO ERASAMA) | 583944666.8965 | 105110040.0414 | 689054706.9379 | 780193768.1013 | 140434878.2582 | 920628646.3595 | 231573939.4216 | 33.61%
| TOTAL CONTRACT PRICE |  | 1977603089.826 | 355968556.1687 | 2333571645.9947 | 2514573033.7592 | 452623146.0767 | 2967196179.8358 | 633624533.8411 | 27.15% | 27.1526 | 633624533.8411
|  | Increase in Supply component for both S/s and line | 12.9%
|  | Increase in Erection component for both S/s and line | 11.6% | [5 empty] | `
|  | Increase in Civil component for both S/s and line | 51.44%
|  | Overal increse in Quantity | 27.15%

## S_220KV Bay
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1
SUPPLY - 220kV BAY
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Cost Data Rate | Least Cost | Amount
1 | 245 KV,1200-600-300A,40KA,5CORE SINGLE PHASE CURRENT TRANSFORMER(4 PS Cl & 1 0.2s Cl) | NOS | 314137.6551 | 6 | 1884825.9304 | 339268.6675 | 2224094.5979 | 6 | 1884825.9304 | 0 | 0% | 6 | 1884825.9304 | 0 |  | 0 | 0 | 1884825.9304 | 339268.6675 | 2224094.5979 | 0
2 | 245 KV,2000A,40KA,ISOLATORS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | S/I WITH OUT EARTH SWITCH | NOS | 511595.6097 | 6 | 3069573.6581 | 552523.2585 | 3622096.9166 | 6 | 3069573.6581 | 0 | 0% | 6 | 3069573.6581 | 0 |  | 0 | 0 | 3069573.6581 | 552523.2585 | 3622096.9166 | 0
2.2 | S/I WITH SINGLE EARTH SWITCH | NOS | 615453.365 | 2 | 1230906.7301 | 221563.2114 | 1452469.9415 | 2 | 1230906.7301 | 0 | 0% | 2 | 1230906.7301 | 0 |  | 0 | 0 | 1230906.7301 | 221563.2114 | 1452469.9415 | 0
2.3 | BEAM MOUNTED S/I WITHOUT EARTH SWITCH | NOS | 518006.58 | 2 | 1036013.16 | 186482.3688 | 1222495.5288 | 2 | 1036013.16 | 0 | 0% | 2 | 1036013.16 | 0 |  | 0 | 0 | 1036013.16 | 186482.3688 | 1222495.5288 | 0
3 | 245 KV, 4400pF, 3CORE, SINGLE PHASE CAPACITOR VOLTAGE TRANSFORMER | NOS | 186559.7859 | 6 | 1119358.7151 | 201484.5687 | 1320843.2839 | 6 | 1119358.7151 | 0 | 0% | 6 | 1119358.7151 | 0 |  | 0 | 0 | 1119358.7151 | 201484.5687 | 1320843.2839 | 0
4 | 245KV, 3150A, 40KA, SF6,CIRCUIT BREAKER WITH SUPPORTING STRUCTURE | NOS | 1474523.6871 | 2 | 2949047.3741 | 530828.5273 | 3479875.9015 | 2 | 2949047.3741 | 0 | 0% | 2 | 2949047.3741 | 0 |  | 0 | 0 | 2949047.3741 | 530828.5273 | 3479875.9015 | 0
5 | 216KV metal oxide polymer housed surge arrrestor, 10KA Long duration discharge class III at 216KV, pressure relief Design B & thermal energy (Wth) & Repetitive charge transfer(Qrs) as per latest IEC, as per technical specification. | NOS | 83342.6432 | 6 | 500055.8591 | 90010.0546 | 590065.9137 | 6 | 500055.8591 | 0 | 0% | 6 | 500055.8591 | 0 |  | 0 | 0 | 500055.8591 | 90010.0546 | 590065.9137 | 0
6 | 220 KV Post Insulators | NOS | 24361.6957 | 16 | 389787.1312 | 70161.6836 | 459948.8148 | 18 | 438510.5226 | 2 | 12.5% | 18 | 438510.5226 | 0 |  | 0 | 0 | 438510.5226 | 78931.8941 | 517442.4167 | 57493.6019
7 | BUS BAR & CIRCUIT MATERIALS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | LONG ROD ANTIFOG TYPE PORCELAIN INSULATOR |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | 160 KN INSULATOR | NOS | 15543.3375 | 50 | 777166.8768 | 139890.0378 | 917056.9146 | 50 | 777166.8768 | 0 | 0% | 50 | 777166.8768 | 0 |  | 0 | 0 | 777166.8768 | 139890.0378 | 917056.9146 | 0
7.1.2 | 90 KN INSULATOR | NOS | 11302.3072 | 25 | 282557.6792 | 50860.3822 | 333418.0614 | 25 | 282557.6792 | 0 | 0% | 25 | 282557.6792 | 0 |  | 0 | 0 | 282557.6792 | 50860.3822 | 333418.0614 | 0
7.2 | ACSR MOOSE CONDUCTOR | KMS | 468000.9963 | 1.5 | 702001.4945 | 126360.269 | 828361.7635 | 2 | 936001.9927 | 0.5 | 33.33% | 1.875 | 877501.8681 | 0.125 | 409923 | 409923 | 51240.375 | 928742.2431 | 167173.6038 | 1095915.8469 | 267554.0834 | Increse of quantity as per the approved layout. (Item No 18 of cost data 23-24)
8 | HARDWARES & FITTINGS/SPACERS/CLAMP & CONNECTORS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
8.1 | 220 KV Double Tension( 160KN) H/W fitting for twin moose ACSR | NOS | 7113.6113 | 12 | 85363.3352 | 15365.4003 | 100728.7355 | 12 | 85363.3352 | 0 | 0% | 12 | 85363.3352 | 0 |  | 0 | 0 | 85363.3352 | 15365.4003 | 100728.7355 | 0
8.2 | 220 KV Single Tension(160KN) H/W fitting for single moose ACSR | NOS | 3678.9194 | 24 | 88294.0655 | 15892.9318 | 104186.9973 | 24 | 88294.0655 | 0 | 0% | 24 | 88294.0655 | 0 |  | 0 | 0 | 88294.0655 | 15892.9318 | 104186.9973 | 0
8.3 | 220 KV Double Suspension(90 KN)H/W fitting for twin mose ACSR | NOS | 7764.8847 | 6 | 46589.308 | 8386.0754 | 54975.3835 | 6 | 46589.308 | 0 | 0% | 6 | 46589.308 | 0 |  | 0 | 0 | 46589.308 | 8386.0754 | 54975.3835 | 0
8.4 | 220 KV Single Suspension(90 KN)H/W fitting for single mose ACSR | NOS | 3384.2957 | 12 | 40611.5486 | 7310.0787 | 47921.6273 | 12 | 40611.5486 | 0 | 0% | 12 | 40611.5486 | 0 |  | 0 | 0 | 40611.5486 | 7310.0787 | 47921.6273 | 0
8.5 | T- clamp for ACSR ZEBRA run to ACSR MOOSE drop | NOS | 897.4392 | 20 | 17948.7848 | 3230.7813 | 21179.5661 | 24 | 21538.5418 | 4 | 20% | 24 | 21538.5418 | 0 |  | 0 | 0 | 21538.5418 | 3876.9375 | 25415.4793 | 4235.9132 | Increse of quantity as per the approved layout.
8.6 | T-Clamp for single Moose -Single Moose ACSR | NOS | 897.4392 | 10 | 8974.3924 | 1615.3906 | 10589.7831 | 24 | 21538.5418 | 14 | 140% | 13 | 11666.7101 | 11 |  | 897.4392 | 9871.8317 | 21538.5418 | 3876.9375 | 25415.4793 | 14825.6963 | Increse of quantity as per the approved layout. (Cost data NA)
8.7 | T-Clamp for twin Moose run -Single Moose drop ACSR | NOS | 1299.6393 | 12 | 15595.672 | 2807.221 | 18402.893 | 12 | 15595.672 | 0 | 0% | 12 | 15595.672 | 0 |  | 0 | 0 | 15595.672 | 2807.221 | 18402.893 | 0
8.8 | 220 KV PI clamp | NOS | 1602.9854 | 16 | 25647.7668 | 4616.598 | 30264.3649 | 18 | 28853.7377 | 2 | 12.5% | 18 | 28853.7377 | 0 |  | 0 | 0 | 28853.7377 | 5193.6728 | 34047.4105 | 3783.0456
8.9 | Spacer for Moose ACSR | NOS | 1090.3015 | 50 | 54515.0727 | 9812.7131 | 64327.7858 | 50 | 54515.0727 | 0 | 0% | 50 | 54515.0727 | 0 |  | 0 | 0 | 54515.0727 | 9812.7131 | 64327.7858 | 0
8.10 | 220 KV Isolator pad clamp | NOS | 1218.2302 | 60 | 73093.8095 | 13156.8857 | 86250.6952 | 60 | 73093.8095 | 0 | 0% | 60 | 73093.8095 | 0 |  | 0 | 0 | 73093.8095 | 13156.8857 | 86250.6952 | 0
8.11 | 220 KV LA Clamp | NOS | 1090.3015 | 6 | 6541.8087 | 1177.5256 | 7719.3343 | 6 | 6541.8087 | 0 | 0% | 6 | 6541.8087 | 0 |  | 0 | 0 | 6541.8087 | 1177.5256 | 7719.3343 | 0
8.12 | 220 KV CB Clamp | NOS | 1347.128 | 12 | 16165.5362 | 2909.7965 | 19075.3328 | 12 | 16165.5362 | 0 | 0% | 12 | 16165.5362 | 0 |  | 0 | 0 | 16165.5362 | 2909.7965 | 19075.3328 | 0
8.13 | 220 KV CVT Clamp | NOS | 1347.128 | 6 | 8082.7681 | 1454.8983 | 9537.6664 | 6 | 8082.7681 | 0 | 0% | 6 | 8082.7681 | 0 |  | 0 | 0 | 8082.7681 | 1454.8983 | 9537.6664 | 0
8.14 | 220 KV CT Clamp | NOS | 1347.128 | 6 | 8082.7681 | 1454.8983 | 9537.6664 | 12 | 16165.5362 | 6 | 100% | 8 | 10777.0242 | 4 |  | 1347.128 | 5388.5121 | 16165.5362 | 2909.7965 | 19075.3328 | 9537.6664 | Cosidered for 6 nos. of CT (Cost data NA)
8.15 | PG Clamp for ACSR Moose | NOS | 1090.3015 | 20 | 21806.0291 | 3925.0852 | 25731.1143 | 20 | 21806.0291 | 0 | 0% | 20 | 21806.0291 | 0 |  | 0 | 0 | 21806.0291 | 3925.0852 | 25731.1143 | 0
| 160KN Porcelain Antifog Disc Insulator | No.s | [5 empty] | 84 |  | 84 | 0% | 0 | 0 | 84 | 797.6 | 797.6 | 66998.4 | 66998.4 | 12059.712 | 79058.112 | 79058.112 | Item No 53 fo cost data 23-24
9 | SUBSTATION EARTHING SYSTEMS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9.1 | EARTHING CONDUCTOR FOR BURRIAL : 75X10 mm GI Flat for laying (spacing maximum 5m both way) | MT | 83342.6432 | 8.1875 | 682367.8911 | 122826.2204 | 805194.1114 | 14.6 | 1216802.5905 | 6.4125 | 78.32% | 10.2344 | 852959.8638 | 4.3656 | 91000 | 83342.6432 | 363842.7266 | 1216802.5905 | 219024.4663 | 1435827.0567 | 630632.9453 | Exact rate not available, S/S str. MS RC rate considered.
9.2 | EARTHING CONDUCTOR: 50X6 mm GI Flat for Raiser from the burial earth mat to equipment,structure etc) | MT | 83342.6432 | 5.1 | 425047.4802 | 76508.5464 | 501556.0267 | 5.1 | 425047.4802 | 0 | 0% | 5.1 | 425047.4802 | 0 |  | 0 | 0 | 425047.4802 | 76508.5464 | 501556.0267 | 0
9.3 | EARTHING DEVICE & ASSOCIATED ACCESSORIES (50 mm heavy duty GI PERFORATED PIPE 3 mtrs long for treated earth pit) | Nos. | 2885.1799 | 30 | 86555.3981 | 15579.9717 | 102135.3698 | 30 | 86555.3981 | 0 | 0% | 30 | 86555.3981 | 0 |  | 0 | 0 | 86555.3981 | 15579.9717 | 102135.3698 | 0
9.4 | EARTHING DEVICE & ASSOCIATED ACCESSORIES 40mm MS rod 3 mtrs long for non treated earth pit) | Nos. | 2500.4247 | 30 | 75012.7401 | 13502.2932 | 88515.0333 | 28 | 70011.8907 | -2 | -6.667% | 28 | 70011.8907 | 0 |  | 0 | 0 | 70011.8907 | 12602.1403 | 82614.0311 | -5901.0022
10 | G.I Cable Trays including support GI angle suitable for different sections i.e. Section:1-1,2-2,3-3 & 4-4 along with its accessories as per TS. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | G.I Cable Trays(size: 450x75x2500mm) | MTRS | 1006.954 | 500 | 503476.9828 | 90625.8569 | 594102.8397 | 0 | 0 | -500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -594102.8397
10.2 | G.I Cable Trays(size: 300x75x2500mm) | MTRS | 833.4749 | 500 | 416737.4448 | 75012.7401 | 491750.1849 | 1120 | 933491.8764 | 620 | 124% | 625 | 520921.806 | 495 |  | 833.4749 | 412570.0704 | 933491.8764 | 168028.5378 | 1101520.4142 | 609770.2293
10.3 | G.I Cable Trays(size: 150x75x2500mm) | MTRS | 577.6175 | 200 | 115523.4963 | 20794.2293 | 136317.7257 | 550 | 317689.6149 | 350 | 175% | 250 | 144404.3704 | 300 |  | 577.6175 | 173285.2445 | 317689.6149 | 57184.1307 | 374873.7456 | 238556.0199 | Incresed as per the approved layout & cable schedule
10.4 | Support G. I angle 50x50x6 mm for cable tray | MT | 83342.6432 | 1 | 83342.6432 | 15001.6758 | 98344.319 | 2 | 166685.2864 | 1 | 100% | 1.25 | 104178.304 | 0.75 | 91000 | 83342.6432 | 62506.9824 | 166685.2864 | 30003.3515 | 196688.6379 | 98344.319 | Exact rate not available, S/S str. MS RC rate considered.
11 | SUB STATION SWITCYARD BMK,AC CONSOLE & OTHER MARSHALLING BOXES (The boxes shall be 3mm thick Al. Alloy) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | BAY MARSHALLING KIOSK (01 nos on 220 kV bay ) | NOS | 74367.2816 | 1 | 74367.2816 | 13386.1107 | 87753.3923 | 1 | 74367.2816 | 0 | 0% | 1 | 74367.2816 | 0 |  | 0 | 0 | 74367.2816 | 13386.1107 | 87753.3923 | 0
11.2 | SWITCH YARD AC CONSOLE FOR LIGHTING (01 no in 220 kV bay ) | NOS | 15386.3341 | 1 | 15386.3341 | 2769.5401 | 18155.8743 | 1 | 15386.3341 | 0 | 0% | 1 | 15386.3341 | 0 |  | 0 | 0 | 15386.3341 | 2769.5401 | 18155.8743 | 0
11.3 | SWITCH YARD RECEPTACLE BOARD FOR WELDING & OTHER EMERGENCY (01 nos on 220 KV BAY) | NOS | 57698.753 | 1 | 57698.753 | 10385.7755 | 68084.5285 | 1 | 57698.753 | 0 | 0% | 1 | 57698.753 | 0 |  | 0 | 0 | 57698.753 | 10385.7755 | 68084.5285 | 0
11.4 | CONSOLE BOX FOR CT, PT, CVT | NOS | 19874.4995 | 4 | 79497.998 | 14309.6396 | 93807.6376 | 4 | 79497.998 | 0 | 0% | 4 | 79497.998 | 0 |  | 0 | 0 | 79497.998 | 14309.6396 | 93807.6376 | 0
12 | SWITCH YARD STRUCTURES (LATTICE TYPE) FOR TOWER COLUMNS WITH SPIKES & BEAMS & FOR ALL EQUIPMENTS FOR 220 KV CLASS INCLUDING FOUNDATION BOLTS & NUTS. (Galvanization thisckness shall be minimum 910gm/sqm as these are to be installed in coastal area) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.1 | DIFFERENT TYPES OF COLUMNS WITH DETAILS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.1.1 | P1S-220 KV (NOMINAL UNIT WT- 4.5 MT) (07 NOS.) | MT |  | 31.5 | 0 | 0 | 0 | 31.5 | 0 | 0 | 0% | 31.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.2 | DIFFERENT TYPE OF BEAMS WITH DETAILS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.2.1 | Q1-220KV (NOMINAL UNIT WT- 1.5 MT) (06 NOS.) | MT |  | 9 | 0 | 0 | 0 | 12 | 0 | 3 | 0% | 11.25 | 0 | 0.75 |  | 0 | 0 | 0 | 0 | 0 | 0
12.2.2 | Q3-220KV (NOMINAL UNIT WT-2.5 MT) (02 NOS.) | MT |  | 5 | 0 | 0 | 0 | 12.5 | 0 | 7.5 | 0% | 6.25 | 0 | 6.25 |  | 0 | 0 | 0 | 0 | 0 | 0
12.3 | TOTAL WEIGHT OF COLUMN & BEAM | MT | 84767.3037 | 45.5 | 3856912.3206 | 694244.2177 | 4551156.5383 | 56 | 4746969.01 | 10.5 | 23.08% | 56 | 4746969.01 | 0 |  | 0 | 0 | 4746969.01 | 854454.4218 | 5601423.4318 | 1050266.8935
12.4 | EQUIPMENT SUPPORT STRUCTURES (LATTICE TYPE) FOR ALL 220KV, 132 KV & 33KV EQUIPMENTS INCLUDING FOUNDATION BOLTS & NUTS. (Galvanization thisckness shall be minimum 910gm/sqm as these are to be installed in coastal area) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.1 | ISOLATORS-220KV ( SI with E/S -02 Nos.) | MT |  | 2.542 | 0 | 0 | 0 | 2.952 | 0 | 0.41 | 0% | 2.952 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.2 | ISOLATORS-220KV ( SI without E/S -06 Nos.) | MT |  | 7.626 | 0 | 0 | 0 | 8.331 | 0 | 0.705 | 0% | 8.331 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.3 | CTS-220 KV (06 nos.) | MT |  | 1.35 | 0 | 0 | 0 | 1.578 | 0 | 0.228 | 0% | 1.578 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.4 | CVTS-220 KV (06 nos.) | MT |  | 1.476 | 0 | 0 | 0 | 1.343 | 0 | -0.133 | 0% | 1.343 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.5 | Surge Arrester-220 KV ( 06 nos.) | MT |  | 1.7526 | 0 | 0 | 0 | 2.506 | 0 | 0.7534 | 0% | 2.1908 | 0 | 0.31525 |  | 0 | 0 | 0 | 0 | 0 | 0
12.4.6 | BPI-220 KV (16 nos.) | MT |  | 4.6848 | 0 | 0 | 0 | 5.379 | 0 | 0.6942 | 0% | 5.379 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12.5 | TOTAL WEIGHT OF EQUIPMENT STRUCTURE | MT | 84767.3037 | 19.4314 | 1647147.3861 | 296486.5295 | 1943633.9156 | 22.089 | 1872424.9725 | 2.6576 | 13.68% | 22.089 | 1872424.9725 | 0 |  | 0 | 0 | 1872424.9725 | 337036.4951 | 2209461.4676 | 265827.552
12.6 | Total weight of GI Nuts and bolts for Columns, Beams & Equipment Structures | MT | 112310.7414 | 3.2466 | 364624.6836 | 65632.4431 | 430257.1267 | 4 | 449242.9655 | 0.75343 | 23.21% | 4 | 449242.9655 | 0 |  | 0 | 0 | 449242.9655 | 80863.7338 | 530106.6993 | 99849.5726
13 | GENERAL EQUIPMENT & SUBSTATION ACCESSORIES |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13.1 | POWER CABLES,1.1KV,XLPE & PVC ARMOURED, ALUMINIUM CONDUCTOR (As per Specification) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13.1.1 | PVC 3.5 CX70 mm2 | MTR | 377.002 | 500 | 188501.007 | 33930.1813 | 222431.1883 | 500 | 188501.007 | 0 | 0% | 500 | 188501.007 | 0 |  | 0 | 0 | 188501.007 | 33930.1813 | 222431.1883 | 0
13.1.2 | PVC 3.5 C X 35 mm2 | MTR | 219.0294 | 500 | 109514.7239 | 19712.6503 | 129227.3742 | 500 | 109514.7239 | 0 | 0% | 500 | 109514.7239 | 0 |  | 0 | 0 | 109514.7239 | 19712.6503 | 129227.3742 | 0
13.1.3 | PVC 4 CX 16 mm2 | MTR | 170.5716 | 1000 | 170571.6053 | 30702.889 | 201274.4943 | 1000 | 170571.6053 | 0 | 0% | 1000 | 170571.6053 | 0 |  | 0 | 0 | 170571.6053 | 30702.889 | 201274.4943 | 0
13.1.4 | PVC 4CX 6 sqmm | MTR | 139.5586 | 1000 | 139558.5862 | 25120.5455 | 164679.1317 | 1000 | 139558.5862 | 0 | 0% | 1000 | 139558.5862 | 0 |  | 0 | 0 | 139558.5862 | 25120.5455 | 164679.1317 | 0 | As per the approved cable schedule
13.1.5 | PVC 2CX 6 sqmm | MTR | 102.7306 | 500 | 51365.313 | 9245.7563 | 60611.0693 | 500 | 51365.313 | 0 | 0% | 500 | 51365.313 | 0 |  | 0 | 0 | 51365.313 | 9245.7563 | 60611.0693 | 0
13.2 | CONTROL CABLES,1.1 KV, PVC,FRLS STRANDED COPPER, ARMOURED (As per specification) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13.2.1 | 2 CX 2.5 mm2 | MTR | 118.2371 | 1000 | 118237.1355 | 21282.6844 | 139519.8199 | 1000 | 118237.1355 | 0 | 0% | 1000 | 118237.1355 | 0 |  | 0 | 0 | 118237.1355 | 21282.6844 | 139519.8199 | 0
13.2.2 | 4 CX 2.5 mm2 | MTR | 187.0473 | 4000 | 748189.087 | 134674.0357 | 882863.1227 | 4000 | 748189.087 | 0 | 0% | 4000 | 748189.087 | 0 |  | 0 | 0 | 748189.087 | 134674.0357 | 882863.1227 | 0
13.2.3 | 5 CX 2.5 mm2 | MTR | 225.8135 | 2500 | 564533.8642 | 101616.0956 | 666149.9598 | 2500 | 564533.8642 | 0 | 0% | 2500 | 564533.8642 | 0 |  | 0 | 0 | 564533.8642 | 101616.0956 | 666149.9598 | 0
13.2.4 | 7CX 2.5 mm2 | MTR | 285.9013 | 2000 | 571802.5406 | 102924.4573 | 674726.9979 | 2000 | 571802.5406 | 0 | 0% | 2000 | 571802.5406 | 0 |  | 0 | 0 | 571802.5406 | 102924.4573 | 674726.9979 | 0
13.2.5 | 10 CX 2.5 mm2 | MTR | 410.9225 | 5000 | 2054612.5187 | 369830.2534 | 2424442.7721 | 5000 | 2054612.5187 | 0 | 0% | 5000 | 2054612.5187 | 0 |  | 0 | 0 | 2054612.5187 | 369830.2534 | 2424442.7721 | 0
13.2.6 | 12 CX 2.5 mm2 | MTR | 476.8252 | 2500 | 1192062.9236 | 214571.3262 | 1406634.2498 | 2500 | 1192062.9236 | 0 | 0% | 2500 | 1192062.9236 | 0 |  | 0 | 0 | 1192062.9236 | 214571.3262 | 1406634.2498 | 0
13.2.7 | 16 CX 2.5 mm2 | MTR | 615.4146 | 2500 | 1538536.4969 | 276936.5694 | 1815473.0664 | 2500 | 1538536.4969 | 0 | 0% | 2500 | 1538536.4969 | 0 |  | 0 | 0 | 1538536.4969 | 276936.5694 | 1815473.0664 | 0
13.2.8 | 19 CX 2.5 mm2 | MTR | 713.2994 | 2500 | 1783248.6011 | 320984.7482 | 2104233.3494 | 2500 | 1783248.6011 | 0 | 0% | 2500 | 1783248.6011 | 0 |  | 0 | 0 | 1783248.6011 | 320984.7482 | 2104233.3494 | 0
13.2.9 | 4 CX 4 mm2 | MTR | 273.3022 | 1000 | 273302.2313 | 49194.4016 | 322496.6329 | 1000 | 273302.2313 | 0 | 0% | 1000 | 273302.2313 | 0 |  | 0 | 0 | 273302.2313 | 49194.4016 | 322496.6329 | 0
13.2.10 | 7 CX 4 mm2 | MTR | 439.0281 | 250 | 109757.0131 | 19756.2624 | 129513.2754 | 250 | 109757.0131 | 0 | 0% | 250 | 109757.0131 | 0 |  | 0 | 0 | 109757.0131 | 19756.2624 | 129513.2754 | 0
13.2.11 | 12 CX 4 mm2 | MTR | 718.1452 | 250 | 179536.3062 | 32316.5351 | 211852.8413 | 250 | 179536.3062 | 0 | 0% | 250 | 179536.3062 | 0 |  | 0 | 0 | 179536.3062 | 32316.5351 | 211852.8413 | 0
14 | SUB STATION LIGHTING (AS PER SPECIFICATION AND APPROVED DRAWINGS )(Switch yard and other street area) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
14.1 | SUB-STATION SWITCH YARD LIGHTING,IT INCLUDES SUPPLY OF FIXTURES & LAMPS (150W LED) of reputed make (Philips/CGL/Bajaj) with switch gear,GI Conduit etc.(Lighting fixtures are to be fixed rigidly on the Column at a suitable height so that the required lux can be maintained). | SET | 8334.7489 | 15 | 125021.2334 | 22503.822 | 147525.0555 | 15 | 125021.2334 | 0 | 0% | 15 | 125021.2334 | 0 |  | 0 | 0 | 125021.2334 | 22503.822 | 147525.0555 | 0
14.2 | STREET LIGHTING, IT INCLUDES SUPPLY OF GI TUBULAR POLE, WITH 100WATT LED LIGHTING FIXTURES WITH LAMPS of reputed make (Philips/CGL/Bajaj)(TO BE PROVIDED IN THE SWITCH YARD, ALONG THE ROADS (APPROACH INSIDE YARD AND OTHER ROADS). | SET | 22438.8885 | 10 | 224388.8851 | 40389.9993 | 264778.8844 | 10 | 224388.8851 | 0 | 0% | 10 | 224388.8851 | 0 |  | 0 | 0 | 224388.8851 | 40389.9993 | 264778.8844 | 0
15 | FIRE FIGHTING SYSTEM(PORTABLE AND WHEEL MOUNTED SETS FOR CONTROL ROOM, EQUIPMENT LIKE TRANSFORMER AND OTHER AREAS AS PER TECH SPEC(REFER TS-INST TO BIDDER BEFORE DESIGN-SL NO 16-ANNEXURE - I) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
15.1 | FOAM TYPE-9 LTRS | NOS | 3911.517 | 2 | 7823.0341 | 1408.1461 | 9231.1802 | 2 | 7823.0341 | 0 | 0% | 2 | 7823.0341 | 0 |  | 0 | 0 | 7823.0341 | 1408.1461 | 9231.1802 | 0
15.2 | DRY CHEMICAL POWDER(TROLLEY MOUNTED)- 22.5 KGS | NOS | 16411.7021 | 2 | 32823.4041 | 5908.2127 | 38731.6169 | 2 | 32823.4041 | 0 | 0% | 2 | 32823.4041 | 0 |  | 0 | 0 | 32823.4041 | 5908.2127 | 38731.6169 | 0
15.3 | DRY POWDER TYPE - 5 KGS | NOS | 4039.4457 | 2 | 8078.8915 | 1454.2005 | 9533.092 | 2 | 8078.8915 | 0 | 0% | 2 | 8078.8915 | 0 |  | 0 | 0 | 8078.8915 | 1454.2005 | 9533.092 | 0
15.4 | CO2 - 4.5 KGS | NOS | 7565.2384 | 4 | 30260.9534 | 5446.9716 | 35707.9251 | 4 | 30260.9534 | 0 | 0% | 4 | 30260.9534 | 0 |  | 0 | 0 | 30260.9534 | 5446.9716 | 35707.9251 | 0
15.5 | CO2 - 9 KGS | NOS | 13847.3131 | 4 | 55389.2522 | 9970.0654 | 65359.3176 | 4 | 55389.2522 | 0 | 0% | 4 | 55389.2522 | 0 |  | 0 | 0 | 55389.2522 | 9970.0654 | 65359.3176 | 0
15.6 | CO2 (TROLLY MOUNTED)- 22.5 KGS | NOS | 25003.2775 | 2 | 50006.5551 | 9001.1799 | 59007.735 | 2 | 50006.5551 | 0 | 0% | 2 | 50006.5551 | 0 |  | 0 | 0 | 50006.5551 | 9001.1799 | 59007.735 | 0
15.7 | 9 litre water type | Nos. | 2692.3177 | 2 | 5384.6354 | 969.2344 | 6353.8698 | 2 | 5384.6354 | 0 | 0% | 2 | 5384.6354 | 0 |  | 0 | 0 | 5384.6354 | 969.2344 | 6353.8698 | 0
15.8 | 50 Litres Mechanical Foam type | Nos. | 13847.3131 | 2 | 27694.6261 | 4985.0327 | 32679.6588 | 2 | 27694.6261 | 0 | 0% | 2 | 27694.6261 | 0 |  | 0 | 0 | 27694.6261 | 4985.0327 | 32679.6588 | 0
15.9 | FIRE BUCKET (6 NOS IN EACH STAND) WITH STAND AND CANOPY | SET | 6923.6565 | 2 | 13847.3131 | 2492.5163 | 16339.8294 | 2 | 13847.3131 | 0 | 0% | 2 | 13847.3131 | 0 |  | 0 | 0 | 13847.3131 | 2492.5163 | 16339.8294 | 0
16 | 220 KV SIDE AUTOMATION , PROTECTION & OTHER PANELS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| SUBSTATION AUTOMATION SYSTEM: Supply of the following 220 kV level consisting of Panels, Bay control Units, DP Relays, Numerical O/C & E/F Relays, DC Supervision relays, Trip Circuit Supervision, Trip Relay ,Test Block, Differential and REF, Overfluxing, High impednce REF, Numerical O/C & E/F relay,Transformer trouble relay etc. Station level consisting of Industrial Computer with accessories, PC with accessories, laser printer, UPS, GPS System & Numerical bay control unit etc. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
16.1 | Sub-Station Automation (in PRP as per the indicative drg ) system (for 02 nos. 220 KV side line feeder bays ),other accessories ( Relays,auxiliary system, Ethernet Switches ,FO Patch cords, LIU,Multimode glass fibre Doublle jacket armoured optical cables, Red boxes etc . (i) Line Interface Unit(LIU) - as per requirement (for 220KV side),(ii)Managed Ethernet switch IEC 61850-3, IEEE1588v2 as per requirement,(iii) Multimode glass fibre optical cord Double Jacketted armoured, rodent sillient of required length,(iv) HDPE pipes for laying of FO cable of required length in all respect to integrate with the existing SAS system. | LS | 2372059.8444 | 1 | 2372059.8444 | 426970.772 | 2799030.6164 | 1 | 2372059.8444 | 0 | 0% | 1 | 2372059.8444 | 0 |  | 0 | 0 | 2372059.8444 | 426970.772 | 2799030.6164 | 0
16.2 | 220 KV SIDE PROTECTION & OTHER PANELS for SAS and Bus Bar protn. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
16.2.1 | BCU based FEEDER PROTECTION RELAY PANEL (MAIN-I , MAIN-II & BACK-UP PROTECTION WITH AUTO RECLOSURE DISTANCE PROTECTION with Numerical Bay control unit (BCU) (48DI, 32DO, IEC 61850 protocol with PRP ) for substation automation system. | Nos. | 1570688.2754 | 2 | 3141376.5507 | 565447.7791 | 3706824.3298 | 2 | 3141376.5507 | 0 | 0% | 2 | 3141376.5507 | 0 |  | 0 | 0 | 3141376.5507 | 565447.7791 | 3706824.3298 | 0
16.2.2 | Bus Bar Protection system in all respect to integrate with the existing system for above two nos 220 KV Line Feeders (including supply of relays,auxiliary relays,switches,FO cables,Managed Switches etc). | Nos. | 705206.9808 | 2 | 1410413.9615 | 253874.5131 | 1664288.4746 | 2 | 1410413.9615 | 0 | 0% | 2 | 1410413.9615 | 0 |  | 0 | 0 | 1410413.9615 | 253874.5131 | 1664288.4746 | 0
17 | WALKIE TALKIE SET | SET | 5770.3599 | 1 | 5770.3599 | 1038.6648 | 6809.0247 | 1 | 5770.3599 | 0 | 0% | 1 | 5770.3599 | 0 |  | 0 | 0 | 5770.3599 | 1038.6648 | 6809.0247 | 0
18 | BEST QUALITY &APPROVED MAKE INSULATING MAT (Confirming to IS:15652:2006) TO BE KEPT INFRONT OF ALL PANELS,BOARDS ETC.(2000X1000X3)mm Size | NO | 4488.1654 | 4 | 17952.6615 | 3231.4791 | 21184.1405 | 4 | 17952.6615 | 0 | 0% | 4 | 17952.6615 | 0 |  | 0 | 0 | 17952.6615 | 3231.4791 | 21184.1405 | 0
19 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
19.1 | 24 fibre optic approach cable along with installation hardware including HDPE pipes | KM | 189764.7876 | 1 | 189764.7876 | 34157.6618 | 223922.4493 | 2.5 | 474411.9689 | 1.5 | 150% | 1.25 | 237205.9844 | 1.25 | 175983.59 | 175983.59 | 219979.4875 | 457185.4719 | 82293.3849 | 539478.8569 | 315556.4076 | Item 31+32 of OPTCL CD 23-24
19.2 | Digital tele-protection coupler compatible for interfacing with SDHMUX installed at 400KV Easama grid S/S and Duburi New grid S/s | NO | 375682.9916 | 2 | 751365.9832 | 135245.877 | 886611.8601 | 2 | 751365.9832 | 0 | 0% | 2 | 751365.9832 | 0 |  | 0 | 0 | 751365.9832 | 135245.877 | 886611.8601 | 0
19.3 | Supply of FODP(Fibre Optic Distribution panel) 48F: Indoor type, rack mounted with FCPC coupling and pig tails(DWSM Fibre) | NO | 66674.1145 | 1 | 66674.1145 | 12001.3406 | 78675.4552 | 1 | 66674.1145 | 0 | 0% | 1 | 66674.1145 | 0 |  | 0 | 0 | 66674.1145 | 12001.3406 | 78675.4552 | 0
A | SUPPLY COMPONENT OF THE WORKS CONTRACT FOR SUBSTATION-220 KV BAY EXTENSION |  |  |  | 41271733.1086 | 7428911.9596 | 48700645.0682 |  | 43894719.4432 |  | 0% |  | 42571547.9666 |  |  |  | 1365683.6302 | 43937231.5967 | 7908701.6874 | 51845933.2841 | 3145288.2159

## S_220kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1 | [19 empty] | SUPPLY - 220kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Cost Data Rate | Least Cost | Amount
1 | SUPPLY of Following type tested Lattice type Galvanized steel tangent / Angle tower with stubs and cleats, different type of G.I HT Nuts & Bolts, washer, spring washer for the towers, hanger and all accessories, tower super structure complete including step bolts. Supply of black bituminous paint for three coats up to a height of 500mm above the cooping(legs & bracing members). All Supply should confirm to the Technical Specificationand designed for Wind Zone-6 i.e. Wind Speed of 55 Mtr/Sec. (Galvanization thisckness shall be minimum 910gm/sqm as these are to be installed in coastal area). Note: Weight as indicated are tentative |  |  |  | 0 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
1.1 | STUBS & CLEATS |  |  |  | 0 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | OA TYPE(NOMINAL UNIT WEIGHT 0.232 MT) | Nos |  | 89 | 0 | 0 | 0 | 78 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | OB TYPE (NOMINAL UNIT WEIGHT 0.437 MT) | Nos |  | 24 | 0 | 0 | 0 | 28 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | OC TYPE (NOMINAL UNIT WEIGHT 0.776 MT) | Nos |  | 15 | 0 | 0 | 0 | 28 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.4 | OC+15/24 Type (NOMINAL UNIT WEIGHT 1.068 MT) | Nos |  | 2 | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.5 | UR TYPE (NOMINAL UNIT WEIGHT 0.697 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0
1.2 | TOWER SUPER STRUCTURES |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | OA TYPE (SUSPENSION) TOWERS (NOMINAL UNIT WEIGHT 4.242 MT) | Nos |  | 89 | 0 | 0 | 0 | 78 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | +3 EXTENSION (NOMINAL UNIT WEIGHT 0.725MT) | Nos |  | 16 | 0 | 0 | 0 | 23 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.3 | +6 EXTENSION (NOMINAL UNIT WEIGHT 1.448 MT) | Nos |  | 6 | 0 | 0 | 0 | 9 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.4 | OB TYPE (30 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 6.343 MT) | Nos |  | 24 | 0 | 0 | 0 | 28 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.5 | +3 EXTENSION (NOMINAL UNIT WEIGHT 1.242 MT) | Nos |  | 3 | 0 | 0 | 0 | 14 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
New | + 6 EXTENSION | Nos | [5 empty] | 2 | 0
1.2.6 | OC TYPE (60 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 9.01MT) | Nos |  | 15 | 0 | 0 | 0 | 28 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
New | + 3 EXTENSION | Nos | [5 empty] | 5 | 0
1.2.7 | +6 EXTENSION (NOMINAL UNIT WEIGHT 2.597 MT) | Nos |  | 2 | 0 | 0 | 0 | 11 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.8 | OC+15 EXTENSION (NOMINAL UNIT WEIGHT 8.55 MT) | Nos |  | 2 | 0 | 0 | 0 | 4 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.9 | UR TYPE (60 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 12.474 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.10 | UR+6 EXTENSION (NOMINAL UNIT WEIGHT 4.148 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3 | TEMPLATES (Hot dip galvanised) Note: Weight as indicated are tentative |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 | OA (NOMINAL UNIT WEIGHT 0.579 MT) | Nos |  | 8 | 0 | 0 | 0 | 15 | 0 |  | 0% |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.2 | OB (NOMINAL UNIT WEIGHT 0.815 MT) | Nos |  | 5 | 0 | 0 | 0 | 5 | 0 |  | 0% |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.3 | OC (NOMINAL UNIT WEIGHT 0.984 MT) | Nos |  | 5 | 0 | 0 | 0 | 5 | 0 |  | 0% |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.4 | OC+15/24 (NOMINAL UNIT WEIGHT 2.073 MT) | Nos |  | 1 | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.5 | UR+6 (NOMINAL UNIT WEIGHT 1.510 MT) | Nos |  | 1 | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.4 | WEIGHT OF THE STRUCTURES & Tempates including Tower Stub | MT | 78929.1029 | 825.307 | 65140741.1225 | 11725333.4021 | 76866074.5246 | 1291.4206 | 101930669.4174 | 466.1136 | 56.48% | 1031.6337 | 81425926.4032 | 259.7868 | 88000 | 78929.1029 | 20504743.0143 | 101930669.4174 | 18347520.4951 | 120278189.9126 | 43412115.388 | As per the approved structure drawing & route alignment RC rate considered
1.5 | Weight of different type G.I Nuts and Bolts | MT | 95909.7 | 41.265 | 3957713.772 | 712388.479 | 4670102.2509 | 54.7334 | 5249468.7714 | 13.4684 | 32.64% | 51.5812 | 4947142.215 | 3.1522 | 115450 | 95909.7 | 302326.5565 | 5249468.7714 | 944904.3789 | 6194373.1503 | 1524270.8994 | As per approved structure drawing RC rate considered
1.6 | Conducting type test on designed Transmission line towers suitable for Wind Zone-VI: a) Preparation of Structural drawings, fabrication drawing, Shop floor drawings, proto-corrected structural & shop floor drawings and Bill of material with Single line diagram of Tower; b) Fabrication, galvanization and proto-assembly of Steel tower structures as per approved structural drawings. c) Transportation of Tower Structures including BOM verification at the Tower testing beds of Testing Lab. d) In case of pre-mature failure (major/minor) the following activities are required to be carried out by the manufacturer: • Modification in structural drawings, shop drawings and BOM as per revision of the tower design • Fabrication, galvanization, transportation of the modified members to the testing agency Laboratories. e) Lifting back the scrap tower material after completion of tests including loading and transportation from Testing Agency Laboratories. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.6.1 | OA type Tower | Nos | 2388197.2751 | 1 | 2388197.2751 | 429875.5095 | 2818072.7846 | 1 | 2388197.2751 | 0 | 0% | 1 | 2388197.2751 | 0 |  | 0 | 0 | 2388197.2751 | 429875.5095 | 2818072.7846 | 0
1.6.2 | OB Type Tower | Nos | 2880481.4654 | 1 | 2880481.4654 | 518486.6638 | 3398968.1292 | 1 | 2880481.4654 | 0 | 0% | 1 | 2880481.4654 | 0 |  | 0 | 0 | 2880481.4654 | 518486.6638 | 3398968.1292 | 0
1.6.3 | OC Type Tower | Nos | 3694248.5506 | 1 | 3694248.5506 | 664964.7391 | 4359213.2897 | 1 | 3694248.5506 | 0 | 0% | 1 | 3694248.5506 | 0 |  | 0 | 0 | 3694248.5506 | 664964.7391 | 4359213.2897 | 0
1.6.4 | UR Type Tower | Nos | 4343791.0386 | 1 | 4343791.0386 | 781882.3869 | 5125673.4256 | 0 | 0 | -1 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -5125673.4256
2 | Supply of the following tower accessories as per technical specification and as directed by the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | EARTHING DEVICE | Nos. | 2564.389 | 173 | 443639.3006 | 79855.0741 | 523494.3747 | 142 | 364143.241 | -31 | -17.92% | 142 | 364143.241 | 0 |  | 0 | 0 | 364143.241 | 65545.7834 | 429689.0244 | -93805.3504
2.2 | DANGER BOARD | Nos. | 277.1789 | 131 | 36310.4305 | 6535.8775 | 42846.308 | 134 | 37141.9671 | 3 | 2.29% | 134 | 37141.9671 | 0 |  | 0 | 0 | 37141.9671 | 6685.5541 | 43827.5211 | 981.2132
2.3 | NUMBER PLATE | Nos. | 146.3427 | 131 | 19170.8916 | 3450.7605 | 22621.6521 | 134 | 19609.9197 | 3 | 2.29% | 134 | 19609.9197 | 0 |  | 0 | 0 | 19609.9197 | 3529.7855 | 23139.7052 | 518.0531
2.4 | PHASE PLATE | Nos. | 215.1528 | 786 | 169110.1168 | 30439.821 | 199549.9378 | 810 | 174273.7845 | 24 | 3.053% | 810 | 174273.7845 | 0 |  | 0 | 0 | 174273.7845 | 31369.2812 | 205643.0657 | 6093.1279
2.5 | BIRD GUARD | Nos. | 274.2714 | 534 | 146460.9213 | 26362.9658 | 172823.8871 | 468 | 128359.0096 | -66 | -12.36% | 468 | 128359.0096 | 0 |  | 0 | 0 | 128359.0096 | 23104.6217 | 151463.6314 | -21360.2557
2.6 | ANTICLIMBING DEVICE | Nos. | 5770.3599 | 131 | 755917.1437 | 136065.0859 | 891982.2296 | 135 | 778998.5832 | 4 | 3.053% | 135 | 778998.5832 | 0 |  | 0 | 0 | 778998.5832 | 140219.745 | 919218.3282 | 27236.0986
2.7 | CIRCUIT PLATE | Nos. | 146.3427 | 262 | 38341.7832 | 6901.521 | 45243.3042 | 270 | 39512.5247 | 8 | 3.053% | 270 | 39512.5247 | 0 |  | 0 | 0 | 39512.5247 | 7112.2544 | 46624.7792 | 1381.4749
3 | Supply of following POWER CONDUCTORS in the proposed 220kV lines including provision for sag and wastage as per the technical specification and as per the instruction of the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | ACSR Zebra (54/7/3.18mm) | Kms. | 341080.2155 | 220 | 75037647.4009 | 13506776.5322 | 88544423.9331 | 206.4754 | 70424660.2757 | -13.5246 | -6.148% | 206.4754 | 70424660.2757 | 0 |  | 0 | 0 | 70424660.2757 | 12676438.8496 | 83101099.1253 | -5443324.8077
4 | POWER CONDUCTOR ACESSORIES |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | For ACSR ZEBRA |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | VIBRATION DAMPER | Nos. | 847.0431 | 1572 | 1331551.7305 | 239679.3115 | 1571231.042 | 1668 | 1412867.8667 | 96 | 6.107% | 1668 | 1412867.8667 | 0 |  | 0 | 0 | 1412867.8667 | 254316.216 | 1667184.0827 | 95953.0407 | As per the requirement in line, calculation is attached
4.1.2 | MID SPAN JOINT | Nos. | 944.9279 | 50 | 47246.3964 | 8504.3513 | 55750.7477 | 50 | 47246.3964 | 0 | 0% | 50 | 47246.3964 | 0 |  | 0 | 0 | 47246.3964 | 8504.3513 | 55750.7477 | 0
4.1.3 | Repair Sleeve | Nos. | 307.2227 | 50 | 15361.136 | 2765.0045 | 18126.1405 | 50 | 15361.136 | 0 | 0% | 50 | 15361.136 | 0 |  | 0 | 0 | 15361.136 | 2765.0045 | 18126.1405 | 0
5 | Supply of the following Type Long Rod Porcelain insulators as per the technical specification and as per the instruction of the Engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | 160 KN Long Rod Antifog PORCELAIN INSULATOR | Nos. | 7771.6688 | 1361 | 10577241.1928 | 1903903.4147 | 12481144.6076 | 1980 | 15387904.1601 | 619 | 45.48% | 1701 | 13219608.5739 | 279 | 14498 | 7771.6688 | 2168295.5862 | 15387904.1601 | 2769822.7488 | 18157726.9089 | 5676582.3013 | Item No 58 of cost data 23-24
5.2 | 90 KN Long Rod Antifog PORCELAIN INSULATOR | Nos. | 5651.1536 | 1392 | 7866405.788 | 1415953.0418 | 9282358.8298 | 1490 | 8420218.8391 | 98 | 7.04% | 1490 | 8420218.8391 | 0 |  | 0 | 0 | 8420218.8391 | 1515639.391 | 9935858.2302 | 653499.4004
6 | Supply of the following hard ware fittings suitable for following conductors as per the technical specification. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1 | For ACSR ZEBRA |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 | Single suspension Hard wares AGS Type fittings suitable for 90 KN Long Rod insulator. | Set | 3576.1888 | 450 | 1609284.9468 | 289671.2904 | 1898956.2373 | 390 | 1394713.6206 | -60 | -13.33% | 390 | 1394713.6206 | 0 |  | 0 | 0 | 1394713.6206 | 251048.4517 | 1645762.0723 | -253194.165
6.1.2 | Double suspension Hard wares AGS Type fittings suitable for 90 KN Long Rod insulator. | Set | 6292.7354 | 84 | 528589.775 | 95146.1595 | 623735.9345 | 180 | 1132692.3751 | 96 | 114.3% | 105 | 660737.2188 | 75 | 4508.08 | 4508.08 | 338106 | 998843.2188 | 179791.7794 | 1178634.9982 | 554899.0636 | Item No 16 of cost data 23-24
6.1.3 | Single tension Hard wares fittings, suitable for 160 KN Long Rod insulator. | Set | 2823.1539 | 360 | 1016335.4038 | 182940.3727 | 1199275.7765 | 456 | 1287358.1782 | 96 | 26.67% | 450 | 1270419.2548 | 6 | 2049.68 | 2049.68 | 12298.08 | 1282717.3348 | 230889.1203 | 1513606.4551 | 314330.6785 | Item No 17 of cost data 23-24
6.1.4 | Double tension Hard wares fittings, suitable for 160 KN Log Rod insulator. | Set | 5756.7917 | 144 | 828978.0019 | 149216.0403 | 978194.0422 | 252 | 1450711.5033 | 108 | 75% | 180 | 1036222.5024 | 72 | 4675.6 | 4675.6 | 336643.2 | 1372865.7024 | 247115.8264 | 1619981.5288 | 641787.4866 | Item No 18 of cost data 23-24
7 | “D” Shackle | Nos. | 328.5442 | 504 | 165586.2625 | 29805.5272 | 195391.7897 | 50 | 16427.2086 | -454 | -90.08% | 50 | 16427.2086 | 0 |  | 0 | 0 | 16427.2086 | 2956.8975 | 19384.1061 | -176007.6836
8 | Hanger | Nos. | 565.0184 | 534 | 301719.8484 | 54309.5727 | 356029.4211 | 468 | 264428.6312 | -66 | -12.36% | 468 | 264428.6312 | 0 |  | 0 | 0 | 264428.6312 | 47597.1536 | 312025.7848 | -44003.6363
9 | U'-Bolt. | Nos | 186.0781 | 89 | 16560.9522 | 2980.9714 | 19541.9236 | 78 | 14514.093 | -11 | -12.36% | 78 | 14514.093 | 0 |  | 0 | 0 | 14514.093 | 2612.5367 | 17126.6297 | -2415.2939
10 | Supply of following items for EHV Cable as per the technical specification of OPTCL and as per the instruction of engineer in charge |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | 220kV XLPE 1C X 1000 Sqmm Copper cable having Al sheath and HDPE outer sheath(Laying Condition: shall be buried 1.5 mtrs below ground level) for 2 nos. lines with 2 spare (i.e. 6 runs + 2 spare) | Mtrs | 16668.5286 | 5000 | 83342643.1823 | 15001675.7728 | 98344318.9551 | 10962 | 182720410.9129 | 5962 | 119.2% | 6250 | 104178303.9779 | 4712 | 18135.7 | 16668.5286 | 78542106.935 | 182720410.9129 | 32889673.9643 | 215610084.8772 | 117265765.9221 | Item No 155 Of Cost Data 23-24
10.2 | 220kV Cable sealing termination end(Outdoor Type) along with terminal connector suitable for 1C x 1000 sqmm Copper Cable | Nos | 532823.0521 | 16 | 8525168.8342 | 1534530.3902 | 10059699.2244 | 14 | 7459522.73 | -2 | -12.5% | 14 | 7459522.73 | 0 |  | 0 | 0 | 7459522.73 | 1342714.0914 | 8802236.8214 | -1257462.4031
10.3 | EHV Cable Accessories such as Trefoil Clamp for Under Ground Cable fixing to be fixed at every one meter interval,link box with & without SVL,Bonding Cables,Erathing Cable for 220 KV system and any other materials required to complete the system as per detail Enggg after due calculation & technical specification and approved drawings of the Engineer In-Charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.3.1 | LINK BOX WITH SVL | Nos. | 33080.2307 | 7 | 231561.615 | 41681.0907 | 273242.7056 | 7 | 231561.615 | 0 | 0% | 7 | 231561.615 | 0 |  | 0 | 0 | 231561.615 | 41681.0907 | 273242.7056 | 0
10.3.2 | LINK BOX WITHOUT SVL | Nos. | 14745.7214 | 7 | 103220.0501 | 18579.609 | 121799.6592 | 7 | 103220.0501 | 0 | 0% | 7 | 103220.0501 | 0 |  | 0 | 0 | 103220.0501 | 18579.609 | 121799.6592 | 0
10.3.3 | TREFOIL CLAMP FOR EHV CABLE | Nos. | 1090.3015 | 850 | 926756.2363 | 166816.1225 | 1093572.3589 | 1180 | 1286555.7163 | 330 | 38.82% | 1063 | 1158990.4461 | 117 |  | 1090.3015 | 127565.2702 | 1286555.7163 | 231580.0289 | 1518135.7453 | 424563.3864
10.3.4 | SHEATH BONDING CABLE | Mtrs. | 4518.2092 | 140 | 632549.2918 | 113858.8725 | 746408.1644 | 420 | 1897647.8755 | 280 | 200% | 175 | 790686.6148 | 245 |  | 4518.2092 | 1106961.2607 | 1897647.8755 | 341576.6176 | 2239224.4931 | 1492816.3288
10.3.5 | EARTH CONTINUTITY CABLE | Mtrs. | 4518.2092 | 320 | 1445826.9528 | 260248.8515 | 1706075.8043 |  | 0 | -320 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1706075.8043
11 | Supply of lattice type structure suitable for 220 KV as per the technical specification of OPTCL. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | Structure Suport for Cable Sleaing end (16 nos), RP1 Column (3Nos), Q1 beam (2Nos.) LA(6 no) including Foundation Nuts & Bolts. (Galvanization thisckness shall be minimum 910gm/sqm as these are to be installed in coastal area). | MT | 84767.3037 | 21 | 1780113.3787 | 320420.4082 | 2100533.7869 |  | 0 | -21 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -2100533.7869
11.2 | Total weight of GI Nuts and bolts for Equipment Structures | MT | 110268.7279 | 1.04 | 114679.477 | 20642.3059 | 135321.7829 | 0 | 0 | -1.04 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -135321.7829
NEW | 220KV 1C*1000SQ.MM Copper Cable Straight Through Joint | Nos. | [5 empty] | 14 | 0 | 14 |  | 0 | 0 | 14 | 386906 | 386906 | 5416684 | 5416684 | 975003.12 | 6391687.12 | 6391687.12 | As per budgetary offer
12 | 220kV 10KA Class-3 Lightning arrester | Nos. | 83342.6432 | 6 | 500055.8591 | 90010.0546 | 590065.9137 | 12 | 1000111.7182 | 6 | 100% | 8 | 666741.1455 | 4 | 70578.02 | 70578.02 | 282312.08 | 949053.2255 | 170829.5806 | 1119882.806 | 529816.8923 | Item No 27 Of Cost Data 23-24
13 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13.1 | 24Fibre(DWSM) OPGW fibre Optic cable | KM | 147987.3433 | 35 | 5179557.0151 | 932320.2627 | 6111877.2778 | 36 | 5327544.3584 | 1 | 2.857% | 36 | 5327544.3584 | 0 |  | 0 | 0 | 5327544.3584 | 958957.9845 | 6286502.3429 | 174625.0651
13.2 | OPGW hardwarw set like suspension assembly, Tension assembly(Dead end assembly, Pass through assembly), Vibration damper, Down Lead clamp Assemblies for 24F, 48 fibre(DWSM) OPGW, Joint box | KM | 33242.0799 | 35 | 1163472.7966 | 209425.1034 | 1372897.8999 | 36 | 1196714.8765 | 1 | 2.857% | 36 | 1196714.8765 | 0 |  | 0 | 0 | 1196714.8765 | 215408.6778 | 1412123.5542 | 39225.6543
B | SUPPLY COMPONENT OF THE WORKS CONTRACT FOR 220 KV TRANSMISSION LINE-PARADEEP-ERSAMA |  |  |  | 287302237.3364 | 51714402.7205 | 339016640.0569 |  | 420177498.6464 |  | 0 |  | 316188746.3702 |  |  |  | 109138041.9828 | 425326788.3531 | 76558821.9036 | 501885610.2566 | 162868970.1997
0

## S_400kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1 | [20 empty] | SUPPLY - 400kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Cost Data Rate | Least Cost | Amount
1 | SUPPLY of Following type tested Lattice type Galvanized steel tangent / Angle tower with stubs and cleats , different type of G.I HT Nuts & Bolts, washer, spring washer for the towers ,hanger and all accessories, tower super structure complete including step bolts. Supply of black bituminous paint for three coats up to a height of 500mm above the cooping(legs & bracing members). All Supply should confirm to the Technical Specification and the structures are to be designed for Wind Zone-6 i.e. Wind Speed of 55 Mtr/Sec.(As per BIS 802). (Galvanization thisckness shall be minimum 910gm/sqm as these are to be installed in coastal area). Note:Weight as indicated are tentative. |  |  |  | 0 |  |  |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | TOWER STRUCTURES |  |  |  | 0 |  |  |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | DA TYPE (SUSPENSION ) TOWERS (Nominal unit weight 11.884 MT) | Nos. |  | 98 | 0 | 0 | 0 | 97 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | +3 EXTENSION (Nominal unit weight 2.085 MT) | Nos. |  | 30 | 0 | 0 | 0 | 37 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | +6 EXTENSION (Nominal unit weight 2.958MT) | Nos. |  | 9 | 0 | 0 | 0 | 15 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.4 | +9 EXTENSION (Nominal unit weight 3.988MT) | Nos. |  | 0 | 0 | 0 | 0 | 1 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.5 | +18 EXTENSION (Nominal unit weight 9.22 MT) | Nos. |  | 0 | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.6 | DB TYPE (15 deg ANGLE ) TOWERS (Nominal unit weight 19.337MT) | Nos. |  | 24 | 0 | 0 | 0 | 30 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 | +3 EXTENSION (Nominal unit weight 3.04 MT) | Nos. |  | 7 | 0 | 0 | 0 | 11 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.8 | +6 EXTENSION (Nominal unit weight 4.791 MT) | Nos. |  |  | 0 | 0 | 0 | 13 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.9 | +9 EXTENSION (Nominal unit weight 6.295 MT) | Nos. |  |  | 0 | 0 | 0 | 1 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.10 | +18 EXTENSION (Nominal unit weight 11.043 MT)
1.1.11 | DC TYPE (30 deg ANGLE ) TOWERS (Nominal unit weight 22.895 MT) | Nos. |  | 21 | 0 | 0 | 0 | 12 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.12 | +3 EXTENSION (Nominal unit weight 3.531 MT) | Nos. |  | 9 | 0 | 0 | 0 | 5 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.13 | +6 EXTENSION (Nominal unit weight 5.432 MT) | Nos. |  | 2 | 0 | 0 | 0 | 3 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.14 | +9 EXTENSION (Nominal unit weight 7.472 MT)
1.1.15 | DD TYPE (60 deg angle)TOWER (Nominal unit weight 33.658 MT) | Nos. |  | 33 | 0 | 0 | 0 | 46 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.16 | +3 EXTENSION (Nominal unit weight 5.437 MT) | Nos. |  | 2 | 0 | 0 | 0 | 5 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.17 | +6 EXTENSION (Nominal unit weight 8.084 MT) | Nos. |  | 5 | 0 | 0 | 0 | 8 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.18 | +9 EXTENSION (Nominal unit weight 10.844 MT) | Nos. |  |  | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.19 | +12 EXTENSION (Nominal unit weight 8.084 MT) | Nos. |  |  | 0 | 0 | 0 | 13 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.20 | +18 TO DD TYPE TOWER (Nominal unit weight 22.857 MT) | Nos. |  | 8 | 0 | 0 | 0 | 5 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.21 | +25 TO DD TYPE TOWER (Nominal unit weight 33.042 MT) | Nos. |  | 8 | 0 | 0 | 0 | 7 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2 | TEMPLATES (Hot dip galvanised) Note: Weight as indicated are tentative |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | DA (Nominal unit weight 1.526 MT) | Nos. |  | 5 | 0 | 0 | 0 | 5 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | DB (Nominal unit weight 1.85 MT) | Nos. |  | 2 | 0 | 0 | 0 | 2 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.3 | DC (Nominal unit weight 2.053 MT) | Nos. |  | 2 | 0 | 0 | 0 | 2 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.4 | DD (Nominal unit weight 2.85 MT) | Nos. |  | 2 | 0 | 0 | 0 | 2 | 0 |  | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3 | WEIGHT OF THE STRUCTURES (including Tower stubs, Templates & Foundation Nut and Bolts) | MT | 78929.1029 | 3892.946 | 307266735.3966 | 55308012.3714 | 362574747.768 | 4465.34 | 352445280.3188 | 572.394 | 14.7% | 4465.34 | 352445280.3188 | 0 |  | 0 | 0 | 352445280.3188 | 63440150.4574 | 415885430.7762 | 53310683.0082 | As per the approved structure drawing
1.4 | Weight of different type G.I Nuts and Bolts | MT | 95909.7 | 178 | 17071926.6064 | 3072946.7892 | 20144873.3956 | 133.93 | 12845186.1258 | -44.07 | -24.76% | 133.93 | 12845186.1258 | 0 |  | 0 | 0 | 12845186.1258 | 2312133.5027 | 15157319.6285 | -4987553.7671 | As per the approved structure drawing
1.5 | Conducting type test on designed Transmission line towers suitable for Wind Zone-VI: a) Preparation of Structural drawings, fabrication drawing, Shop floor drawings, proto-corrected structural & shop floor drawings and Bill of material with Single line diagram of Tower; b) Fabrication, galvanization and proto-assembly of Steel tower structures as per approved structural drawings. c) Transportation of Tower Structures including BOM verification at the Tower testing beds of Testing Lab. d) In case of pre-mature failure (major/minor) the following activities are required to be carried out by the manufacturer: • Modification in structural drawings, shop drawings and BOM as per revision of the tower design • Fabrication, galvanization, transportation of the modified members to the testing agency Laboratories. e) Lifting back the scrap tower material after completion of tests including loading and transportation from Testing Agency Laboratories. |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.5.1 | DA type Tower | Nos | 4042808.7186 | 1 | 4042808.7186 | 727705.5693 | 4770514.2879 | 1 | 4042808.7186 | 0 | 0% | 1 | 4042808.7186 | 0 |  | 0 | 0 | 4042808.7186 | 727705.5693 | 4770514.2879 | 0
1.5.2 | DB Type Tower | Nos | 5803028.2147 | 1 | 5803028.2147 | 1044545.0786 | 6847573.2934 | 1 | 5803028.2147 | 0 | 0% | 1 | 5803028.2147 | 0 |  | 0 | 0 | 5803028.2147 | 1044545.0786 | 6847573.2934 | 0
1.5.3 | DC Type Tower | Nos | 6777608.4649 | 1 | 6777608.4649 | 1219969.5237 | 7997577.9886 | 1 | 6777608.4649 | 0 | 0% | 1 | 6777608.4649 | 0 |  | 0 | 0 | 6777608.4649 | 1219969.5237 | 7997577.9886 | 0
1.5.4 | DD Type Tower | Nos | 8491048.6982 | 1 | 8491048.6982 | 1528388.7657 | 10019437.4639 | 1 | 8491048.6982 | 0 | 0% | 1 | 8491048.6982 | 0 |  | 0 | 0 | 8491048.6982 | 1528388.7657 | 10019437.4639 | 0
2 | Supply of the following tower accessories as per technical specification and as directed by the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | EARTHING DEVICE | Nos. | 2564.389 | 254 | 651354.8113 | 117243.866 | 768598.6774 | 254 | 651354.8113 | 0 | 0% | 254 | 651354.8113 | 0 |  | 0 | 0 | 651354.8113 | 117243.866 | 768598.6774 | 0
2.2 | DANGER BOARD | Nos. | 277.1789 | 176 | 48783.4791 | 8781.0262 | 57564.5054 | 185 | 51278.0889 | 9 | 5.114% | 185 | 51278.0889 | 0 |  | 0 | 0 | 51278.0889 | 9230.056 | 60508.1448 | 2943.6395
2.3 | NUMBER PLATE | Nos. | 146.3427 | 176 | 25756.3124 | 4636.1362 | 30392.4486 | 185 | 27073.3966 | 9 | 5.114% | 185 | 27073.3966 | 0 |  | 0 | 0 | 27073.3966 | 4873.2114 | 31946.6079 | 1554.1593
2.4 | PHASE PLATE | Nos. | 215.1528 | 1056 | 227201.3783 | 40896.2481 | 268097.6264 | 1110 | 238819.6306 | 54 | 5.114% | 1110 | 238819.6306 | 0 |  | 0 | 0 | 238819.6306 | 42987.5335 | 281807.1641 | 13709.5377
2.5 | BIRD GUARD | Nos. | 274.2714 | 588 | 161271.5762 | 29028.8837 | 190300.4599 | 582 | 159625.9479 | -6 | -1.02% | 582 | 159625.9479 | 0 |  | 0 | 0 | 159625.9479 | 28732.6706 | 188358.6185 | -1941.8414
2.6 | ANTICLIMBING DEVICE | Nos. | 5770.3599 | 176 | 1015583.3381 | 182805.0009 | 1198388.339 | 185 | 1067516.577 | 9 | 5.114% | 185 | 1067516.577 | 0 |  | 0 | 0 | 1067516.577 | 192152.9839 | 1259669.5609 | 61281.2219
2.7 | Circuit plate | Nos. | 146.3427 | 352 | 51512.6248 | 9272.2725 | 60784.8973 | 370 | 54146.7931 | 18 | 5.114% | 370 | 54146.7931 | 0 |  | 0 | 0 | 54146.7931 | 9746.4228 | 63893.2159 | 3108.3186
3 | Supply of following POWER CONDUCTORS in the proposed 400 kV lines with 1.5% provision for sag and wastage as per the technical specification and as per the instruction of the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | ACSR Moose(54/7/3.53 mm) | Kms. | 378425.7055 | 861 | 325824532.3983 | 58648415.8317 | 384472948.2299 | 833.6966 | 315492239.1289 | -27.3034 | -3.171% | 833.6966 | 315492239.1289 | 0 |  | 0 | 0 | 315492239.1289 | 56788603.0432 | 372280842.1721 | -12192106.0578
4 | POWER CONDUCTOR ACESSORIES |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | For ACSR Moose( 400KV DC line) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | 4R VIBRATION DAMPER FOR SUSPENSION | Nos. | 947.8354 | 2352 | 2229308.8556 | 401275.594 | 2630584.4496 | 2328 | 2206560.806 | -24 | -1.02% | 2328 | 2206560.806 | 0 |  | 0 | 0 | 2206560.806 | 397180.9451 | 2603741.7511 | -26842.6985
4.1.2 | 4R VIBRATION DAMPER FOR TENSION | Nos. | 947.8354 | 3744 | 3548695.7293 | 638765.2313 | 4187460.9606 | 4272 | 4049152.8193 | 528 | 14.1% | 4272 | 4049152.8193 | 0 |  | 0 | 0 | 4049152.8193 | 728847.5075 | 4778000.3268 | 590539.3662
4.1.3 | MID SPAN JOINT | Nos. | 892.5935 | 400 | 357037.383 | 64266.7289 | 421304.1119 | 451.7568 | 403235.164 | 51.7568 | 12.94% | 451.7568 | 403235.164 | 0 |  | 0 | 0 | 403235.164 | 72582.3295 | 475817.4935 | 54513.3816
4.1.4 | Repair Sleeve | Nos. | 390.5702 | 150 | 58585.5315 | 10545.3957 | 69130.9272 | 150 | 58585.5315 | 0 | 0% | 150 | 58585.5315 | 0 |  | 0 | 0 | 58585.5315 | 10545.3957 | 69130.9272 | 0
4.1.5 | Line Spacer | set | 892.5935 | 14784 | 13196101.6745 | 2375298.3014 | 15571399.9759 | 14784 | 13196101.6745 | 0 | 0% | 14784 | 13196101.6745 | 0 |  | 0 | 0 | 13196101.6745 | 2375298.3014 | 15571399.9759 | 0
4.1.6 | Rigid Spacer | set | 440.9664 | 1872 | 825489.0372 | 148588.0267 | 974077.0639 | 2088 | 920737.7723 | 216 | 11.54% | 2088 | 920737.7723 | 0 |  | 0 | 0 | 920737.7723 | 165732.799 | 1086470.5713 | 112393.5074
5 | Supply of the following Long Rod Porcelain insulators as per the technical specification and as per the instruction of the Engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | 160 KN Long Rod PORCELAIN INSULATOR (taking 5% extra towards wastage) | Nos. | 6995.3741 | 7963 | 55704164.2139 | 10026749.5585 | 65730913.7724 | 6408 | 44826357.4385 | -1555 | -19.53% | 6408 | 44826357.4385 | 0 |  | 0 | 0 | 44826357.4385 | 8068744.3389 | 52895101.7774 | -12835811.995
5.2 | 120 KN Long Rod PORCELAIN INSULATOR (taking 5% extra towards wastage) | Nos. | 5828.5093 | 6098 | 35542249.6295 | 6397604.9333 | 41939854.5628 | 3915 | 22818613.8569 | -2183 | -35.8% | 3915 | 22818613.8569 | 0 |  | 0 | 0 | 22818613.8569 | 4107350.4942 | 26925964.3512 | -15013890.2116
6 | Supply of the following hard ware fittings suitable for ACSR Moose conductors as per the technical specification. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1 | For ACSR MOOSE (400KV DC line) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 | Single suspension Hard wares (AGS type) fittings for pilot insulator. | set | 5018.2942 | 270 | 1354939.4235 | 243889.0962 | 1598828.5198 | 141 | 707579.4767 | -129 | -47.78% | 141 | 707579.4767 | 0 |  | 0 | 0 | 707579.4767 | 127364.3058 | 834943.7826 | -763884.7372
6.1.2 | Double suspension Hard wares fittings.(AGS type) for ACSR Moose. | set | 10594.8227 | 591 | 6261540.1963 | 1127077.2353 | 7388617.4317 | 582 | 6166186.7923 | -9 | -1.523% | 582 | 6166186.7923 | 0 |  | 0 | 0 | 6166186.7923 | 1109913.6226 | 7276100.415 | -112517.0167
6.1.3 | Double tension Hard wares fittings suitable for ACSR Moose. | set | 13940.3521 | 948 | 13215453.7985 | 2378781.6837 | 15594235.4822 | 1068 | 14888296.0514 | 120 | 12.66% | 1068 | 14888296.0514 | 0 |  | 0 | 0 | 14888296.0514 | 2679893.2893 | 17568189.3407 | 1973953.8585
7 | D SACKLE(SUITABLE FOR 20MM DIA, 75MM LONG) | Nos. | 234.536 | 588 | 137907.1429 | 24823.2857 | 162730.4286 | 582 | 136499.9272 | -6 | -1.02% | 582 | 136499.9272 | 0 |  | 0 | 0 | 136499.9272 | 24569.9869 | 161069.9141 | -1660.5146 | As per tower requirement
8 | U' Bolt | Nos. | 167.6641 | 196 | 32862.1704 | 5915.1907 | 38777.3611 | 196 | 32862.1704 | 0 | 0% | 196 | 32862.1704 | 0 |  | 0 | 0 | 32862.1704 | 5915.1907 | 38777.3611 | 0
9 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9.1 | 24Fibre(DWSM) OPGW fibre Optic cable | KM | 147987.3433 | 69 | 10211126.6868 | 1838002.8036 | 12049129.4905 | 71.577 | 10592490.0705 | 2.577 | 3.735% | 71.577 | 10592490.0705 | 0 |  | 0 | 0 | 10592490.0705 | 1906648.2127 | 12499138.2832 | 450008.7927
9.2 | OPGW hardwarw set like suspension assembly, Tension assembly(Dead end assembly, Pass through assembly), Vibration damper, Down Lead clamp Assemblies for 24F, 48 fibre(DWSM) OPGW, Joint box | KM | 136395.2582 | 69 | 9411272.8174 | 1694029.1071 | 11105301.9245 | 71.577 | 9762763.3978 | 2.577 | 3.735% | 71.577 | 9762763.3978 | 0 |  | 0 | 0 | 9762763.3978 | 1757297.4116 | 11520060.8095 | 414758.8849
10 | Supply of the GI earth wire of size 7/3.66 mm as per the technical specification, with 1.5% provision for Sag & Wastage and as per the direction of Engineer in charge. | Kms. | 56876.908 | 72 | 4095137.3735 | 737124.7272 | 4832262.1007 | 69.4747 | 3951507.2553 | -2.5253 | -3.507% | 69.4747 | 3951507.2553 | 0 |  | 0 | 0 | 3951507.2553 | 711271.306 | 4662778.5613 | -169483.5394
11 | EARTH CONDUCTOR ACESSORIES |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | VIBRATION DAMPER | Nos. | 362.4647 | 254 | 92066.024 | 16571.8843 | 108637.9083 | 550 | 199355.5637 | 296 | 116.5% | 318 | 115263.7623 | 232 | 357.01 | 357.01 | 82826.32 | 198090.0823 | 35656.2148 | 233746.2971 | 125108.3888 | Item No 44 fo cost data 23-24
11.2 | FLEXIBLE EARTH BOND for 7/3.66mm earth wire | Nos. | 613.4763 | 256 | 157049.929 | 28268.9872 | 185318.9162 | 275 | 168705.9784 | 19 | 7.422% | 275 | 168705.9784 | 0 |  | 0 | 0 | 168705.9784 | 30367.0761 | 199073.0545 | 13754.1383
11.3 | SUSPENSION CLAMP for 7/3.66mm earth wire | Nos. | 641.5818 | 98 | 62875.0197 | 11317.5035 | 74192.5232 | 97 | 62233.4379 | -1 | -1.02% | 97 | 62233.4379 | 0 |  | 0 | 0 | 62233.4379 | 11202.0188 | 73435.4567 | -757.0666
11.4 | TENSION CLAMP with terminal jumper for 7/3.66mm earth wire | Nos. | 641.5818 | 156 | 100086.7661 | 18015.6179 | 118102.3839 | 178 | 114201.5664 | 22 | 14.1% | 178 | 114201.5664 | 0 |  | 0 | 0 | 114201.5664 | 20556.282 | 134757.8483 | 16655.4644
11.5 | MID SPAN JOINT | Nos. | 245.1967 | 98 | 24029.2749 | 4325.2695 | 28354.5444 | 74 | 18144.5545 | -24 | -24.49% | 74 | 18144.5545 | 0 |  | 0 | 0 | 18144.5545 | 3266.0198 | 21410.5743 | -6943.9701
C | TOTAL OF SUPPLY COMPONENT OF THE WORKS CONTRACT FOR 400 KV TRANSMISSION LINE-ERSAMA-LOC-358 to LOC-182) |  |  |  | 834077130.6955 | 150133883.5252 | 984211014.2207 |  | 843427186.2211 |  | 0% |  | 843343094.4196 |  |  |  | 82826.32 | 843425920.7396 | 151816665.7331 | 995242586.4728 | 11031572.2521

## E_220KV Bay
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1
ERECTION - 220kV BAY
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
PART A | ELECTRICAL WORKS |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | ERECTION OF SUPERSTRUCTURE : |  |  |  | 0 | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Supply of labour,T&P and other necessary arrangements for erection of Columns,Beams,Equipments supporting structures & Nuts and Bolts | MT | 5936.0857 | 68.18 | 404722.3228 | 72850.0181 | 477572.3409 | 82.089 | 487287.3388 | 13.909 | 20.4% | 82.089 | 487287.3388 | 0 |  | 0 | 0 | 487287.3388 | 87711.721 | 574999.0597 | 97426.7188
2 | ERECTION OF EQUIPMENTS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| Supply of all labour ,T&P and Transportation from the site store,erections as per specification and testing commissioning etc as per the instruction of the Engineer-in-charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | 245 KV,1200-600-300A,40KA,5CORE SINGLE PHASE CURRENT TRANSFORMER(4 PS Cl & 1 0.2s Cl) | NOS | 5342.9617 | 6 | 32057.7702 | 5770.3986 | 37828.1689 | 6 | 32057.7702 | 0 | 0 | 6 | 32057.7702 | 0 |  | 0 | 0 | 32057.7702 | 5770.3986 | 37828.1689 | 0
2.2 | 245 KV,2000A,40KA,ISOLATORS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | S/I WITH OUT EARTH SWITCH | NOS | 14840.6988 | 6 | 89044.1929 | 16027.9547 | 105072.1476 | 6 | 89044.1929 | 0 | 0 | 6 | 89044.1929 | 0 |  | 0 | 0 | 89044.1929 | 16027.9547 | 105072.1476 | 0
2.2.2 | S/I WITH SINGLE EARTH SWITCH | NOS | 14840.6988 | 2 | 29681.3976 | 5342.6516 | 35024.0492 | 2 | 29681.3976 | 0 | 0 | 2 | 29681.3976 | 0 |  | 0 | 0 | 29681.3976 | 5342.6516 | 35024.0492 | 0
2.2.3 | BEAM MOUNTED S/I WITHOUT EARTH SWITCH | NOS | 14840.6988 | 2 | 29681.3976 | 5342.6516 | 35024.0492 | 2 | 29681.3976 | 0 | 0 | 2 | 29681.3976 | 0 |  | 0 | 0 | 29681.3976 | 5342.6516 | 35024.0492 | 0
2.3 | 245 KV,4400pF,3CORE,SINGLE PHASE CAPACITOR VOLTAGE TRANSFORMER | NOS | 5342.9617 | 6 | 32057.7702 | 5770.3986 | 37828.1689 | 6 | 32057.7702 | 0 | 0 | 6 | 32057.7702 | 0 |  | 0 | 0 | 32057.7702 | 5770.3986 | 37828.1689 | 0
2.4 | 245KV,3150A,40KA,SF6,CIRCUIT BREAKER WITH SUPPORTING STRUCTURE | NOS | 53424.7713 | 2 | 106849.5425 | 19232.9177 | 126082.4602 | 2 | 106849.5425 | 0 | 0 | 2 | 106849.5425 | 0 |  | 0 | 0 | 106849.5425 | 19232.9177 | 126082.4602 | 0
2.5 | 216KV metal oxide polymer housed surge arrrestor, 10KA Long duration discharge class III at 216KV, pressure relief Design B & thermal energy (Wth) & Repetitive charge transfer(Qrs) as per latest IEC, as per technical specification. | NOS | 5342.9617 | 6 | 32057.7702 | 5770.3986 | 37828.1689 | 6 | 32057.7702 | 0 | 0 | 6 | 32057.7702 | 0 |  | 0 | 0 | 32057.7702 | 5770.3986 | 37828.1689 | 0
2.6 | 220 KV Bus Post Insulators | NOS | 1781.3103 | 16 | 28500.9646 | 5130.1736 | 33631.1382 | 18 | 32063.5852 | 2 | 12.5% | 18 | 32063.5852 | 0 |  | 0 | 0 | 32063.5852 | 5771.4453 | 37835.0305 | 4203.8923
3 | BUS-BAR STRINGING |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Supply of labour,T&P and other necessary arrangements for stringing of bus bar conductors,hoisting of single or double insulator strings,Single or Double Hard-wares Fittings, Clamp & connectors, as per requirements, Jumpers, connections to Equipments,testing,commissioning etc. as per the instruction of Engineer-in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Single conductor/Phase/Mtr. | MTR | 89.1624 | 750 | 66871.8225 | 12036.9281 | 78908.7506 | 750 | 66871.8225 | 0 | 0 | 750 | 66871.8225 | 0 |  | 0 | 0 | 66871.8225 | 12036.9281 | 78908.7506 | 0 | As per the approved layout
3.1.2 | Twin Conductor /Phase/Mtr. | MTR | 100.7923 | 150 | 15118.8468 | 2721.3924 | 17840.2393 | 150 | 15118.8468 | 0 | 0 | 150 | 15118.8468 | 0 |  | 0 | 0 | 15118.8468 | 2721.3924 | 17840.2393 | 0
4 | SUBSTATION EARTHING SYSTEM |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Substation earth-mat Design, engineering, supply inclusive of corrosion protection measures if any,laying of earth-mat conductors of Hot dip galvanized flats of size 75X10mm to the approval of Project Manager, excavation, welding/jointing ,application of two coats of bituminous Paint,wrapping of HT Tape etc of ground conductors along with risers (of size 50X6 mm GI flats) etc back filling and good compaction,grounding driven rods(40 mm MS solid rod),perforated GI pipes for treated earth pits(with details of treatment as per IS). The spacing between the earth conductor not more than 5 mtrs(both way) and to be buried at depth of 700mm from the finished ground level. For provision of treated earth-pit and untreated earth pit, refer the specification for designing. Provision of water taps inside the switch yard areas and peripheral treated and un-treated earth pit are required to be provided for watering the treated earth pits. The no. of treated and un treated earth pits are to be done as per the practice and as indicated in the drawing for different equipments. This is as per approved drawing and specification. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | 75x10 MM GI FLAT | MTRS | 171.5408 | 1250 | 214425.9527 | 38596.6715 | 253022.6242 | 2466 | 423019.5195 | 1216 | 97.28% | 1562.5 | 268032.4409 | 903.5 | 85.77 | 85.77 | 77493.195 | 345525.6359 | 62194.6145 | 407720.2504 | 154697.6262 | As per approved earthing layout, Item 21.1.vi.b of OPTCL CD 23-24
4.1.2 | 50x6 MM GI FLAT | MTRS | 136.6511 | 2000 | 273302.2313 | 49194.4016 | 322496.6329 | 2106 | 287787.2495 | 106 | 5.3% | 2106 | 287787.2495 | 0 |  | 0 | 0 | 287787.2495 | 51801.7049 | 339588.9544 | 17092.3215
4.1.3 | 40 MM MS ROD FOR NON-TREATED EARTH PIT ELECTORDE | NOS | 1781.3103 | 30 | 53439.3086 | 9619.0756 | 63058.3842 | 30 | 53439.3086 | 0 | 0 | 30 | 53439.3086 | 0 |  | 0 | 0 | 53439.3086 | 9619.0756 | 63058.3842 | 0
4.1.4 | 50MM GI PIPE FOR TREATED EARTH PIT ELECTRORDE WITH CHAMBER AND COVER | NOS | 6530.1788 | 30 | 195905.3653 | 35262.9658 | 231168.3311 | 28 | 182845.0077 | -2 | -6.667% | 28 | 182845.0077 | 0 |  | 0 | 0 | 182845.0077 | 32912.1014 | 215757.109 | -15411.2221
5 | G.I Cable Trays including support GI angle suitable for different sections i.e. Section:1-1,2-2,3-3 & 4-4 along with its accessories as per TS. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | G.I Cable Trays(size: 450x75x2500mm) | MTRS | 53.3036 | 500 | 26651.8133 | 4797.3264 | 31449.1397 | 0 | 0 | -500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -31449.1397
5.2 | G.I Cable Trays(size: 300x75x2500mm) | MTRS | 53.3036 | 500 | 26651.8133 | 4797.3264 | 31449.1397 | 1120 | 59700.0619 | 620 | 124% | 625 | 33314.7667 | 495 |  | 53.3036 | 26385.2952 | 59700.0619 | 10746.0111 | 70446.073 | 38996.9333 | As per the approved cable trench layout
5.3 | G.I Cable Trays(size: 150x75x2500mm) | MTRS | 53.3036 | 200 | 10660.7253 | 1918.9306 | 12579.6559 | 550 | 29316.9947 | 350 | 175% | 250 | 13325.9067 | 300 |  | 53.3036 | 15991.088 | 29316.9947 | 5277.059 | 34594.0537 | 22014.3978 | As per the approved cable trench layout and trench for UG cable upto tower hight is concidered
5.4 | Support G. I angle 50x50x6 mm for cable tray | MT | 9497.7371 | 1 | 9497.7371 | 1709.5927 | 11207.3298 | 2 | 18995.4742 | 1 | 100% | 1.25 | 11872.1714 | 0.75 | 8603.72 | 8603.72 | 6452.79 | 18324.9614 | 3298.4931 | 21623.4544 | 10416.1246 | ANNX-II-8.1.ii of RC 23-24
6 | SUB STATION SWITCYARD BMK,AC CONSOLE & OTHER MARSHALLING BOXES |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1 | BAY MARSHALLING KIOSK (01 nos on 220 kV bay ) | NOS | 3561.6514 | 1 | 3561.6514 | 641.0973 | 4202.7487 | 1 | 3561.6514 | 0 | 0 | 1 | 3561.6514 | 0 |  | 0 | 0 | 3561.6514 | 641.0973 | 4202.7487 | 0
6.2 | SWITCH YARD AC CONSOLE FOR LIGHTING (01 nos on 220 kV bay ) | NOS | 1781.3103 | 1 | 1781.3103 | 320.6359 | 2101.9461 | 1 | 1781.3103 | 0 | 0 | 1 | 1781.3103 | 0 |  | 0 | 0 | 1781.3103 | 320.6359 | 2101.9461 | 0
6.3 | SWITCH YARD RECEPTACLE BOARD FOR WELDING & OTHER EMERGENCY (01 no on 220KV BAY ) | NOS | 1781.3103 | 1 | 1781.3103 | 320.6359 | 2101.9461 | 1 | 1781.3103 | 0 | 0 | 1 | 1781.3103 | 0 |  | 0 | 0 | 1781.3103 | 320.6359 | 2101.9461 | 0
7 | Laying of Power and Control Cable including fixing of cable with terminal connections both at equipments and control panels with supply of and fixing of lugs,Ferrules,clamps,connectors,glands,fixing of cable trays, including supply of N&B,Link plates,Cable Markers,PVC pipes Bends,Plaster of Paris, M-Seal compounds etc for sealing purpose and all necessary arrangements,laying of Earthing Flats,earthing ,laying of Cable trench slabs and chequered plate etc for the cable trench,Cable scheduled and cable diagram to be prepared by the contractor |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | POWER CABLES,1.1KV,XLPE & PVC ARMOURED, ALUMINIUM CONDUCTOR (As per Specification) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | PVC 3.5 CX70 mm2 | MTR | 24.2289 | 500 | 12114.4606 | 2180.6029 | 14295.0635 | 500 | 12114.4606 | 0 | 0 | 500 | 12114.4606 | 0 |  | 0 | 0 | 12114.4606 | 2180.6029 | 14295.0635 | 0
7.1.2 | PVC 3.5 CX35 mm2 | MTR | 24.2289 | 500 | 12114.4606 | 2180.6029 | 14295.0635 | 500 | 12114.4606 | 0 | 0 | 500 | 12114.4606 | 0 |  | 0 | 0 | 12114.4606 | 2180.6029 | 14295.0635 | 0
7.1.3 | PVC 4 CX 16 mm2 | MTR | 24.2289 | 1000 | 24228.9212 | 4361.2058 | 28590.127 | 1000 | 24228.9212 | 0 | 0 | 1000 | 24228.9212 | 0 |  | 0 | 0 | 24228.9212 | 4361.2058 | 28590.127 | 0
7.1.4 | PVC 4CX 6 sqmm | MTR | 24.2289 | 1000 | 24228.9212 | 4361.2058 | 28590.127 | 1000 | 24228.9212 | 0 | 0 | 1000 | 24228.9212 | 0 |  | 0 | 0 | 24228.9212 | 4361.2058 | 28590.127 | 0 | As per the approved cable schedule
7.1.5 | PVC 2CX 6 sqmm | MTR | 24.2289 | 500 | 12114.4606 | 2180.6029 | 14295.0635 | 500 | 12114.4606 | 0 | 0 | 500 | 12114.4606 | 0 |  | 0 | 0 | 12114.4606 | 2180.6029 | 14295.0635 | 0
7.2 | CONTROL CABLES,1.1 KV, PVC,FRLS,STRANDED COPPER, ARMOURED (As per specification) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.2.1 | 2 CX 2.5 mm2 | MTR | 24.2289 | 1000 | 24228.9212 | 4361.2058 | 28590.127 | 1000 | 24228.9212 | 0 | 0 | 1000 | 24228.9212 | 0 |  | 0 | 0 | 24228.9212 | 4361.2058 | 28590.127 | 0
7.2.2 | 4 CX 2.5 mm2 | MTR | 24.2289 | 4000 | 96915.6848 | 17444.8233 | 114360.5081 | 4000 | 96915.6848 | 0 | 0 | 4000 | 96915.6848 | 0 |  | 0 | 0 | 96915.6848 | 17444.8233 | 114360.5081 | 0
7.2.3 | 5 CX 2.5 mm2 | MTR | 24.2289 | 2500 | 60572.303 | 10903.0145 | 71475.3176 | 2500 | 60572.303 | 0 | 0 | 2500 | 60572.303 | 0 |  | 0 | 0 | 60572.303 | 10903.0145 | 71475.3176 | 0
7.2.4 | 7CX 2.5 mm2 | MTR | 24.2289 | 2000 | 48457.8424 | 8722.4116 | 57180.2541 | 2000 | 48457.8424 | 0 | 0 | 2000 | 48457.8424 | 0 |  | 0 | 0 | 48457.8424 | 8722.4116 | 57180.2541 | 0
7.2.5 | 10 CX 2.5 mm2 | MTR | 24.2289 | 4000 | 96915.6848 | 17444.8233 | 114360.5081 | 5000 | 121144.6061 | 1000 | 25% | 5000 | 121144.6061 | 0 |  | 0 | 0 | 121144.6061 | 21806.0291 | 142950.6351 | 28590.127 | As per the approved cable trench layout
7.2.6 | 12 CX 2.5 mm2 | MTR | 24.2289 | 2500 | 60572.303 | 10903.0145 | 71475.3176 | 2500 | 60572.303 | 0 | 0 | 2500 | 60572.303 | 0 |  | 0 | 0 | 60572.303 | 10903.0145 | 71475.3176 | 0
7.2.7 | 16 CX 2.5 mm2 | MTR | 24.2289 | 2500 | 60572.303 | 10903.0145 | 71475.3176 | 2500 | 60572.303 | 0 | 0 | 2500 | 60572.303 | 0 |  | 0 | 0 | 60572.303 | 10903.0145 | 71475.3176 | 0
7.2.8 | 19 CX 2.5 mm2 | MTR | 24.2289 | 2500 | 60572.303 | 10903.0145 | 71475.3176 | 2500 | 60572.303 | 0 | 0 | 2500 | 60572.303 | 0 |  | 0 | 0 | 60572.303 | 10903.0145 | 71475.3176 | 0
7.2.9 | 4 CX 4 mm2 | MTR | 24.2289 | 1000 | 24228.9212 | 4361.2058 | 28590.127 | 1000 | 24228.9212 | 0 | 0 | 1000 | 24228.9212 | 0 |  | 0 | 0 | 24228.9212 | 4361.2058 | 28590.127 | 0
7.2.10 | 7 CX 4 mm2 | MTR | 24.2289 | 250 | 6057.2303 | 1090.3015 | 7147.5318 | 250 | 6057.2303 | 0 | 0 | 250 | 6057.2303 | 0 |  | 0 | 0 | 6057.2303 | 1090.3015 | 7147.5318 | 0
7.2.11 | 12 CX 4 mm2 | MTR | 24.2289 | 250 | 6057.2303 | 1090.3015 | 7147.5318 | 250 | 6057.2303 | 0 | 0 | 250 | 6057.2303 | 0 |  | 0 | 0 | 6057.2303 | 1090.3015 | 7147.5318 | 0
8 | Switch yard lighting: Design, engineering, procurement of labour, material including all associated works for construction of switch yard lightings as per technical specification and approved drawings. The Light fixture shall be of reputed make (Philips/CGL/Bajaj) and fixtures shall be LED type and proper cabling from the lighting outdoor distribution boards to the junction boxes and from junction boxes to the fixtures. The lighting fixtures are to be installed on the switch yard structures. The quantity of such fixtures are to be designed and to be ascertained. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
8.1 | SUB-STATION SWITCH YARD LIGHTING,IT INCLUDES ERECTION OF FIXTURES AND LAMPS(LED type) | SET | 772.418 | 15 | 11586.2701 | 2085.5286 | 13671.7987 | 15 | 11586.2701 | 0 | 0 | 15 | 11586.2701 | 0 |  | 0 | 0 | 11586.2701 | 2085.5286 | 13671.7987 | 0
8.2 | STREET LIGHTING, IT INCLUDES ERECTION OF GI TUBULAR POLE WITH LED LIGHTING FIXTURES WITH LAMPS.TO BE ERECTED IN & AROUND THE CONTROL ROOM BUILDING, A PORTION OF THE SWITCH YARD ALONG THE ROADS (APPROACH INSIDE YARD), COLONY QUARTERS AND OTHER ROADS. | SET | 10684.9543 | 10 | 106849.5425 | 19232.9177 | 126082.4602 | 10 | 106849.5425 | 0 | 0 | 10 | 106849.5425 | 0 |  | 0 | 0 | 106849.5425 | 19232.9177 | 126082.4602 | 0
9 | FIRE FIGHTING SYSTEM(PORTABLE AND WHEEL MOUNTED SETS FOR CONTROL ROOM,EQUIPMENT LIKE TRANSFORMER AND OTHER AREAS AS PER TECH SPEC(REFER TS-INST TO BIDDER BEFORE DESIGN-SL NO 16-ANNEXURE - I) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9.1 | FOAM TYPE-9 LTRS | NOS | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.2 | DRY CHEMICAL POWDER(TROLLEY MOUNTED)- 22.5 KGS | NOS | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.3 | DRY POWDER TYPE - 5 KGS | NOS | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.4 | CO2 - 4.5 KGS | NOS | 119.2063 | 4 | 476.8252 | 85.8285 | 562.6537 | 4 | 476.8252 | 0 | 0 | 4 | 476.8252 | 0 |  | 0 | 0 | 476.8252 | 85.8285 | 562.6537 | 0
9.5 | CO2 - 9 KGS | NOS | 119.2063 | 4 | 476.8252 | 85.8285 | 562.6537 | 4 | 476.8252 | 0 | 0 | 4 | 476.8252 | 0 |  | 0 | 0 | 476.8252 | 85.8285 | 562.6537 | 0
9.6 | CO2 (TROLLY MOUNTED)- 22.5 KGS | NOS | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.7 | 9 litre water type | Nos. | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.8 | 50 Litres Mechanical Foam type | Nos. | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
9.9 | FIRE BUCKET (6 NOS IN EACH STAND) WITH STAND AND CANOPY | SET | 119.2063 | 2 | 238.4126 | 42.9143 | 281.3268 | 2 | 238.4126 | 0 | 0 | 2 | 238.4126 | 0 |  | 0 | 0 | 238.4126 | 42.9143 | 281.3268 | 0
10 | 220 KV SIDE AUTOMATION , PROTECTION & OTHER PANELS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| SUBSTATION AUTOMATION SYSTEM: Supply of the following 220 kV level consisting of Panels, Bay control Units, DP Relays, Numerical O/C & E/F Relays, DC Supervision relays, Trip Circuit Supervision, Trip Relay ,Test Block, Differential and REF, Overfluxing, High impednce REF, Numerical O/C & E/F relay,Transformer trouble relay etc. Station level consisting of Industrial Computer with accessories, PC with accessories, laser printer, UPS, GPS System & Numerical bay control unit etc. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Sub-Station Automation (in PRP as per the indicative drg ) system (for 02 nos. 220 KV side line feeder bays ),other accessories ( Relays,auxiliary system, Ethernet Switches ,FO Patch cords, LIU,Multimode glass fibre Doublle jacket armoured optical cables, Red boxes etc . (i) Line Interface Unit(LIU) - as per requirement (for 220KV side),(ii)Managed Ethernet switch IEC 61850-3, IEEE1588v2 as per requirement,(iii) Multimode glass fibre optical cord Double Jacketted armoured, rodent sillient of required length,(iv) HDPE pipes for laying of FO cable of required length in all respect to integrate with the existing SAS system. | LS | 59360.857 | 1 | 59360.857 | 10684.9543 | 70045.8112 | 1 | 59360.857 | 0 | 0 | 1 | 59360.857 | 0 |  | 0 | 0 | 59360.857 | 10684.9543 | 70045.8112 | 0
10.2 | 220 KV SIDE PROTECTION & OTHER PANELS for SAS and Bus Bar protn. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.2.1 | BCU based FEEDER PROTECTION RELAY PANEL (MAIN-I , MAIN-II & BACK-UP PROTECTION WITH AUTO RECLOSURE DISTANCE PROTECTION with Numerical Bay control unit (BCU) (48DI, 32DO, IEC 61850 protocol with PRP ) for substation automation system. | Nos. | 29680.4285 | 2 | 59360.857 | 10684.9543 | 70045.8112 | 1 | 29680.4285 | -1 | -50% | 1 | 29680.4285 | 0 |  | 0 | 0 | 29680.4285 | 5342.4771 | 35022.9056 | -35022.9056
10.2.2 | Bus Bar Protection system in all respect to integrate with the existing system for above two nos 220 KV Line Feeders (including supply of relays,auxiliary relays,switches,FO cables,Managed Switches etc). | Nos. | 29680.4285 | 2 | 59360.857 | 10684.9543 | 70045.8112 | 1 | 29680.4285 | -1 | -50% | 1 | 29680.4285 | 0 |  | 0 | 0 | 29680.4285 | 5342.4771 | 35022.9056 | -35022.9056
11 | COLOUR CODING, BAY MARKING Etc:Design, engineering, procurement of labour, material including all associated works for the followings. This should be as per direction of site In charge. a)Color coding (red,Yellow & Blue) for equipments,Bus gantry &column of entire switch yard. Good quality weather proof sticker may be used for identification. b)Each bay should be identified with the help of bay marker sign board, suitably grouted. MS sign board with stand to be installed. Proper painting and lettering to be done of the entire switch yard area. | SET | 41552.5999 | 1 | 41552.5999 | 7479.468 | 49032.0679 | 1 | 41552.5999 | 0 | 0 | 1 | 41552.5999 | 0 |  | 0 | 0 | 41552.5999 | 7479.468 | 49032.0679 | 0
12 | BEST QUALITY & APPROVED MAKE RUBBER MAT TO BE KEPT INFRONT OF ALL PANELS,BOARDS ETC. | NOS | 178.3249 | 4 | 713.2994 | 128.3939 | 841.6933 | 1 | 178.3249 | -3 | -75% | 1 | 178.3249 | 0 |  | 0 | 0 | 178.3249 | 32.0985 | 210.4233 | -631.27
13 | WALKIE TALKIE SET | NOS | 178.3249 | 1 | 178.3249 | 32.0985 | 210.4233 | 1 | 178.3249 | 0 | 0 | 1 | 178.3249 | 0 |  | 0 | 0 | 178.3249 | 32.0985 | 210.4233 | 0
14 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
14.1 | Erection of 24 fibre(DWSM) optic approach cable along with hardware | KM | 29680.4285 | 1 | 29680.4285 | 5342.4771 | 35022.9056 | 2.5 | 74201.0712 | 1.5 | 150% | 1.25 | 37100.5356 | 1.25 |  | 29680.4285 | 37100.5356 | 74201.0712 | 13356.1928 | 87557.264 | 52534.3584 | As per the approved cable trench layout
14.2 | Digital tele-protection coupler compatible for interfacing with SDHMUX installed at 400KV Easama grid S/S and Duburi New grid S/s | NO | 23744.3428 | 2 | 47488.6856 | 8547.9634 | 56036.649 | 1 | 23744.3428 | -1 | -50% | 1 | 23744.3428 | 0 |  | 0 | 0 | 23744.3428 | 4273.9817 | 28018.3245 | -28018.3245
14.3 | Installation & commissioning of FODP(Fibre Optic Distribution panel) 48F: Indoor type, rack mounted with FCPC coupling and pig tails(DWSM Fibre) | NO | 35616.5142 | 1 | 35616.5142 | 6410.9726 | 42027.4867 | 1 | 35616.5142 | 0 | 0 | 1 | 35616.5142 | 0 |  | 0 | 0 | 35616.5142 | 6410.9726 | 42027.4867 | 0
PART-A | ERECTION COMPONENT OF THE WORKS CONTRACT FOR 220 KV Bay Extn-PARADEEP |  |  |  | 2768625.7432 | 498352.6338 | 3266978.377 |  | 3084431.4383 |  | 0 |  | 2842844.1381 |  |  |  | 163422.9038 | 3006267.0419 | 541128.0675 | 3547395.1094 | 280416.7325

## E_220kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1
ERECTION - 220kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  |  | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA | Deviation quantity |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
1 | ERECTION,TESTING & COMMISSIONING of Following tested Lattice type Galvanized steel tangent / Angle tower without stubs and cleats including different type of G.I HT Nuts & Bolts, washer, spring washer for the above type towers ,hanger and all accessories, tower super structure complete with tightening, punching of bolts including step bolts. All other left out portion of the bolts above bottom cross arm shall be riveted by using suitable hammer. Painting of black bituminous paints three coats shall be provided up to a height of 500mm above the cooping legs & bracing members. All Erection should confirm to the Technical Specification laid there in the Tender Specification and designed for Wind Zone-6 i.e. Wind Speed of 55 Mtr/Sec. |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | TOWER SUPER STRUCTURES |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | OA TYPE (SUSPENSION) TOWERS (NOMINAL UNIT WEIGHT 4.242 MT) | Nos |  | 89 | 0 | 0 | 0 | 78 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | +3 EXTENSION (NOMINAL UNIT WEIGHT 0.725MT) | Nos |  | 16 | 0 | 0 | 0 | 23 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | +6 EXTENSION (NOMINAL UNIT WEIGHT 1.448 MT) | Nos |  | 6 | 0 | 0 | 0 | 9 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.4 | OB TYPE (30 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 6.343 MT) | Nos |  | 24 | 0 | 0 | 0 | 28 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.5 | +3 EXTENSION (NOMINAL UNIT WEIGHT 1.242 MT) | Nos |  | 3 | 0 | 0 | 0 | 14 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
New | + 6 EXTENSION | Nos | [5 empty] | 2
1.1.6 | OC TYPE (60 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 9.01MT) | Nos |  | 15 | 0 | 0 | 0 | 28 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 | +3 EXTENSION (NOMINAL UNIT WEIGHT 1.474MT) | Nos |  | 2 | 0 | 0 | 0 | 14 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
New | + 6 EXTENSION | Nos | [5 empty] | 5
1.1.8 | +15 EXTENSION (NOMINAL UNIT WEIGHT 8.55 MT) | Nos |  | 2 | 0 | 0 | 0 | 4 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.9 | UR TYPE (60 deg ANGLE ) TOWERS (NOMINAL UNIT WEIGHT 12.474 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.10 | UR+6 EXTENSION (NOMINAL UNIT WEIGHT 4.148 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.11 | WEIGHT OF THE STRUCTURES | MT | 6530.1788 | 761.09 | 4970053.817 | 894609.6871 | 5864663.5041 | 1240.5588 | 8101071.0928 | 479.4688 | 63% | 951.3625 | 6212567.2713 | 289.1963 | 5744.84 | 5744.84 | 1661386.7019 | 7873953.9732 | 1417311.7152 | 9291265.6883 | 3426602.1842 | As per the approved structure drawing & route alignment(Item no 9i of RC of OPTCL RC 23-24
1.2 | Weight of different type G.I Nuts and Bolts | MT | 6530.1788 | 38.05 | 248473.305 | 44725.1949 | 293198.5 | 53.4129 | 348795.5284 | 15.3629 | 40.38% | 47.5625 | 310591.6313 | 5.8504 | 5744.84 | 5744.84 | 33609.3821 | 344201.0135 | 61956.1824 | 406157.1959 | 112958.6959 | As per approved structure drawing, Item no 9i of RC of OPTCL RC 23-24
1.3 | Fixing of of Templates & setting of stubs |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 | OA Type | Nos |  | 89 | 0 | 0 | 0 | 78 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.2 | OB Type | Nos |  | 24 | 0 | 0 | 0 | 28 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.3 | OC Type | Nos |  | 15 | 0 | 0 | 0 | 20 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.4 | OC+15 /24 TYPE (NOMINAL UNIT WEIGHT 1.068 MT) |  |  | 2 |  |  |  | 8 | 0 |  | 0%
1.3.5 | UR TYPE (NOMINAL UNIT WEIGHT 0.697 MT) | Nos |  | 3 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.6 | Weight of Templates, Stubs & Clear, Foundation Nut and Bolts | MT | 5936.0857 | 142.97 | 848682.1721 | 152762.791 | 1001444.963 | 146.9584 | 872357.9412 | 3.9884 | 2.79% | 146.9584 | 872357.9412 | 0 |  | 0 | 0 | 872357.9412 | 157024.4294 | 1029382.3706 | 27937.4076 | As per the approved structure drawing & route alignment
2 | Erection of the following tower accessories as per technical specification and as directed by the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | EARTHING DEVICE | Nos. | 2968.5274 | 173 | 513555.2448 | 92439.9441 | 605995.1889 | 142 | 421530.8946 | -31 | -17.92% | 142 | 421530.8946 | 0 |  | 0 | 0 | 421530.8946 | 75875.561 | 497406.4556 | -108588.7333
2.2 | DANGER BOARD | Nos. | 60.0877 | 131 | 7871.4919 | 1416.8685 | 9288.3605 | 134 | 8051.7551 | 3 | 2.29% | 134 | 8051.7551 | 0 |  | 0 | 0 | 8051.7551 | 1449.3159 | 9501.071 | 212.7105
2.3 | NUMBER PLATE | Nos. | 60.0877 | 131 | 7871.4919 | 1416.8685 | 9288.3605 | 134 | 8051.7551 | 3 | 2.29% | 134 | 8051.7551 | 0 |  | 0 | 0 | 8051.7551 | 1449.3159 | 9501.071 | 212.7105
2.4 | PHASE PLATE | Nos. | 60.0877 | 786 | 47228.9515 | 8501.2113 | 55730.1628 | 804 | 48310.5306 | 18 | 2.29% | 804 | 48310.5306 | 0 |  | 0 | 0 | 48310.5306 | 8695.8955 | 57006.4261 | 1276.2633
2.5 | BIRD GUARD | Nos. | 60.0877 | 534 | 32086.8449 | 5775.6321 | 37862.477 | 468 | 28121.0551 | -66 | -12.36% | 468 | 28121.0551 | 0 |  | 0 | 0 | 28121.0551 | 5061.7899 | 33182.845 | -4679.632
2.6 | ANTICLIMBING DEVICE | Nos. | 1009.8614 | 131 | 132291.8481 | 23812.5327 | 156104.3808 | 134 | 135321.4324 | 3 | 2.29% | 134 | 135321.4324 | 0 |  | 0 | 0 | 135321.4324 | 24357.8578 | 159679.2903 | 3574.9095
2.7 | CIRCUIT PLATE | Nos. | 60.0877 | 262 | 15742.9838 | 2833.7371 | 18576.7209 | 268 | 16103.5102 | 6 | 2.29% | 268 | 16103.5102 | 0 |  | 0 | 0 | 16103.5102 | 2898.6318 | 19002.142 | 425.4211
3 | Hoisting and fixing of insulators with required accessories, Hardwares etc., paying out of conductor ,jointing, stringing, sagging & Jumpering etc. of power conductor in the proposed lines and without earth wire with all required accessories including scaffolding for 33 KV,11 KV, LT , P&T lines, roads and using own required T&P and compression jointing machines etc. with 1.5% provision for Sag & Wastage and as per the direction of Engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | DOUBLE CIRCUIT(ACSR ZEBRA, SIX POWER CONDCTOR ) | RKM | 89041.2855 | 35 | 3116444.9908 | 560960.0983 | 3677405.0891 | 34 | 3027403.7053 | -1 | -2.857% | 34 | 3027403.7053 | 0 |  | 0 | 0 | 3027403.7053 | 544932.667 | 3572336.3723 | -105068.7168
3.2 | Additional charges for stringing above EHT lines/Railway/NH Crossings | RKM | 890412.8545 | 0.54 | 480822.9414 | 86548.1295 | 567371.0709 | 1.5 | 1335619.2818 | 0.96 | 177.8% | 0.675 | 601028.6768 | 0.825 | 26047.61 | 26047.61 | 21489.2782 | 622517.955 | 112053.2319 | 734571.187 | 167200.1161 | Item Anx-10.1.I.b.i of RC 23-24
4 | Supply of following items for EHV Cable as per the technical specification of OPTCL and as per the instruction of engineer in charge |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | 220kV XLPE 1C X 1000 Sqmm Copper cable having Al sheath and PVC outer sheath(Laying Condition: shall be buried 1.5 mtrs below ground level) for 2 nos. lines with 2 spare (i.e. 6 runs + 2 spare) | Mtrs. | 534.9746 | 5000 | 2674872.9017 | 481477.1223 | 3156350.024 | 10962 | 5864391.3497 | 5962 | 119.2% | 6250 | 3343591.1271 | 4712 |  | 534.9746 | 2520800.2226 | 5864391.3497 | 1055590.443 | 6919981.7927 | 3763631.7686 | As per approved cable laying schedule
4.2 | 220kV Cable sealing termination end(Outdoor Type) along with terminal connector suitable for 1C x 1000 sqmm Copper Cable | Nos. | 77169.1141 | 16 | 1234705.8249 | 222247.0485 | 1456952.8734 | 14 | 1080367.5968 | -2 | -12.5% | 14 | 1080367.5968 | 0 |  | 0 | 0 | 1080367.5968 | 194466.1674 | 1274833.7642 | -182119.1092
4.3 | EHV Cable Accessories such as Trefoil Clamp for Under Ground Cable fixing to be fixed at every one meter interval,link box,SVL,Bonding Cables,Erathing Cable for 220 KV system and any other materials required to complete the system as per technical specification,approved drawings of the Engineer In-Charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.3.1 | LINK BOX WITH SVL | Nos. | 1781.3103 | 7 | 12469.172 | 2244.451 | 14713.623 | 7 | 12469.172 | 0 | 0 | 7 | 12469.172 | 0 |  | 0 | 0 | 12469.172 | 2244.451 | 14713.623 | 0
4.3.2 | LINK BOX WITHOUT SVL | Nos. | 1781.3103 | 7 | 12469.172 | 2244.451 | 14713.623 | 7 | 12469.172 | 0 | 0 | 7 | 12469.172 | 0 |  | 0 | 0 | 12469.172 | 2244.451 | 14713.623 | 0
4.3.3 | TREFOIL CLAMP FOR EHV CABLE | Nos. | 89.1624 | 850 | 75788.0655 | 13641.8518 | 89429.9173 | 1180 | 105211.6675 | 330 | 38.82% | 1062.5 | 94735.0819 | 117.5 |  | 89.1624 | 10476.5855 | 105211.6675 | 18938.1001 | 124149.7676 | 34719.8503 | As per approved cable laying schedule
4.3.4 | SHEATH BONDING CABLE | Mtrs. | 89.1624 | 140 | 12482.7402 | 2246.8932 | 14729.6334 | 420 | 37448.2206 | 280 | 200% | 175 | 15603.4253 | 245 |  | 89.1624 | 21844.7954 | 37448.2206 | 6740.6797 | 44188.9003 | 29459.2669
4.3.5 | EARTH CONTINUTITY CABLE | Mtrs. | 89.1624 | 320 | 28531.9776 | 5135.756 | 33667.7336 |  | 0 | -320 | -100% |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -33667.7336
5 | Supply of lattice type structure as per the technical specification of OPTCL. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Structure Suport for Cable Sleaing end(16 nos), RP1 Column (3Nos), Q1 beam (2Nos.) LA(6 no) including Foundation Nuts & Bolts | MT | 5936.0857 | 21 | 124657.7996 | 22438.4039 | 147096.2036 | 0 | 0 | -21 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -147096.2036
5.2 | Total weight of GI Nuts and bolts for Equipment Structures | MT | 5936.0857 | 1.04 | 6173.5291 | 1111.2352 | 7284.7644 |  | 0 | -1.04 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -7284.7644
NEW | 220KV 1C*1000SQ.MM Copper Cable Straight Through Joint | NO.S | [5 empty] | 14 |  | 14 | 0% | 0 | 0 | 14 | 80000 | 80000 | 1120000 | 1120000 | 201600 | 1321600 | 1321600 | As per budgetary offer
6 | 220kV 10KA Class-3 Lightning arrester | Nos. | 5342.9617 | 6 | 32057.7702 | 5770.3986 | 37828.1689 | 12 | 64115.5405 | 6 | 100% | 8 | 42743.6936 | 4 | 4047.5 | 4047.5 | 16190 | 58933.6936 | 10608.0649 | 69541.7585 | 31713.5896 | Item Anx-2 10.1.i 0f RC 23-24
7 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | 24Fibre(DWSM) OPGW fibre Optic cable | KM | 47488.6856 | 35 | 1662103.9951 | 299178.7191 | 1961282.7142 | 36 | 1709592.6807 | 1 | 2.857% | 36 | 1709592.6807 | 0 |  | 0 | 0 | 1709592.6807 | 307726.6825 | 2017319.3632 | 56036.649
7.2 | OPGW hardwarw set like suspension assembly, Tension assembly(Dead end assembly, Pass through assembly), Vibration damper, Down Lead clamp Assemblies for 24F, 48 fibre(DWSM) OPGW, Joint box | KM | 5936.0857 | 35 | 207762.9994 | 37397.3399 | 245160.3393 | 36 | 213699.0851 | 1 | 2.857% | 36 | 213699.0851 | 0 |  | 0 | 0 | 213699.0851 | 38465.8353 | 252164.9204 | 7004.5811
B | ERECTION COMPONENT OF THE WORKS CONTRACT FOR 220 KV TRANSMISSION LINE-PARADEEP-ERSAMA |  |  |  | 16505202.031 | 2970936.3656 | 19476138.3966 |  | 23450502.9674 |  | 0 |  | 18214711.1936 |  |  |  | 5405796.9658 | 23620508.1594 | 4251691.4687 | 27872199.628 | 8396061.2315

## E_400kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1
ERECTION - 400kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
A | ELECTRICAL WORKS |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | ERECTION,TESTING & COMMISSIONING of Following tested Lattice type Galvanized steel tangent / Angle tower with stubs and cleats , different type of G.I HT Nuts & Bolts, washer, spring washer for the above type towers ,hanger and all accessories, tower super structure complete with tightening, punching of bolts including step bolts. All other left out portion of the bolts above bottom cross arm shall be riveted by using suitable hammer. Painting of black bituminous paints three coats shall be provided up to a height of 500mm above the cooping(legs & bracing members. All Erection should confirm to the Technical Specification laid there in the Tender Specification and designed for Wind Zone-6 i.e. Wind Speed of 55 Mtr/Sec. |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | TOWER STRUCTURES |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | DA TYPE (SUSPENSION ) TOWERS (Nominal unit weight 11.884 MT) | Nos. |  | 98 | 0 | 0 | 0 | 97 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | +3 EXTENSION (Nominal unit weight 2.085 MT) | Nos. |  | 30 | 0 | 0 | 0 | 37 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | +6 EXTENSION (Nominal unit weight 2.958MT) | Nos. |  | 9 | 0 | 0 | 0 | 15 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.4 | +9 EXTENSION (Nominal unit weight 3.988MT) | Nos. |  | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.5 | +18 EXTENSION (Nominal unit weight 9.22 MT) | Nos. |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.6 | DB TYPE (15 deg ANGLE ) TOWERS (Nominal unit weight 19.337MT) | Nos. |  | 24 | 0 | 0 | 0 | 30 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 | +3 EXTENSION (Nominal unit weight 3.04 MT) | Nos. |  | 7 | 0 | 0 | 0 | 11 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.8 | +6 EXTENSION (Nominal unit weight 4.791 MT) | Nos. |  | 0 | 0 | 0 | 0 | 13 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.9 | +9 EXTENSION (Nominal unit weight 6.295 MT) | Nos. |  | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.10 | +18 EXTENSION (Nominal unit weight 11.043 MT) |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.11 | DC TYPE (30 deg ANGLE ) TOWERS (Nominal unit weight 22.895 MT) | Nos. |  | 21 | 0 | 0 | 0 | 12 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.12 | +3 EXTENSION (Nominal unit weight 3.531 MT) | Nos. |  | 9 | 0 | 0 | 0 | 5 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.13 | +6 EXTENSION (Nominal unit weight 5.432 MT) | Nos. |  | 2 | 0 | 0 | 0 | 3 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.14 | +9 EXTENSION (Nominal unit weight 7.472 MT) |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.15 | DD TYPE (60 deg angle)TOWER (Nominal unit weight 33.658 MT) | Nos. |  | 33 | 0 | 0 | 0 | 46 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.16 | +3 EXTENSION (Nominal unit weight 5.437 MT) | Nos. |  | 2 | 0 | 0 | 0 | 5 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.17 | +6 EXTENSION (Nominal unit weight 8.084 MT) | Nos. |  | 5 | 0 | 0 | 0 | 8 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.18 | +9 EXTENSION (Nominal unit weight 10.844 MT) | Nos. |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.19 | +12 EXTENSION (Nominal unit weight 10.844 MT) | Nos. |  | 0 | 0 | 0 | 0 | 13 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.20 | +18 TO DD TYPE TOWER (Nominal unit weight 22.857 MT) | Nos. |  | 8 | 0 | 0 | 0 | 5 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.21 | +25 TO DD TYPE TOWER (Nominal unit weight 33.042 MT) | Nos. |  | 8 | 0 | 0 | 0 | 7 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.22 | WEIGHT OF THE STRUCTURES | MT | 5841.1083 | 3709.387 | 21666931.2886 | 3900047.6319 | 25566978.9205 | 4340.492 | 25353283.9584 | 631.105 | 17.01% | 4340.492 | 25353283.9584 | 0 |  | 0 | 0 | 25353283.9584 | 4563591.1125 | 29916875.0709 | 4349896.1504 | As per the approved structure drawing & route alignment
1.2 | Weight of different type G.I Nuts and Bolts | MT | 5841.1083 | 178 | 1039717.282 | 187149.1108 | 1226866.3927 | 132.212 | 772264.6139 | -45.788 | -25.72% | 132.212 | 772264.6139 | 0 |  | 0 | 0 | 772264.6139 | 139007.6305 | 911272.2445 | -315594.1483 | As per approved structure drawing
1.3 | Fixing of templates and setting of stubs |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 | DA TYPE (SUSPENSION ) TOWERS | Nos. |  | 98 | 0 | 0 | 0 | 97 | 0 |  | 0 | 97 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.2 | DB TYPE (15 deg ANGLE ) TOWERS | Nos. |  | 24 | 0 | 0 | 0 | 30 | 0 |  | 0 | 30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.3 | DC TYPE (30 deg ANGLE ) TOWERS | Nos. |  | 21 | 0 | 0 | 0 | 12 | 0 |  | 0 | 12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.4 | DD TYPE (60 deg angle)TOWER | Nos. |  | 33 | 0 | 0 | 0 | 46 | 0 |  | 0 | 41.25 | 0 | 4.75 |  | 0 | 0 | 0 | 0 | 0 | 0
1.3.5 | Weight of Templates, Stub & Cleat & Foundation Nut and Bolts | MT | 5841.1083 | 530 | 3095787.4126 | 557241.7343 | 3653029.1468 | 348.17 | 2033698.6857 | -181.83 | -34.31% | 348.17 | 2033698.6857 | 0 |  | 0 | 0 | 2033698.6857 | 366065.7634 | 2399764.4492 | -1253264.6977 | As per the approved structure drawing & route alignment
2 | Erection of the following tower accessories as per technical specification and as directed by the engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | EARTHING DEVICE | Nos. | 1752.2356 | 254 | 445067.8378 | 80112.2108 | 525180.0486 | 254 | 445067.8378 | 0 | 0 | 254 | 445067.8378 | 0 |  | 0 | 0 | 445067.8378 | 80112.2108 | 525180.0486 | 0
2.2 | DANGER BOARD | Nos. | 117.268 | 176 | 20639.1642 | 3715.0496 | 24354.2138 | 186 | 21811.844 | 10 | 5.682% | 186 | 21811.844 | 0 |  | 0 | 0 | 21811.844 | 3926.1319 | 25737.976 | 1383.7621
2.3 | NUMBER PLATE | Nos. | 117.268 | 176 | 20639.1642 | 3715.0496 | 24354.2138 | 186 | 21811.844 | 10 | 5.682% | 186 | 21811.844 | 0 |  | 0 | 0 | 21811.844 | 3926.1319 | 25737.976 | 1383.7621
2.4 | PHASE PLATE | Nos. | 117.268 | 1056 | 123834.9855 | 22290.2974 | 146125.2829 | 1116 | 130871.0642 | 60 | 5.682% | 1116 | 130871.0642 | 0 |  | 0 | 0 | 130871.0642 | 23556.7916 | 154427.8557 | 8302.5729
2.5 | BIRD GUARD | Nos. | 175.4174 | 588 | 103145.4251 | 18566.1765 | 121711.6016 | 582 | 102092.9207 | -6 | -1.02% | 582 | 102092.9207 | 0 |  | 0 | 0 | 102092.9207 | 18376.7257 | 120469.6465 | -1241.9551
2.6 | ANTICLIMBING DEVICE | Nos. | 4088.8727 | 176 | 719641.6029 | 129535.4885 | 849177.0914 | 186 | 760530.3303 | 10 | 5.682% | 186 | 760530.3303 | 0 |  | 0 | 0 | 760530.3303 | 136895.4595 | 897425.7898 | 48248.6984
2.7 | Circuit plate | Nos. | 117.268 | 352 | 41278.3285 | 7430.0991 | 48708.4276 | 372 | 43623.6881 | 20 | 5.682% | 372 | 43623.6881 | 0 |  | 0 | 0 | 43623.6881 | 7852.2639 | 51475.9519 | 2767.5243
2.8 | Counterpoise earthing including all materials | Mtrs | 33.9205 | 400 | 13568.1959 | 2442.2753 | 16010.4711 | 0 | 0 | -400 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -16010.4711
3 | Hoisting and fixing of insulators with required accessories, Hardwares etc., paying out of conductor,GI Earth wire & its hardware ,jointing, stringing, sagging & Jumpering etc. of power conductor in the proposed lines and without earth wire with all required accessories including scaffolding for 33 KV,11 KV, LT , P&T lines, roads and using own required T&P and compression jointing machines etc. with 1.5% provision for Sag & Wastage and as per the direction of Engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | ACSR Moose(54/7/3.53 mm) for 400kv lines | Route Kms. | 350494.6051 | 68.3 | 23938781.5273 | 4308980.6749 | 28247762.2022 | 68.448 | 23990654.7288 | 0.148 | 0.2167% | 68.448 | 23990654.7288 | 0 |  | 0 | 0 | 23990654.7288 | 4318317.8512 | 28308972.58 | 61210.3778
3.2 | Additional Charges for stringing in EHV LINE crossing/Railway/National Highway crossing. | Route Kms. | 584158.3212 | 1.5 | 876237.4819 | 157722.7467 | 1033960.2286 | 2.134 | 1246593.8575 | 0.634 | 42.27% | 1.875 | 1095296.8523 | 0.259 | 77228.88 | 77228.88 | 20002.2799 | 1115299.1323 | 200753.8438 | 1316052.9761 | 282092.7475 | As per approved route alignment (Item Anx-I10.1.c.i of RC 23-24)
3.3 | Additional Charges for stringing in river crossing tower | Route Kms. | 1051484.7844 | 2 | 2102969.5688 | 378534.5224 | 2481504.0912 | 3.43 | 3606592.8105 | 1.43 | 71.5% | 2.5 | 2628711.961 | 0.93 | 143425.06 | 143425.06 | 133385.3058 | 2762097.2668 | 497177.508 | 3259274.7749 | 777770.6836 | As per approved route alignment (Item Anx-I10.1.c.ii of RC 23-24)
3.4 | Additional Charges for stringing in tower placed in Hilly terrain | Route Kms. | 490692.8348 | 1 | 490692.8348 | 88324.7103 | 579017.545 |  | 0 | -1 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -579017.545
4 | Supply of all materials for continuous welding of bolts & nuts (around the bolts) up to top of tower without cross arm, including welding rods, welding generator machine (diesel engine optd.), application of required zinc rich paints around the welding portion (two coats),fuel,lubricants,T&P and labours. | Nos. | 5.8149 | 587986 | 3419103.9522 | 615438.7114 | 4034542.6635 | 432343 | 2514049.076 | -155643 | -26.47% | 432343 | 2514049.076 | 0 |  | 0 | 0 | 2514049.076 | 452528.8337 | 2966577.9096 | -1067964.7539 | As per the approved structure drawing
5 | ACCESSORIES FOR OPGW SYSTEM AS PER TECHNICAL SPECIFICATION) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | 24Fibre(DWSM) OPGW fibre Optic cable | Kms | 40890.6657 | 69 | 2821455.9367 | 507862.0686 | 3329318.0053 | 71.577 | 2926831.1824 | 2.577 | 3.735% | 71.577 | 2926831.1824 | 0 |  | 0 | 0 | 2926831.1824 | 526829.6128 | 3453660.7952 | 124342.7899
5.2 | OPGW hardwarw set like suspension assembly, Tension assembly(Dead end assembly, Pass through assembly), Vibration damper, Down Lead clamp Assemblies for 24F, 48 fibre(DWSM) OPGW, Joint box | Kms | 11683.1858 | 69 | 806139.8208 | 145105.1677 | 951244.9885 | 68.448 | 799690.7022 | -0.552 | -0.8% | 68.448 | 799690.7022 | 0 |  | 0 | 0 | 799690.7022 | 143944.3264 | 943635.0286 | -7609.9599
C | TOTAL OF ERECTION COMPONENT OF THE WORKS CONTRACT FOR 400 KV TRANSMISSION LINE-ERSAMA-LOC-358 to LOC-182) |  |  |  | 61745631.8096 | 11114213.7257 | 72859845.5353 |  | 64769469.1447 |  | 0% |  | 63640291.2899 |  |  |  | 153387.5857 | 63793678.8757 | 11482862.1976 | 75276541.0733 | 2416695.538

## C_220KV Bay
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1 | [20 empty] | CIVIL - 220kV BAY
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
PART B | CIVIL WORKS |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | CONTOUR SURVEY,AND LEVELING, BACK FILLING |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Contour survey and furnishing contour map including supply of all materials, Labour and T&P | SQ.MTRS. | 7.7533 | 5000 | 38766.2739 | 6977.9293 | 45744.2032 | 7500 | 58149.4109 | 2500 | 50% | 6250 | 48457.8424 | 1250 | 4.57 | 4.57 | 5712.5 | 54170.3424 | 9750.6616 | 63921.0041 | 18176.8008 | As per the site requirement, Item 1.1 of OPTCL RC 23-24
1.2 | Soil investigation : Supply of labour,T&Pand other necessary arrangements for Soil investigation/testing of the Switchyard,control Room, Quarters area etc.as per the site requirement,Technical specification & instruction of Engineer-in-Charge. | PER POINT | 26712.8702 | 5 | 133564.3511 | 24041.5832 | 157605.9343 | 5 | 133564.3511 | 0 | 0% | 5 | 133564.3511 | 0 |  | 0 | 0 | 133564.3511 | 24041.5832 | 157605.9343 | 0
2 | Excavation for OPEN CAST and PILE foundation and back filling of columns,Equipments foundations,including supply of all labours,T&P,and materials and as per the direction of the Engineer-in-Charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Soft Soil/Loose Soil. | CUM | 83.3475 | 450 | 37506.37 | 6751.1466 | 44257.5166 | 450 | 37506.37 | 0 | 0% | 450 | 37506.37 | 0 |  | 0 | 0 | 37506.37 | 6751.1466 | 44257.5166 | 0
2.2 | Hard/Dense Soil. | CUM | 119.2063 | 150 | 17880.9439 | 3218.5699 | 21099.5137 | 0 | 0 | -150 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -21099.5137
2.3 | Muddy Soil. | CUM | 119.2063 | 500 | 59603.1462 | 10728.5663 | 70331.7125 | 0 | 0 | -500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -70331.7125
2.4 | Soft/Disintegrated Rock (not requiring blasting) | CUM | 297.5312 | 50 | 14876.5576 | 2677.7804 | 17554.338 | 0 | 0 | -50 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -17554.338
2.5 | Hard rock (requiring blasting/using breaker machinery) | CUM | 594.0931 | 50 | 29704.6574 | 5346.8383 | 35051.4957 | 0 | 0 | -50 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -35051.4957
3 | Cutting, Filling and Leveling of Sub-station area including supply of labour and T&P |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | LEVELLING OF S/S AREA:Providing, neatly dressing up and levelling of substation area including switchyard area to a required level as decided by the Engineer in Charge, the work includes removal, clearing of the entire area from vegetation, trees, bushes, uprooting of plants and disposal of surplus earth and unusable material from the site by means of any mechanical transport, if required as per direction of the Project In charge, with all labours, tools, tackles and plants complete as per approved drawing and specification. This also includes excavation in all type of soils or rocks, back filling and disposal of excess earth or rocks to make the area to a level for construction as per scope and as per approved drawing and specification. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | CUTTING of substation area |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.1 | [i]Soft/loose soil | CUM | 178.3249 | 40 | 7132.9944 | 1283.939 | 8416.9334 | 0 | 0 | -40 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -8416.9334
3.2.1 | FILLING of substation area with borrowed earth with supply of all labour,T & P. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.2.1.1 | Beyond 100mtr lead | CUM | 415.7683 | 9600 | 3991375.5646 | 718447.6016 | 4709823.1663 | 7500 | 3118262.1599 | -2100 | -21.88% | 7500 | 3118262.1599 | 0 |  | 0 | 0 | 3118262.1599 | 561287.1888 | 3679549.3487 | -1030273.8176 | As per the site requirement
4 | Anti-Weed Treatment |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Supply of labour,T&P,Chemicals and other necessary arrangements for anti-weed treatment of the switch-yard areas,controlroom etc. as per the instruction of Engineer-in-Charge. | Sq.Mtrs | 9.6916 | 3200 | 31013.0192 | 5582.3434 | 36595.3626 | 3200 | 31013.0192 | 0 | 0% | 3200 | 31013.0192 | 0 |  | 0 | 0 | 31013.0192 | 5582.3434 | 36595.3626 | 0
5 | PILE FOUNDATION (UNDER-REAM PILE) BORING &CONCRETE WORKS AND PILE RISER,CAPPING,PEDESTAL & TIE-BEAM CONCRETE WORKS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Boring for under ream cast-in-Situ piling, with Manual Auger method or by using Motor driven Machinery,including supply of Bentonite required for stabilization bore of required diameter bore holes & approximate length of the bore is 10 Mtrs. with under reemed piles. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1.1 | 250MM DIA | Mtrs. | 415.7683 | 50 | 20788.4144 | 3741.9146 | 24530.329 | 0 | 0 | -50 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -24530.329
5.1.2 | 300MM DIA | Mtrs. | 415.7683 | 70 | 29103.7802 | 5238.6804 | 34342.4606 | 100 | 41576.8288 | 30 | 42.86% | 87.5 | 36379.7252 | 12.5 | 759.63 | 415.7683 | 5197.1036 | 41576.8288 | 7483.8292 | 49060.658 | 14718.1974 | As per the approved foundation drawing, Item 4.1.ii of OPTCL RC 23-24
5.1.3 | 375MM DIA | Mtrs. | 415.7683 | 1300 | 540498.7744 | 97289.7794 | 637788.5538 | 1500 | 623652.432 | 200 | 15.38% | 1500 | 623652.432 | 0 |  | 0 | 0 | 623652.432 | 112257.4378 | 735909.8697 | 98121.316 | As per the approved foundation drawing
5.1.4 | 400MM DIA | Mtrs. | 474.8869 | 60 | 28493.2113 | 5128.778 | 33621.9894 | 0 | 0 | -60 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -33621.9894
5.1.5 | 450MM DIA | Mtrs. | 534.9746 | 100 | 53497.458 | 9629.5424 | 63127.0005 | 0 | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -63127.0005
5.1.6 | 500MM DIA | Mtrs. | 712.3303 | 100 | 71233.0284 | 12821.9451 | 84054.9735 | 0 | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -84054.9735
NEW | Design, Engineering, Providing and laying of plain cement concrete (PCC 1:3:6) of grade M10 with approved quality coarse aggregates (Nominal size 12mm to 20mm) , fine aggregates, cement in Column & Equipments foundation as blind layer inclusive of labour charges for concrete mixing & curing. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. | CUM |  |  | 0 | 0 | 0 | 35 | 0 | 35 | 0% | 0 | 0 | 35 | 5237.8 | 5237.8 | 183323 | 183323 | 32998.14 | 216321.14 | 216321.14
5.2 | Supply of all materials like cement, all coarse aggregates, fine aggregates and making Under-reamed pile foundations (after pile boring as per required depth, basing on design), Pile riser (if required),capping, tie beams etc, required for foundation of columns, equipment etc. as per requirement including supply of all equipment with labours, proper curing of the foundations and T&P as per specification in the concrete ratio 1:1.5:3 (Grade M-20) in all type of soil & back filling and disposal of excess earth as per the direction of Engineer In Charge. | CUM | 7717.396 | 590 | 4553263.6307 | 819587.4535 | 5372851.0842 | 400 | 3086958.3937 | -190 | -32.2% | 400 | 3086958.3937 | 0 |  | 0 | 0 | 3086958.3937 | 555652.5109 | 3642610.9045 | -1730240.1797
5.3 | Supply of Steel of different size (as per design) with cutting, bending, binding in position of M.S.Rod for reinfocement of foundation concrete of Piles(Under reem Pile), Capping, Pile Risers and Tie Beams etc. including supply of binding wire (With supply of MS Rod (FE-500-TATA/ RINL/ Sail/JINDAL) as per BIS-1786 ). | MT. | 72942.621 | 42 | 3063590.0837 | 551446.2151 | 3615036.2988 | 25 | 1823565.526 | -17 | -40.48% | 25 | 1823565.526 | 0 |  | 0 | 0 | 1823565.526 | 328241.7947 | 2151807.3207 | -1463228.9781
6 | Cable Trenches: Design, engineering, and construction of RCC cable trenches and all associated works for cable trench and cable trench crossings as per technical specifications and approved drawings and as per direction of the Engineer in Charge including supply of all labour, T&P, materials. (1) This also includes excavation in all types of soil or rocks,back filling,and disposal of excess earth as per the direction of Engineer In charge. (2) Design, Engineering, Providing and laying of plain cement concrete (PCC 1:3:6) of grade M10 with approved quality coarse aggregates (Nominal size 12mm to 20mm) , fine aggregates, cement in column and equipment foundation as blind layer inclusive of labour charges for concrete mixing & curing. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. (3) Open cast foundation for the cable trench with RCC: 1:1.5:3 (Grade M-20 Nominal mixing),including supply of Labour all materials like MS Rod (FE-500-TATA/ RINL/ Sail/JINDAL) as per BIS-1786 ),Cement, coarse and fine aggregates,shuttering,cutting,bending,binding of M.S.Rod including supply of binding wire proper curing of the foundations/concrete and T&P in line with the Specification and as per direction of Engineer in Charge. (4) Fly ash brickwork with Fly ash brick ,plastering (!:6 Ratio) & curing, wherever required including the supply of labour,material, cement, etc. (5)Supply,fabrication & Fixing of MS Angle(G.I) for cable tray support (as per specification). The cable tray support frame shall be pre fabricated GI angle as per requirement and to be welded with the plate fixed on the trench wall for better rigidity. The plate (6mm) fixed on the wall are also to be welded with the MS rods provided for the trench wall before concreting. (6) Precast of RCC covers (1:1.5:3) and its fixing on the cable trench as per spec and instruction of Engg. In Charge. (7) CABLE TRENCHES INSIDE THE CONTROL ROOM SHALL BE COVERED WITH M.S CHEQUERED PLATE(Duly painted as per instruction of Engg in charge) INCLUDING STANDARD SUPPORT STAND {HD Galvanised (M.S JOIST ,CHANNEL,ANGLE)}. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Cable trench with covers |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 | Section 2- 2 | Mtrs | 10565.748 | 100 | 1056574.7962 | 190183.4633 | 1246758.2595 | 100 | 1056574.7962 | 0 | 0% | 100 | 1056574.7962 | 0 |  | 0 | 0 | 1056574.7962 | 190183.4633 | 1246758.2595 | 0
6.1.2 | Section 3-3 | Mtrs | 9553.9482 | 200 | 1910789.6424 | 343942.1356 | 2254731.778 | 150 | 1433092.2318 | -50 | -25% | 150 | 1433092.2318 | 0 |  | 0 | 0 | 1433092.2318 | 257956.6017 | 1691048.8335 | -563682.9445
6.1.3 | Section 4-4 | Mtrs | 2621.5693 | 75 | 196617.6956 | 35391.1852 | 232008.8808 | 75 | 196617.6956 | 0 | 0% | 75 | 196617.6956 | 0 |  | 0 | 0 | 196617.6956 | 35391.1852 | 232008.8808 | 0 | As per approved layout
7 | Cable trench crossing:Design,engineering,construction including supply of labour, materials, cement, reinforcement steel, form box etc,and all associated works for construction of trench crossing as per technical specification and approved drawing. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | Road crossing for |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | Section 2- 2 & Section 3-3 | Nos | 356165.1418 | 2 | 712330.2836 | 128219.451 | 840549.7347 |  | 0 | -2 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -840549.7347
8 | PCC before site surfacing :Providing and supplying all labour, material, equipments etc. required for proper levelling of earth after erection of structures and equipments and proper compaction by using roller of adequate capacity(minimum 3 Ton capacity) with water sprinkling of switch yard area .After proper levelling of the switch yard area (after anti-weed treatment), spreading of plain cement concert with mixing ratio 1:4:8 (M10) and maintaining proper sloping for easy discharge of storm water having concrete thickness of 75 mm. including rolling , dressing, compacting,the area . As per technical specification and approved drawing, and as per the instruction of the Engg-in-Charge.This also includes excavation in all types of soil or rocks,backfilling,and disposal of excess earth as per the direction of Engineer In charge and approved drawing. | CUM | 4773.0975 | 200 | 954619.4957 | 171831.5092 | 1126451.005 | 280 | 1336467.294 | 80 | 40% | 250 | 1193274.3697 | 30 | 5145.91 | 4773.0975 | 143192.9244 | 1336467.294 | 240564.1129 | 1577031.4069 | 450580.402 | As per the approved layout, Item 3.3.i of OPTCL RC 23-24
9 | METAL SPREADING IN THE SWITCH-YARD |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9.1 | Providing supplying and laying two layers of machine crushed metals (gravel) fill, the first layer after compaction shall make minimum 50 mm thickness coarse/ layer of 20 mm nominal size consolidated/ compacted and (by using roller as specified in the specification).A final layer of 50 mm thickness of machine crushed 20 mm nominal size of metals(gravel) above the first layer of 50 mm thickness and as per the technical specification and instruction of Engineer in charge above the PCC(1:4:8).The total compacted thickness of the metals(20 mm Nominal) 100mm above the PCC. | CUM | 3027.646 | 300 | 908293.7984 | 163492.8837 | 1071786.6821 | 370 | 1120229.018 | 70 | 23.33% | 370 | 1120229.018 | 0 |  | 0 | 0 | 1120229.018 | 201641.2232 | 1321870.2412 | 250083.5592 | As per the approved layout
10 | Roads: Design, construction of roads and walkways/ shoulders within sub-station as per specification, layout and approved drawings complete. This also includes excavation in all types of soil or rocks,backfilling,and disposal of excess earth as per the direction of Engineer In charge. Provision of drains on both the side of the roads for easy discharge of rain water. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | 3.75 mtrs Concrete road with shoulder at both the side & shall have drain on both side of the road as per technical specification indicated in the civil section( Periphery roads outside switch yard fencing and colony roads) | MTRS | 13291.9862 | 100 | 1329198.6176 | 239255.7512 | 1568454.3688 | 100 | 1329198.6176 | 0 | 0% | 100 | 1329198.6176 | 0 |  | 0 | 0 | 1329198.6176 | 239255.7512 | 1568454.3688 | 0
10.2 | 7 mtrs wide Concrete roads with shoulder as per specification indicated in the civil section.( for main and approach roads).Shall have drain on both side of the road. | MTRS | 20092.5598 | 100 | 2009255.9782 | 361666.0761 | 2370922.0543 | 0 | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -2370922.0543
11 | Drainage system:Collection of rainfall data, Design, construction of storm water drainage scheme, road-culverts, and drains crossing cable trenches etc. as per specification and approved drawing. This also includes excavation in all types of soil or rocks,backfilling,and disposal of excess earth as per the direction of Engineer In charge. All the switcyard bays , roads water drainage shall be connected to the main surface drain. As per approved drawing and specification. RCC type drainage system to be considered. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | Storm water drain | MTRS | 2374.4343 | 200 | 474886.8557 | 85479.634 | 560366.4898 | 350 | 831051.9975 | 150 | 75% | 250 | 593608.5697 | 100 |  | 2374.4343 | 237443.4279 | 831051.9975 | 149589.3596 | 980641.3571 | 420274.8673 | As per the approved layout
11.2 | Road-culverts, drain crossings | MTRS | 5936.0857 | 250 | 1484021.4242 | 267123.8564 | 1751145.2805 | 0 | 0 | -250 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1751145.2805
11.3 | Cable trench crossing | MTRS | 2968.5274 | 100 | 296852.7427 | 53433.4937 | 350286.2364 | 0 | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -350286.2364
12 | Switchyard fencing: Providing and fixing of G.I chain link(2.5mm dia) fencing( the posts and links shall be of HD Galvanised ) in switch yard and other areas of the substation with a total fence height complete as per specification and approved drawings, and as required under the safety regulation of local, state and central government bodies and as per instruction of the Engineer-in-Charge.(The PCC work for grouting the post shall be 1:2:4 and a continuous RR masonary work with ratio 1:5 and cement pointing of the joints, for the fencing upto a height of 350mm from the finished ground level) .This also includes excavation in all types of soil or rocks,backfilling,and disposal of excess earth as per the direction of Engineer In charge. The earthing of the fencing as per specification. | MTRS | 4647.1071 | 250 | 1161776.7721 | 209119.819 | 1370896.5911 | 350 | 1626487.4809 | 100 | 40% | 312.5 | 1452220.9651 | 37.5 |  | 4647.1071 | 174266.5158 | 1626487.4809 | 292767.7466 | 1919255.2275 | 548358.6364 | As per approved layout drawing and fenching around the specail tower is concidered
13 | STONE PITCHING & TOE WALL:Stone pitching including making of toe walls both at top and bottom, including surface drain both at top and bottom and partition wall in every 10 mtrs by using boulders and RR masonry walls respectively. This also includes excavation in all types of soil or rocks,back filling,and disposal of excess earth and supply of materials and labour & T&P as per the direction of Engineer In charge and as per approved drawing and specification. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13.1 | Excavation in Soft & Loose Soil | Cum | 119.2063 | 500 | 59603.1462 | 10728.5663 | 70331.7125 | 500 | 59603.1462 | 0 | 0% | 500 | 59603.1462 | 0 |  | 0 | 0 | 59603.1462 | 10728.5663 | 70331.7125 | 0
13.2 | P.C.C (1:3:6): Lean Concrete Grade M-10 | Cum | 5606.5724 | 50 | 280328.6184 | 50459.1513 | 330787.7697 | 50 | 280328.6184 | 0 | 0% | 50 | 280328.6184 | 0 |  | 0 | 0 | 280328.6184 | 50459.1513 | 330787.7697 | 0
13.3 | RR Masonry (1:5) | Cum | 3680.8577 | 500 | 1840428.8552 | 331277.1939 | 2171706.0491 | 500 | 1840428.8552 | 0 | 0% | 500 | 1840428.8552 | 0 |  | 0 | 0 | 1840428.8552 | 331277.1939 | 2171706.0491 | 0
13.4 | P.C.C (1:2:4): Lean Concrete Grade M-15 | Cum | 6279.1672 | 50 | 313958.3611 | 56512.505 | 370470.866 | 50 | 313958.3611 | 0 | 0% | 50 | 313958.3611 | 0 |  | 0 | 0 | 313958.3611 | 56512.505 | 370470.866 | 0
PART-A | CIVIL COMPONENT OF THE WORKS CONTRACT FOR 220 KV Bay Extn-PARADEEP |  |  |  | 27711429.3427 | 4988057.2817 | 32699486.6244 |  | 20378286.6041 |  | 0% |  | 19808495.064 |  |  |  | 749135.4716 | 20557630.5356 | 3700373.4964 | 24258004.032 | -8441482.5924
[11 empty] | 0% | [9 empty] | 0

## C_220kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1
CIVIL - 220kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks | Open Cast | Pile | Total
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
1 | SURVEY OF LINE & PREPARATION LAND SCHEDULE: Supply of required T&P’s, Technical personnel’s, labours for conducting | [9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Preliminary survey, Detail survey and resurvey (required for avoiding ROW problem) including but not limited to taking of levels, profile plotting, tower spotting ,marking of towers locations at site including showing P&T line, power line, Railway line, river crossing, roads and submission of route map and survey report etc. The P&T lines and railway lines for a minimum distance of 8 kms on either side of alignment shall be clearly indicated. | KM. | 7123.3028 | 34.871 | 248396.6932 | 44711.4048 | 293108.098 | 0 | 0 | -34.871 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -293108.098
1.2 | Check survey including supply of all labour, T&P as per instruction of Engineer in Charge and as per the approved profile. | KM. | 10684.9543 | 34.871 | 372595.0398 | 67067.1072 | 439662.147 | 36 | 384658.3531 | 1.129 | 3.238% | 36 | 384658.3531 | 0 |  | 0 | 0 | 384658.3531 | 69238.5036 | 453896.8567 | 14234.7098
1.3 | Preparation of land schedule on revenue (if required) maps indicating alignment therein duly authenticated by Revenue Inspector & Tahasildar, enumeration of trees with the help of Forest officer and other prominent features required for alignment of the proposed 220 KV line. Final route to be plotted on 1:50000 topo sheet for approval. | KM. | 7123.3028 | 34.871 | 248396.6932 | 44711.4048 | 293108.098 | 0 | 0 | -34.871 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -293108.098
1.4 | Soil Testing in complete shape along with submission of report etc. up to the depth of 15 Mtrs. | Per Loc. | 35616.5142 | 30 | 1068495.4254 | 192329.1766 | 1260824.602 | 25 | 890412.8545 | -5 | -16.67% | 25 | 890412.8545 | 0 |  | 0 | 0 | 890412.8545 | 160274.3138 | 1050687.1683 | -210137.4337
2 | EXCAVATION WORKS FOR FOUNDATIONS: |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Excavation for following type of soil and rocks and back filling (back filling shall be done in layers of 500mm sprinkling of water and compaction thereafter and disposed of excess quantity of excavated soil at suitable place after back filling), & if required for filling the foundation, borrowed earth/morrum/sand shall be brought for filling and compaction, including supply of sand, all T&P, labour as required. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Soft/Loose soil | CUM | 119.2063 | 3700 | 441063.2817 | 79391.3907 | 520454.6724 | 3327.77 | 396691.1235 | -372.23 | -10.06% | 3327.77 | 396691.1235 | 0 |  | 0 | 0 | 396691.1235 | 71404.4022 | 468095.5258 | -52359.1467 | As per approved foundation drawing and site requirement | #REF! | #REF! | #REF!
2.1.2 | Dense/Compact soil | CUM | 142.4661 | 5000 | 712330.2836 | 128219.451 | 840549.7347 | 3327.77 | 474094.2696 | -1672.23 | -33.44% | 3327.77 | 474094.2696 | 0 |  | 0 | 0 | 474094.2696 | 85336.9685 | 559431.2381 | -281118.4966 | As per approved foundation drawing and site requirement | #REF! | #REF! | #REF!
2.1.3 | Soft/Disintegrated rock(not requiring blasting) | CUM | 297.5312 | 600 | 178518.6915 | 32133.3645 | 210652.056 | 0 | 0 | -600 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -210652.056 |  | #REF! | #REF! | #REF!
2.1.4 | Hard rock (requiring blasting/using breaker machinery) | CUM | 594.0931 | 500 | 297046.574 | 53468.3833 | 350514.9574 | 0 | 0 | -500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -350514.9574 |  | #REF! | #REF! | #REF!
2.1.5 | Fully submerged soil | CUM | 142.4661 | 4500 | 641097.2552 | 115397.5059 | 756494.7612 | 0 | 0 | -4500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -756494.7612 |  | #REF! | #REF! | #REF!
2.1.6 | Partial Submerged soil | CUM | 130.8362 | 5700 | 745766.1949 | 134237.9151 | 880004.11 | 0 | 0 | -5700 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -880004.11 |  | #REF! | #REF! | #REF!
3.0 | FOUNDATION MATERIALS: Supply of all materials like cement, steel, all coarse aggregates, fine aggregates and making foundations of the required above mentioned type towers as per the direction laid down in the technical specification and the direction of the site- in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1 | OPEN CAST AND PILE FOUNDATION .This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Design, Engineering, Providing and laying of plain cement concrete (PCC 1:3:6) of grade M10 with approved quality coarse aggregates (Nominal size 12mm to 20mm) , fine aggregates, cement in tower foundation as blind layer inclusive of labour charges for concrete mixing & curing. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. | CUM | 5910.8876 | 360 | 2127919.5427 | 383025.5177 | 2510945.0604 | 545.87 | 3226576.2244 | 185.87 | 51.63% | 450 | 2659899.4284 | 95.87 | 5513.48 | 5513.48 | 528577.3276 | 3188476.756 | 573925.8161 | 3762402.5721 | 1251457.5117 | As per approved foundation drawing , Item no 6.2 iii of OPTCL RC 23-24 | #REF! | #REF! | #REF!
3.1.2 | Design, Engineering and laying of reinforced cement concrete (RCC1:1.5:3) of grade M20 for open cast foundation and pile caping, riser and tie beam for under ream/DMC (500 mm dia) and reverbed pile (1000 mm dia) with supply of approved quality coarse aggregates(Nominal size 12mm to 20mm), fine aggregates, cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample cement concrete cubes as per IS. The surrounding area shall be clear from materials. Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. | CUM | 9047.0792 | 3463 | 31330035.2013 | 5639406.3362 | 36969441.5375 | 7044.388 | 63731136.0125 | 3581.388 | 103.4% | 4328.75 | 39162544.0016 | 2715.638 | 7870.43 | 7870.43 | 21373238.7843 | 60535782.7859 | 10896440.9015 | 71432223.6874 | 34462782.1499 | As per approved foundation drawing ,Item no 6.4 i of OPTCL RC 23-24 | #REF! | #REF! | #REF!
3.1.3 | Design, Engineering and laying of reinforced cement concrete (RCC 1:1::2) of grade M25 for riverbed pile (1000 mm dia) foundation with supply of approved quality coarse aggregates (Nominal size 12mm to 20mm), fine aggregates, cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample cement concrete cubes as per IS. The surrounding area shall be clear from materials, Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. | CUM | 11463.1872 | 95 | 1089002.7843 | 196020.5012 | 1285023.2855 | 0 | 0 | -95 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1285023.2855 |  |  | #REF! | #REF!
3.1.4 | Design, Engineering and laying of reinforced cement concrete (RCC 1:1.5:3) of grade M20 for under ream and DMC (500 mm dia) foundation with supply of approved quality coarse aggregates (Nominal size 12mm to 20mm), fine aggregates, cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample cement concrete cubes as per IS. The surrounding area shall be clear from materials, Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. | CUM | 9047.0792 | 1650 | 14927680.6474 | 2686982.5165 | 17614663.164 | 8156.05 | 73788430.1482 | 6506.05 | 394.3% | 2062.5 | 18659600.8093 | 6093.55 | 7870.43 | 7870.43 | 47958858.7265 | 66618459.5358 | 11991322.7164 | 78609782.2522 | 60995119.0883 | As per approved foundation drawing ,Item no 6.4 i of OPTCL RC 23-24 |  | #REF! | #REF!
3.1.5 | Cutting, bending, hooking, fixing and binding in poisition of MS Rod (FE-500-TATA/ RINL/ Sail/JINDAL) as per BIS-1786 for rainforcement of foundation concrete of towers including supply of wire for binding (With supply of steel rod FE-500 as per BIS-1786 of different size(as per design). | MT | 72942.621 | 353 | 25748745.2277 | 4634774.141 | 30383519.3687 | 1161.31 | 84708995.2418 | 808.31 | 229% | 441.25 | 32185931.5346 | 720.06 | 68623.36 | 68623.36 | 49412936.6016 | 81598868.1362 | 14687796.2645 | 96286664.4007 | 65903145.0321 | As per approved foundation drawing , Item no 6.5 i of OPTCL RC 23-24 | #REF! | #REF! | #REF!
3.2 | Pile foundation: Boring for under ream cast in situ piling with bentonite sowing for stabilization of bore. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 | Boring for under reamed cast in situ piling with betonite showing for stabilisation of bore pile diameter (500mm) & approximate length of the bore is 10 Mtrs to 12 Mtrs with under reem in sandy and submerged soil | MTR | 1049.5969 | 7800 | 8186855.5616 | 1473634.0011 | 9660489.5627 | 14976 | 15718762.6782 | 7176 | 92% | 9750 | 10233569.452 | 5226 | 1470.26 | 1049.5969 | 5485193.2263 | 15718762.6782 | 2829377.2821 | 18548139.9603 | 8887650.3977 | As per approved foundation drawing , Item no 7.1 Vi of OPTCL RC 23-24 |  | #REF! | #REF!
3.2.2 | Boring by DMC method piling with betonite showing for stabilisation of bore pile diameter (500mm) & approximate length of the bore is 10 Mtrs to 18 Mtrs in sandy and submerged soil | MTR | 2469.4116 | 500 | 1234705.8249 | 222247.0485 | 1456952.8734 | 0 | 0 | -500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1456952.8734 |  |  |  | 0
3.2.3 | Boring by DMC method piling with betonite showing for stabilisation of bore pile diameter (1000mm) & approximate length of the bore is 25 Mtrs to 30 Mtrs in river bed and river bank. | MTR | 6173.5291 | 120 | 740823.495 | 133348.2291 | 874171.724 | 6000 | 37041174.7477 | 5880 | 4900% | 150 | 926029.3687 | 5850 | 6462.95 | 6173.5291 | 36115145.379 | 37041174.7477 | 6667411.4546 | 43708586.2023 | 42834414.4782 | As per approved foundation drawing , Item no 7.5 Ii of OPTCL RC 23-24 |  | #REF! | #REF!
3.2.4 | Supply and putting MS liner of nominal thickness 6/8 mm as per approved T.S and as per instructions of engineer in charge for river bed & river bank pile foundation. | MT | 82725.2903 | 18 | 1489055.2249 | 268029.9405 | 1757085.1653 | 18 | 1489055.2249 | 0 | 0% | 18 | 1489055.2249 | 0 |  | 0 | 0 | 1489055.2249 | 268029.9405 | 1757085.1653 | 0
4 | Supply of borrowed earth/morrum for back filling for foundation/revertment works |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4.1 | (i) Up to 30 mtr lead | CUM | 427.3982 | 350 | 149589.3596 | 26926.0847 | 176515.4443 | 0 | 0 | -350 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -176515.4443
4.2 | (ii) Beyond 30 mtr lead | CUM | 437.0897 | 350 | 152981.4085 | 27536.6535 | 180518.0621 | 0 | 0 | -350 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -180518.0621
4.3 | (iii) beyond 100 mtr lead | CUM | 446.7813 | 350 | 156373.4575 | 28147.2223 | 184520.6798 | 350 | 156373.4575 | 0 | 0% | 350 | 156373.4575 | 0 |  | 0 | 0 | 156373.4575 | 28147.2223 | 184520.6798 | 0
5 | SHORING & SHUTTERING- Required in wet/submerged or special locations of open cast/shallow type foundations with supply of all materials,T&P and Labour. | SQ.MTR. | 455.5037 | 6300 | 2869673.4283 | 516541.2171 | 3386214.6453 | 0 | 0 | -6300 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -3386214.6453 | As per approved foundation drawing and site requirement
6 | Head-Loading of all types of foundation-materials, towers, structures, conductors, Insulators, Hard-wares for inaccessible Locations beyond 400 mtrs from the nearest approach road as per the recommendation of site Engineer-In- Charge and approval of the General Manager of Concerned circle. | MT-Mtr | 7.7533 | 210001 | 1628191.2586 | 293074.4266 | 1921265.6852 | 210001 | 1628191.2586 | 0 | 0% | 210001 | 1628191.2586 | 0 |  | 0 | 0 | 1628191.2586 | 293074.4266 | 1921265.6852 | 0 | As per site requirement
7 | DE-WATERING ( for water logged and open cast foundations) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | With Supply of all T&P, Fuel, Lubricant & electricity on HP Hour basis. | HP Hour | 178.3249 | 7500 | 1337436.4509 | 240738.5612 | 1578175.012 | 3500 | 624137.0104 | -4000 | -53.33% | 3500 | 624137.0104 | 0 |  | 0 | 0 | 624137.0104 | 112344.6619 | 736481.6723 | -841693.3397 | As per site requirement
8 | WELDING OF TOWER MEMBERS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
8.1 | Supply of all materials for continuous welding of bolts & nuts (around the bolts) up to top of tower without cross arm, including welding rods, welding generator machine (diesel engine operator), application of required zinc rich paints around the welding portion after welding (two coats), fuel, lubricants,T&P and labours and other arrangements etc. | Nos. | 11.6299 | 164996 | 1918884.0404 | 345399.1273 | 2264283.1677 | 164996 | 1918884.0404 | 0 | 0% | 164996 | 1918884.0404 | 0 |  | 0 | 0 | 1918884.0404 | 345399.1273 | 2264283.1677 | 0 | As per approved structure drawing
9 | PAINTING OF TOWER LEGS |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9.1 | Supply and painting over tower structure by applying one coat of zinc phosphate primer of ASIAN/BERGER make, 2coats of Aluminium paint of ASIAN/BERGER make and applying one coat of black enamel paint over tower legs up to a height of 1mtr. Including cost of material, consumables, T&P and as per instruction of the engineer in charge.(Scrapping and washing of the structures are to be done prior to painting of towers) | SQ.MTR. | 237.4434 | 200 | 47488.6856 | 8547.9634 | 56036.649 | 200 | 47488.6856 | 0 | 0% | 200 | 47488.6856 | 0 |  | 0 | 0 | 47488.6856 | 8547.9634 | 56036.649 | 0 | As per site requirement
10 | REVETMENT: (including Benching) Supply of all materials like cement, Late-rite stone (stone masonry) all type aggregates, labours, & T&P for construction of revetment walls as per requirement to protect the towers, where felt unsafe and as per approved drawing and the direction of Engineer in charge. This includes supply of all labourers, T&P and dewatering (including Supply of all T&P, Fuel, Lubricant & electricity etc. as per Technical specification and instruction of Engineer In charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Excavation in all type of soil including rock & back filling including supply of sand with back filling. | CUM | 356.6497 | 75 | 26748.729 | 4814.7712 | 31563.5002 | 0 | 0 | -75 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -31563.5002
10.2 | Lean Concrete in the ratio1:3:6(Grade M-10) including supply of sand chips etc. | CUM | 6382.867 | 7 | 44680.069 | 8042.4124 | 52722.4815 | 0 | 0 | -7 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -52722.4815
10.3 | PCC in the ratio 1:2:4(Grade M-15) as above. | CUM | 7693.1671 | 13 | 100011.1718 | 18002.0109 | 118013.1827 | 0 | 0 | -13 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -118013.1827
10.4 | RR Massonary work in the ratio 1:5. | CUM | 5770.3599 | 75 | 432776.9907 | 77899.8583 | 510676.849 | 0 | 0 | -75 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -510676.849
11 | Cable trench for 220kVUG CABLE for DC Line with Gantry ,LA,SI and CSE. This includes supply of all labourers, T&P and dewatering (including Supply of all T&P, Fuel, Lubricant & electricity etc. as per Technical specification and instruction of Engineer In charge. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | Excavation in all type of soil including rock & back filling including supply of sand with back filling | Cum | 172.5099 | 2325.65 | 401197.6932 | 72215.5848 | 473413.2779 | 2662.2 | 459255.9064 | 336.55 | 14.47% | 2662.2 | 459255.9064 | 0 |  | 0 | 0 | 459255.9064 | 82666.0632 | 541921.9696 | 68508.6916
11.2 | Lean Concrete in the ratio 1:3:6(Grade-M10) including supply of sand, chips etec. | Cum | 6146.3927 | 102.53 | 630189.6469 | 113434.1364 | 743623.7833 | 461.97 | 2839449.0508 | 359.44 | 350.6% | 128.1625 | 787737.0586 | 333.8075 | 5513.48 | 5513.48 | 1840440.9751 | 2628178.0337 | 473072.0461 | 3101250.0798 | 2357626.2965 | As per approved foundation drawing , Item no 6.2 iII of OPTCL RC 23-24
11.3 | Providing & Laying of RCC work of ratio 1:1.5:3(Grade M20) with approved quality stone chips of nominal size 12mm to 20mm including labours & T & P as per specification | Cum | 9260.2937 | 416.79 | 3859597.8058 | 694727.605 | 4554325.4108 | 1244.97 | 11528787.8314 | 828.18 | 198.7% | 520.9875 | 4824497.2572 | 723.9825 | 7870.43 | 7870.43 | 5698053.5875 | 10522550.8447 | 1894059.152 | 12416609.9967 | 7862284.5859 | As per approved foundation drawing , Item no 6.4 i of OPTCL RC 23-24
11.4 | Steel of different size(as per design) with cutting ,bending in position of MS Rod (FE-500-TATA/ RINL/ Sail/JINDAL) as per BIS-1786 ) for reinforcement of foundation concrete of towers(open cast) including supply of binding wire(with supply of steel rod FE-500 as per BIS-1786) | MT | 72942.621 | 73.5 | 5361282.6466 | 965030.8764 | 6326313.5229 | 182.0248 | 13277365.496 | 108.5248 | 147.7% | 91.875 | 6701603.3082 | 90.1498 | 68623.36 | 68623.36 | 6186381.699 | 12887985.0072 | 2319837.3013 | 15207822.3085 | 8881508.7855 | As per approved foundation drawing , Item no 6.5 i of OPTCL RC 23-24
12 | Railway, NHAI, Water,Gas/Oil pipeline, Power line and other statutory/government body clearances except Forest clearance (excluding payment of statutory fees) have to be obtained by submitting the required docuemnts to the concerned departments through OPTCL. The documents for above clearances including required drawings etc. have to be submitted by the contractor within 05 months of award of contract. Beyond the above period, L.D is applicable & the amount shall be deducted as specified in the specification. | LS | 759818.9692 | 1 | 759818.9692 | 136767.4145 | 896586.3836 | 1 | 759818.9692 | 0 | 0% | 1 | 759818.9692 | 0 |  | 0 | 0 | 759818.9692 | 136767.4145 | 896586.3836 | 0
13 | Forest clearances (excluding payment of statutory fees) has to be obtained by submitting the required docuemnts to the concerned departments through OPTCL. The documents for above clearances including required drawings etc. have to be submitted by the contractor within 05 months of award of contract. Beyond the above period, L.D is applicable & the amount shall be deducted as specified in the specification. | Hectare | 94977.3711 | 3.2 | 303927.5877 | 54706.9658 | 358634.5535 | 3.2 | 303927.5877 | 0 | 0% | 3.2 | 303927.5877 | 0 |  | 0 | 0 | 303927.5877 | 54706.9658 | 358634.5535 | 0
14 | Right of Way compensation (including land damage, crop damage & tree removal etc.) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
14.1 | Per location for foundation and erection of tower | Per Loc. | 56986.4227 | 131 | 7465221.3722 | 1343739.847 | 8808961.2192 | 134 | 7636180.6403 | 3 | 2.29% | 134 | 7636180.6403 | 0 |  | 0 | 0 | 7636180.6403 | 1374512.5153 | 9010693.1555 | 201731.9363
14.2 | Per kilometer for stringing | Per Km. | 75981.8969 | 35 | 2659366.3921 | 478685.9506 | 3138052.3427 | 35 | 2659366.3921 | 0 | 0% | 35 | 2659366.3921 | 0 |  | 0 | 0 | 2659366.3921 | 478685.9506 | 3138052.3427 | 0 | As per approved route length
15 | PTCC approval has to be obtained by submitting the required documents to the concerned department through OPTCL & any other charges are to be borne by the bidders. The documents for PTCC clearance including required drawings etc has to be submitted by the contractor within 5 months of award of contract. Beyond the above period L.D as applicable & the amount shall be deducted as specified in the specification. | LS | 142466.0567 | 1 | 142466.0567 | 25643.8902 | 168109.9469 | 1 | 142466.0567 | 0 | 0% | 1 | 142466.0567 | 0 |  | 0 | 0 | 142466.0567 | 25643.8902 | 168109.9469 | 0
B | CIVIL COMPONENT OF THE WORKS CONTRACT FOR 220 KV TRANSMISSION LINE-PARADEEP-ERSAMA |  |  |  | 122276432.8626 | 22009757.9153 | 144286190.7778 |  | 325831679.2616 |  | 0% |  | 136112414.0492 |  |  |  | 174598826.3068 | 310711240.356 | 55928023.2641 | 366639263.6201 | 222353072.8423

## C_400kV TL
JV of R S Infraprojects Pvt. Ltd. and M/s. A.K Das Associates Limited
BOQ Amendment Proposal - 1 | [20 empty] | CIVIL - 400kV T/L
Construction of (i) 400KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from Loc no. 358 (dead end tower of proposed GIS at Ersama, Paradeep) to Loc. No. 182 (After Birupa River Crossing towards 400KV New DUBURI gird sub-station) (Approx. line length- 68.3 Kms). (ii) 220KV D/C line using Wind-Zone-VI (55 mtrs/sec) Lattice Towers from proposed GIS at Ersama, Paradeep to existing 220/132/33KV grid sub-station at Paradeep (Approx. line length- 34.871 Kms.). (iii) 2 Nos. 220KV feeder bay extension (AIS) at existing 220/132/33KV grid sub-station, Paradeep for connectivity with proposed GIS S/S at Ersama, Paradeep (GIS)
LOA No.: Sr.GM-CPC-I-Constrn-400&220KV Ersama - Paradeep Line (Pkg-36(II)/ 2020-21)-42/2020/997; dt. 24.12.2021
Sl. No. | DESCRIPTION | UOM | Basic Price per Unit | LOA |  |  |  | Actual |  | Deviation quantity | Deviation Percentage | Within 25% deviation |  | Beyond 25% deviation |  |  |  | Total Revised Price | Total GST in INR (18%) | Total Revised Price (incl. GST) | Differential Amount (BOQ Amount & Amended Amount) including GST | Remarks
|  |  |  | Qty | Amount | Total GST @18% | Total Amount Including GST | Qty | Amount as per LOA |  |  | Qty | Amount | Qty | Rate Contract Rate | Least Cost | Amount
B | CIVIL WORKS |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | FOUNDATION MATERIALS: Supply of all materials like Cement, steel, all coarse aggregates, fine aggregates and making foundations of the required above mentioned type towers as per the direction laid down in the technical specification and the direction of the site- in charge.This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Excavation in all type soil and rocks and back filling (back filling shall be done in layers and disposed of excess quantity of excavated soil at suitable place after back filling), & if required for filling the foundation, borrowed earth/murrum/sand shall be brought for filling and compaction, including supply of sand, all T&P, labour as required. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Soft/Loose Soil | CUM | 140.5277 | 10000 | 1405277.4303 | 252949.9374 | 1658227.3677 | 8742 | 1228493.5295 | -1258 | -12.58% | 8742 | 1228493.5295 | 0 |  | 0 | 0 | 1228493.5295 | 221128.8353 | 1449622.3648 | -208605.0029
1.1.2 | Dense/Compact Soil | CUM | 525.283 | 13650 | 7170113.1119 | 1290620.3601 | 8460733.472 | 5830 | 3062399.9591 | -7820 | -57.29% | 5830 | 3062399.9591 | 0 |  | 0 | 0 | 3062399.9591 | 551231.9926 | 3613631.9518 | -4847101.5202
1.1.3 | Soft rock/Disintegrated rock (not requiring blasting) | CUM | 525.283 | 1900 | 998037.7225 | 179646.7901 | 1177684.5126 |  | 0 | -1900 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1177684.5126
1.1.4 | Hard rock (requiring blasting/using breaker machinery) | CUM | 876.1178 | 1700 | 1489400.2447 | 268092.044 | 1757492.2887 |  | 0 | -1700 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1757492.2887
1.1.5 | Fully submerged soil | CUM | 210.307 | 21200 | 4458509.1656 | 802531.6498 | 5261040.8154 |  | 0 | -21200 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -5261040.8154
1.1.6 | Partially submerged soil | CUM | 210.307 | 22700 | 4773969.7198 | 859314.5496 | 5633284.2693 |  | 0 | -22700 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -5633284.2693
1.2 | Design, Engineering, Providing and laying of plain Cement concrete (PCC 1:3:6) of grade M10 with approved quality coarse aggregates (Nominal size 12mm to 20mm) , fine aggregates, Cement in tower foundation as blind layer inclusive of labour charges for concrete mixing & curing. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. | CUM | 7418.8957 | 1600 | 11870233.0798 | 2136641.9544 | 14006875.0342 | 1165 | 8643013.4612 | -435 | -27.19% | 1165 | 8643013.4612 | 0 |  | 0 | 0 | 8643013.4612 | 1555742.423 | 10198755.8842 | -3808119.1499 | As per approved drawing and site requirement
1.3 | Design, Engineering and laying of reinforced cement concrete (RCC1:1.5:3) of grade M20 for open cast foundation and pile caping, riser and tie beam for under ream/DMC (500 mm dia) and reverbed pile (1000 mm dia) with supply of approved quality coarse aggregates(Nominal size 12mm to 20mm), fine aggregates, cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample cement concrete cubes as per IS. The surrounding area shall be clear from materials. Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P and dewatering wherever required as per Technical specification and instruction of Engineer In charge. | CUM | 9651.8331 | 20370 | 196607839.3038 | 35389411.0747 | 231997250.3785 | 17825 | 172043924.1821 | -2545 | -12.49% | 17825 | 172043924.1821 | 0 |  | 0 | 0 | 172043924.1821 | 30967906.3528 | 203011830.5349 | -28985419.8436
1.4 | Design, Engineering and laying of reinforced Cement concrete (RCC 1:1::2) of grade M25 for pile (1000 mm dia) foundation with supply of approved quality coarse aggregates (Nominal size 12mm to 20mm), fine aggregates, Cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample Cement concrete cubes as per IS. The surrounding area shall be clear from materials, Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. | CUM | 11413.7602 | 1980 | 22599245.2043 | 4067864.1368 | 26667109.341 | 2330 | 26594061.2757 | 350 | 17.68% | 2330 | 26594061.2757 | 0 | 8875.81 | 0 | 0 | 26594061.2757 | 4786931.0296 | 31380992.3054 | 4713882.9643 | As per approved foundation drawing (Item 6.7i of RC OPTCL 23-24)
1.5 | Design, Engineering and laying of reinforced Cement concrete (RCC 1:1.5:3) of grade M20 for under ream and DMC (500 mm dia) foundation with supply of approved quality coarse aggregates (Nominal size 12mm to 20mm), fine aggregates, Cement in tower foundation and inclusive of labour charges for concrete mixing, supply and fixing of form boxes, curing, shoring, shuttering, testing of sample Cement concrete cubes as per IS. The surrounding area shall be clear from materials, Damage of land if any by the contractor shall be repaired before measurement. This includes supply of all labourers, T&P as per Technical specification and instruction of Engineer In charge. | CUM | 10267.2477 | 2550 | 26181481.5138 | 4712666.6725 | 30894148.1863 | 16015 | 164429971.1542 | 13465 | 528% | 3187.5 | 32726851.8922 | 12827.5 | 7870.43 | 7870.43 | 100957940.825 | 133684792.7172 | 24063262.6891 | 157748055.4063 | 126853907.2201 | As per approved foundation drawing (Item 6.4i of RC OPTCL 23-24)
1.6 | Cutting, bending, hooking, fixing and binding in poisition of MS Rod (FE-500-TATA/ RINL/ Sail/JINDAL) as per BIS-1786 for rainforCement of foundation concrete of towers including supply of wire for binding (With supply of steel rod FE-500 as per BIS-1786 of different size(as per design). | MT | 65752.4464 | 2825 | 185750661.0319 | 33435118.9857 | 219185780.0176 | 3056 | 200939476.1464 | 231 | 8.177% | 3056 | 200939476.1464 | 0 |  | 0 | 0 | 200939476.1464 | 36169105.7063 | 237108581.8527 | 17922801.8351 | As per approved foundation drawing
1.7 | Pile foundation: Boring for under ream cast in situ piling with bentonite sowing for stabilization of bore. |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1.5.1 | Boring for under reamed cast in situ piling with betonite sowing for stabilisation of bore pile diameter (500mm) & approximate length of the bore is 10 Mtrs to 12 Mtrs with under reem in sandy and submerged soil | mtr length | 1643.69 | 12852 | 21124704.0724 | 3802446.733 | 24927150.8054 | 26900 | 44215261.4026 | 14048 | 109.3% | 16065 | 26405880.0905 | 10835 | 1470.26 | 1470.26 | 15930267.1 | 42336147.1905 | 7620506.4943 | 49956653.6847 | 25029502.8793 | Item 7.1(Vi) of RC of optcl 23-24
1.5.2 | Boring by DMC method piling with betonite sowing for stabilisation of bore pile diameter (1000mm) for approximate length of the bore is 25 Mtrs to 30 Mtrs in river bed and river bank & for others 1000 dia bore for 15.5 m to 30 m | mtr length | 7559.4234 | 2520 | 19049747.0131 | 3428954.4624 | 22478701.4755 | 20168 | 152458451.4921 | 17648 | 700.3% | 3150 | 23812183.7664 | 17018 | 6462.95 | 6462.95 | 109986483.1 | 133798666.8664 | 24083760.0359 | 157882426.9023 | 135403725.4269 | As per approved soil test report and foundation drawing (Item 7.5(ii) of RC of optcl 23-24)
1.5.3 | Supply and putting of MS Liner 8mm (or as per approved drawing)for river bed & river bank pile foundation. | MT | 82027.4973 | 360 | 29529899.042 | 5315381.8276 | 34845280.8696 | 172.1664 | 14122378.9179 | -187.8336 | -52.18% | 172.1664 | 14122378.9179 | 0 |  | 0 | 0 | 14122378.9179 | 2542028.2052 | 16664407.1231 | -18180873.7465 | For riverbed pile foundation as per site requirement
2 | SURVEY OF LINE & PREPARATION LAND SCHEDULE: Supply of required T&P’s, Technical personnel’s, labours for conducting |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Preliminary survey :- Making walkover survey ascertaining feasible route and marking on Toposheet ,preparation of route alignment map. | RKms. | 11683.1858 | 68.3 | 797961.5907 | 143633.0863 | 941594.677 | 37.672 | 440128.9758 | -30.628 | -44.84% | 37.672 | 440128.9758 | 0 |  | 0 | 0 | 440128.9758 | 79223.2156 | 519352.1914 | -422242.4856
2.2 | Check survey including supply of all labour, T&P as per instruction of Engineer in Charge and as per the approved profile. | RKms. | 9346.5486 | 68.3 | 638369.2726 | 114906.4691 | 753275.7416 | 68.448 | 639752.5618 | 0.148 | 0.2167% | 68.448 | 639752.5618 | 0 |  | 0 | 0 | 639752.5618 | 115155.4611 | 754908.0229 | 1632.2813
2.3 | Detail survey with Preparation of Land Schedule:- Detail survey including taking of levels, profile plotting, tower spotting , marking of tower locations at site and preparation of tower schedule incluiding showing P&T, Power lines, Railway lines and river crossing, roads & submission of route map, profile & survey report etc. The P&T lines and railway lines for a minimum distance of 8 kms on either side of alignment shall be clearly indicated. It also includes preparation of land schedule with plot No., Mouza on Revenue map indicating alignment therein duly authenticated by Revenue inspector & Tehsildar, Enumeration of trees with the help of forest officers & other prominent features required for alignment of line. | Rkm | 11683.1858 | 68.3 | 797961.5907 | 143633.0863 | 941594.677 | 37.672 | 440128.9758 | -30.628 | -44.84% | 37.672 | 440128.9758 | 0 |  | 0 | 0 | 440128.9758 | 79223.2156 | 519352.1914 | -422242.4856
2.4 | Soil Investgation as per specification |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.4.1 | Normal foundation(Boring upto 3mtr,5 mtr, 7mtr depth.) | Per Mtr | 953.6503 | 1043 | 994657.3034 | 179038.3146 | 1173695.6181 | 31.5 | 30039.9857 | -1011.5 | -96.98% | 31.5 | 30039.9857 | 0 |  | 0 | 0 | 30039.9857 | 5407.1974 | 35447.1831 | -1138248.435
2.4.2 | For dis-integrated rock | per mtr | 1671.7956 | 35 | 58512.8447 | 10532.3121 | 69045.1568 | 0 | 0 | -35 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -69045.1568
2.4.3 | River bed pile foundation( Boring to 30mtr depth) | per mtr | 5015.3867 | 1140 | 5717540.8274 | 1029157.3489 | 6746698.1764 | 690 | 3460616.8166 | -450 | -39.47% | 690 | 3460616.8166 | 0 |  | 0 | 0 | 3460616.8166 | 622911.027 | 4083527.8436 | -2663170.3328
3 | Shoring and Shuttering required in wet or special location with supply of all T & P and labour. | Sq m | 408.9842 | 3054 | 1249037.7164 | 224826.789 | 1473864.5053 | 0 | 0 | -3054 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1473864.5053
4 | Head-Loading of all types of foundation-materials, towers, structures, conductors, Insulators, Hard-wares for inaccessible Locations beyond 400 mtrs from the nearest approach road as per the recommendation of site Engineer-In- Charge and approval of the General Manager of Concerned circle. | MT-Mtr | 5.8149 | 208500 | 1212415.2174 | 218234.7391 | 1430649.9565 | 208500 | 1212415.2174 | 0 | 0% | 208500 | 1212415.2174 | 0 |  | 0 | 0 | 1212415.2174 | 218234.7391 | 1430649.9565 | 0 | As per site requirement
5 | DE-WATERING ( for water logged and open cast foundations) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5.1 | With Supply of all T&P, Fuel, Lubricant & electricity on HP Hour basis. | HP Hour | 178.3249 | 3500 | 624137.0104 | 112344.6619 | 736481.6723 |  | 0 | -3500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -736481.6723 | As per site requirement
6 | Painting of Tower Structures by applying one coat of zinc phosphate primer of ASIAN / BERGER make, 2 coats of Aluminium paint of ASIAN/BERGER make and applying one coat of black enamel paint over tower legs up to height of 1 mtr. including cost of material, consumables, T&P and as per the instruction of the Engineer in Charge (Scrapping and washing of structures are to be done prior to painting of towers) and applying | Per SQm | 256.8266 | 56.32 | 14464.4721 | 2603.605 | 17068.0771 | 100 | 25682.6565 | 43.68 | 77.56% | 70.4 | 18080.5902 | 29.6 | 122.52 | 122.52 | 3626.592 | 21707.1822 | 3907.2928 | 25614.475 | 8546.3978 | OPTCL RC 2023-24 SL. NO. 17
7 | REVETMENT: (including Benching) Supply of all materials like Cement, Late-rite stone (stone masonry) all type aggregates, labours, & T&P for construction of revetment walls as per requirement to protect the towers, where felt unsafe and as per approved drawing and the direction of Engineer in charge. |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
7.1 | Excavation in all type of soil including rock & back filling including supply of sand with back filling. | CUM | 360.5263 | 500.03 | 180273.9896 | 32449.3181 | 212723.3077 |  | 0 | -500.03 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -212723.3077
7.2 | Lean Concrete in the ratio1:3:6(Grade M-10) including supply of sand chips etc. | CUM | 7418.8957 | 26 | 192891.2875 | 34720.4318 | 227611.7193 |  | 0 | -26 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -227611.7193
7.3 | PCC in the ratio 1:2:4(Grade M-15) as above. | CUM | 8645.8482 | 100 | 864584.8245 | 155625.2684 | 1020210.0929 |  | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1020210.0929
7.4 | RR Massonary work in the ratio 1:5. | CUM | 2921.0387 | 485 | 1416703.7895 | 255006.6821 | 1671710.4716 | 0 | 0 | -485 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1671710.4716
8 | PTCC approval has to be obtained by submitting the required documents to the concerned department through OPTCL & any other charges are to be borne by the bidders. The documents for PTCC clearance including required drawings etc has to be submitted by the contractor within 5 months of award of contract. Beyond the above period L.D as applicable & the amount shall be deducted as specified in the specification. | LS | 389410.1292 | 1 | 389410.1292 | 70093.8233 | 459503.9524 | 1 | 389410.1292 | 0 | 0% | 1 | 389410.1292 | 0 |  | 0 | 0 | 389410.1292 | 70093.8233 | 459503.9524 | 0
9 | Railway, NHAI, Water,Gas/Oil pipeline, Power line and other statutory/government body clearances except Forest clearance (excluding payment of statutory fees) have to be obtained by submitting the required docuemnts to the concerned departments through OPTCL. The documents for above clearances including required drawings etc. have to be submitted by the contractor within 05 months of award of contract. Beyond the above period, L.D is applicable & the amount shall be deducted as specified in the specification. | LS | 584158.3212 | 1 | 584158.3212 | 105148.4978 | 689306.8191 | 1 | 584158.3212 | 0 | 0% | 1 | 584158.3212 | 0 |  | 0 | 0 | 584158.3212 | 105148.4978 | 689306.8191 | 0
10 | Forest clearances (excluding payment of statutory fees) has to be obtained by submitting the required docuemnts to the concerned departments through OPTCL. The documents for above clearances including required drawings etc. have to be submitted by the contractor within 05 months of award of contract. Beyond the above period, L.D is applicable & the amount shall be deducted as specified in the specification. | Hectare | 597097.5343 | 5.5 | 3284036.4388 | 591126.559 | 3875162.9978 | 5.5 | 3284036.4388 | 0 | 0% | 5.5 | 3284036.4388 | 0 |  | 0 | 0 | 3284036.4388 | 591126.559 | 3875162.9978 | 0 | As per site requirement
11 | Right of Way compensation (including land damage, crop damage & tree removal etc.) |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
11.1 | Per location for foundation and erection of tower | Per Loc. | 145083.7494 | 176 | 25534739.889 | 4596253.18 | 30130993.0691 | 185 | 26840493.6334 | 9 | 5.114% | 185 | 26840493.6334 | 0 |  | 0 | 0 | 26840493.6334 | 4831288.854 | 31671782.4874 | 1540789.4183
11.2 | Per kilometer for stringing | Per Km. | 93465.4865 | 68.3 | 6383692.7255 | 1149064.6906 | 7532757.4161 | 68.448 | 6397525.6175 | 0.148 | 0.2167% | 68.448 | 6397525.6175 | 0 |  | 0 | 0 | 6397525.6175 | 1151554.6112 | 7549080.2287 | 16322.8126 | As per approved route alignment
C | TOTAL OF CIVIL COMPONENT OF THE WORKS CONTRACT FOR 400 KV TRANSMISSION LINE-ERSAMA-LOC-358 to LOC-182) |  |  |  | 583944666.8965 | 105110040.0414 | 689054706.9379 |  | 831481820.8505 |  | 0 |  | 553315450.4843 |  |  |  | 226878317.617 | 780193768.1013 | 140434878.2582 | 920628646.3595 | 231573939.4216